## 📋 Overview
BlazeUp Partner Platform — Requirements Tracker
PRD v1.8 · 2026-05-15 · Author: BlazeUp Admin
Document Status | PRD — All 6 BLOCKING items resolved. Build can start.
PRD Version | v1.8 (supersedes v1.1)
Last Updated | 2026-05-15
Author | BlazeUp Admin
Scope | Channel Partners only (Referral, Reseller/VAR, SI, MSP). Pack Partners are out-of-scope (see marketplace-pack-architecture-v1.1.md).
Critical Path | ms-sa-partners core + Renil-locked surface + CRM bridge + portal deal registration + SA approval queue = ~7 weeks to v1
Full Build ETA | ~14 weeks (all pages + SA module + attribution)
Auth Gate | B1 — Auth Hardening Phase 0 PRs #633–#641 must merge before partner auth surfaces go live. All non-auth coding proceeds in parallel.
Key Architecture | BlazeUp does NOT build a separate SA CRM. Dogfood tenant at blazeup.blazeup.ai is the only CRM. Partner deals auto-appear as opportunities with source='partner_registered'.
Repo / Services | blazeup-microservice-sa-partners · blazeup-hostapp-partner (pp- prefix) · blazeup-subapp-sa-partners · blazeup-subapp-partner-dashboard · blazeup-subapp-partner-training
Partner Portal URL | partner.blazeup.ai
SHEET INDEX
📋 Overview | This sheet — PRD metadata and index
🎯 Feature Requirements | All features by section/number with FE·BE status, confirm flag, notes
⚠️ Risk Register | 8 risk flags (R1–R8) with severity, impact, mitigation and tracking
❓ Open Questions | Blocking (B1-B6), non-blocking (OQ), and Legal/Compliance items
🗃️ Data Models | MongoDB collections and key schema fields
📡 Kafka Events | All Kafka event names, purpose, triggers, consumers
🔌 API Endpoints | All REST API routes with method, auth, description, status

## 🎯 Feature Requirements
Section # | Feature / Requirement | Description / Details | Priority | Confirmed? | Confirm Note / Owner | ETA | FE Status | FE Note | ETA | BE Status | BE Note | ETA | Blocker / Dependency | Remarks | Test Case IDs
§1 — Context & Strategic Fit
1.1 | Foundational Architecture: No SA CRM | BlazeUp does NOT build a separate SA CRM. Dogfood tenant (blazeup.blazeup.ai) is the only CRM. Partner-registered deals appear as opportunities with source='partner_registered'. Architectural invariant — not a product decision. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | N/A |  |  | B1 Auth Phase 0 | §6 CRM Integration governs this | —
1.2 | Two Partner Populations: Channel vs Pack | Channel Partners (Resellers, referral agents, SIs, MSPs) live at partner.blazeup.ai. Pack Partners (ISVs) are managed in SA Tier K. A company can hold both; managed independently with separate credentialing and portals. | Critical | Rejected / On Hold |  | 2026-05-27 | Not Started |  |  | Done |  |  |  | This PRD covers Channel Partners only | PARTNER_API_COMMISSIONS_PAYOUTS_015: BLOCKED
1.3 | Product Moat: Native Client Health Data | Partner portal exposes client DAU/MAU trend, module adoption depth, renewal date, AI-generated upsell signals — because BlazeUp IS the platform. No integration needed. Primary retention lever for channel programme. | High | Planned |  |  | Not Started |  |  | Not Started |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_002: BLOCKED PARTNER_UI_MY_CLIENTS_003: NOT_STARTED PARTNER_UI_MY_CLIENTS_008: NOT_STARTED PARTNER_UI_MY_CLIENTS_010: NOT_STARTED
§2 — Partner Programme Structure
2.1 | 4-Tier Partner Tiers: Registered / Select / Advanced / Premier | Registered ($0), Select ($50K ARR), Advanced ($200K ARR), Premier ($750K ARR). Tier calc: trailing-12M ARR sourced through BlazeUp, computed on first day of each quarter. Upgrade immediate; downgrade with 30-day notice + grace quarter. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_008: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_009: BLOCKED PARTNER_UI_DASHBOARD_003: NOT_STARTED PARTNER_UI_DASHBOARD_005: NOT_STARTED PARTNER_UI_DASHBOARD_006: NOT_STARTED
2.1a | PSM Allocation: Dedicated at $1.5M within Premier | Dedicated PSM only at $1.5M ARR within Premier tier. Below $1.5M: shared PSM at max 1:3 ratio. Advanced tier also uses shared pool (1:3). Reviewed annually. managerAllocation field on partner_accounts. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-25) | 2026-05-27 | Not Started |  |  | Not Started |  |  |  | Locked decision | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_008: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_009: BLOCKED PARTNER_UI_DASHBOARD_003: NOT_STARTED PARTNER_UI_DASHBOARD_005: NOT_STARTED PARTNER_UI_DASHBOARD_006: NOT_STARTED
2.2 | 4 Partner Types: Referral / Reseller/VAR / SI / MSP | Referral (billing: direct), Reseller/VAR (billing: reseller), SI (billing: direct), MSP (billing: partner_managed). Type selected at registration. Determines deal flows and billing models available. | Critical | Confirmed | Focus on a flow with a simple partner type first | 2026-05-27 | Done |  |  | Done |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_008: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006: BLOCKED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED
2.2a | Reseller Pricing Authority | Reseller sets own end-client price. BlazeUp invoices partner at tier discount. BlazeUp does NOT capture partner's sell price anywhere. Reseller also has authority to create/edit own Custom Plan (module bundle + pricing + seat), scoped to plans they created — no visibility or edit rights on SA-created plans (same self-service model as MSP, see §9.2). Standard VAR norm | High | Confirmed | Locked — Renil 2026-05-08 (OQ-19) | 2026-05-27 | Not Started |  |  | Done |  |  |  | Locked decision | PARTNER_API_CLIENT_HEALTH_MSP_008: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006: BLOCKED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED
2.2b | MSP Tier Qualification: Total ARR Managed | MSP trailing-12M ARR for tier qualification = total ARR managed (all client subscriptions billed through them), NOT only net-new logos. Reflects ongoing managed relationship value. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-21) Custom Plan self-service authority extended to Reseller | 2026-05-27 | Done |  |  | N/A |  |  |  | Locked decision | PARTNER_API_CLIENT_HEALTH_MSP_008: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006: BLOCKED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED
2.3 | Deal Types: Referral / Reseller / Co-sell | Referral (tier referral rate × Y1 ACV), Reseller (margin = list − discount), Co-sell (70/30 default split; override above $100K ACV requires partner agreement in writing, locked at approval). | Critical | Confirmed | Focus on a flow with a simple deal type first | 2026-05-27 | Done |  |  | Done |  |  |  | §3 Scenarios A/B/C | PARTNER_API_DEAL_REGISTRATION_PIPELINE_011: BLOCKED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_010: NOT_STARTED
2.4 | Certification Programme: 4 Certifications | BlazeUp Sales Certified (4h), HR Specialist (6h), CRM Specialist (4h), Implementation Certified (12h). Completion triggers tier re-evaluation. Certificates manually assigned by SA — no partner portal training module/LMS (training portal dropped from scope). | Medium | Confirmed | OQ-8 resolved 08/06 MM — training portal dropped, SA manually assigns certificates | 2026-05-27 | Not Started |  |  | Done |  |  |  |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010: PASSED PARTNER_UI_TRAINING_001: NOT_STARTED PARTNER_UI_TRAINING_002: NOT_STARTED PARTNER_API_CERTIFICATIONS_SA_001: NOT_STARTED PARTNER_API_CERTIFICATIONS_SA_002: PASSED PARTNER_API_CERTIFICATIONS_SA_003: PASSED PARTNER_API_CERTIFICATIONS_SA_004: PASSED
§3 — Deal Scenarios (A–I)
3-A | Scenario A: Pure Referral | Partner introduces prospect, steps back. Registers deal. BlazeUp sales owns close. Commission = tier referral rate × Y1 ACV. Partner sees read-only pipeline view. BlazeUp rep visible with name/photo; partner can message on deal thread. | Critical | Confirmed | Focus on this scenario first | 2026-05-27 | Done |  |  | Done |  |  |  |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_001: PASSED PARTNER_UI_MY_PIPELINE_029: NOT_STARTED
3-B | Scenario B: Reseller-Led | Partner sells independently. Registers deal upfront. Marks Won when client signs. Tenant provisioned. BlazeUp invoices partner at reseller discount. Partner invoices client at their own price (not captured by BlazeUp). | Critical | Confirmed | Focus on this scenario second | 2026-05-27 | Not Started |  |  | Done |  |  |  |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_002: PASSED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED
3-C | Scenario C: Co-sell (Collaborative) | Partner registers + selects Co-sell. BlazeUp assigns rep within 1 business day. Shared deal record with notes, docs, stage updates. Default 70/30 split. Override above $100K ACV: SA proposes → partner accepts in portal. Split locked at approval. | Critical | Confirmed | Locked — Renil 2026-05-08 (OQ-23) | 2026-05-27 | In Progress |  |  | Done |  |  |  | Locked decision | PARTNER_API_DEAL_REGISTRATION_PIPELINE_003: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_011: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_012: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010: BLOCKED PARTNER_UI_MY_PIPELINE_010: NOT_STARTED PARTNER_UI_MY_PIPELINE_016: NOT_STARTED PARTNER_UI_MY_PIPELINE_017: NOT_STARTED PARTNER_UI_MY_PIPELINE_018: NOT_STARTED PARTNER_UI_MY_PIPELINE_027: NOT_STARTED
3-D | Scenario D: Deal Conflict Resolution | Two parties register same domain. Rules in order: (1) prospect confirmed engagement with first party wins; (2) first-registered wins; (3) SA mediates within 5 business days. Loser can re-register after 90 days if no deal closes. | Critical | Confirmed | OQ-17 (90-day auto-unlock vs manual) still open | 2026-05-27 | Done |  |  | Done |  |  | OQ-17 re-registration mechanism TBD |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_004: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_009: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_013: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_014: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_017: BLOCKED PARTNER_UI_MY_PIPELINE_004: NOT_STARTED PARTNER_UI_MY_PIPELINE_005: NOT_STARTED PARTNER_UI_MY_PIPELINE_021: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_001: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_002: NOT_STARTED
3-E | Scenario E: Referral Link Attribution (No Registration) | Partner shares blazeup.ai/ref/{slug}. Server captures partner_id on first click (30-day TTL, server-side, survives browser close/incognito/device change). On signup: tenant attributed automatically. Commission triggered. Partner notified. | High | Rejected / On Hold |  | 2026-05-27 | N/A |  |  | N/A |  |  |  | R4 risk mitigation | PARTNER_API_COMMISSIONS_PAYOUTS_008: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_009: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_001: BLOCKED
3-F | Scenario F: Expansion at Existing Client | Partner registers expansion deal against existing tenant_id — available only to Reseller & MSP (self-service: partner sets own plan/module bundle + pricing, no SA price approval required before submission). On close: modules/seats added to existing tenant (no new tenant). Expansion commission applies on delta ARR using EN/EE stage of lifecycle model. Referral: no expansion (cycle ends after introduction). Co-sell: not yet decided — see new OQ. | High | Confirmed | Co-sell eligibility pending — new OQ | 2026-05-27 | Not Started |  |  | Not Started |  |  | B6 resolved — rates SA-configurable before launch | Locked decision B6 | PARTNER_API_COMMISSIONS_PAYOUTS_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_004: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006: BLOCKED PARTNER_UI_MY_CLIENTS_004: NOT_STARTED
3-G | Scenario G: MSP Model (Partner Manages Client) | MSP provisions tenants on behalf of clients. BlazeUp invoices MSP. MSP has scoped admin access: configure modules, manage users, raise tickets, view health. Hard limits: no payroll data, no PII above ceiling, no export. Ticket content gated on client opt-in (default OFF). | High | Confirmed | Locked — Renil 2026-05-08 (OQ-22) | 2026-05-27 | Not Started |  |  | N/A |  |  |  |  | PARTNER_API_AUTH_ACCESS_CONTROL_005: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_003: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_004: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_006: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_007: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_009: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_009: BLOCKED PARTNER_UI_MY_CLIENTS_005: NOT_STARTED PARTNER_UI_MY_CLIENTS_006: NOT_STARTED
3-H | Scenario H: Tech Partner Also Resells (Dual Account) | Pack partner + channel partner under one login. Two separate dashboards with a switcher. Revenue share (pack) and channel commissions tracked in completely separate ledgers. | Medium | Awaiting Confirmation |  |  | Not Started |  |  | N/A |  |  |  | Lower priority — complex edge case | PARTNER_API_COMMISSIONS_PAYOUTS_015: BLOCKED PARTNER_UI_PARTNER_PORTAL_SHELL_003: NOT_STARTED
3-I | Scenario I: Multi-Partner Influenced Deal | Two partners touched same prospect; neither registered. Policy: no registration = no commission (absolute rule, no exceptions). If both registered → Scenario D conflict. Incentive to register early. | Medium | Awaiting Confirmation |  |  | N/A |  |  | Done |  |  |  |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_015: BLOCKED PARTNER_UI_MY_PIPELINE_022: NOT_STARTED
§4 — Partner Portal (partner.blazeup.ai)
4.1 | Portal Technical Shell: blazeup-hostapp-partner | New repo, Tailwind prefix pp-. Module Federation host. Separate JWT issuer from tenant and SA. Shared singletons: react, react-dom, react-router aligned with tenant host versions. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  | B1 Auth Phase 0 |  | PARTNER_API_AUTH_ACCESS_CONTROL_001: PASSED PARTNER_API_AUTH_ACCESS_CONTROL_002: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003: PASSED PARTNER_UI_DASHBOARD_001: NOT_STARTED PARTNER_UI_PARTNER_PORTAL_SHELL_002: NOT_STARTED
4.2 | Portal IA: 9 Top-Level Routes | / Home, /deals My Pipeline, /deals/register, /deals/:id, /clients My Clients, /clients/:id, /commissions, /training, /resources, /team, /settings, /support | Critical | Confirmed |  | 2026-05-27 | Not Started |  |  | N/A |  |  |  |  | PARTNER_UI_DASHBOARD_001: NOT_STARTED PARTNER_UI_PARTNER_PORTAL_SHELL_001: NOT_STARTED
4.3 | Dashboard / Home — Actionable Metrics | Pipeline total/count, Commission earned/pending/forecast, Active clients count + renewals <30d, Tier progress bar, ACTION REQUIRED section (co-sell tasks, renewal alerts, rate proposal responses), Mini pipeline kanban, Blazey AI assistant. | High | Confirmed |  | 2026-05-27 | Not Started |  |  | Not Started |  |  |  | No vanity metrics — every number must be actionable. Implemented by GET /v1/partner/portal/deals/stats (own pipeline KPI, JWT-scoped) in addition to /portal/dashboard. Endpoint not enumerated in PRD §8.5; feature itself is Confirmed. Verified 2026-09-24 that it correctly OMITS byProvisioningState (SA-only, §2.1) although the Swagger example shows it. | PARTNER_API_DASHBOARD_DATA_001: PASSED PARTNER_UI_COMMISSIONS_008: NOT_STARTED PARTNER_UI_DASHBOARD_002: NOT_STARTED PARTNER_UI_DASHBOARD_003: NOT_STARTED PARTNER_UI_DASHBOARD_004: NOT_STARTED PARTNER_UI_DASHBOARD_005: NOT_STARTED PARTNER_UI_DASHBOARD_007: NOT_STARTED PARTNER_UI_MY_CLIENTS_001: NOT_STARTED PARTNER_UI_MY_PIPELINE_023: NOT_STARTED PARTNER_API_DASHBOARD_DATA_002: NOT_STARTED PARTNER_API_DASHBOARD_DATA_003: NOT_STARTED
4.4 | Deal Registration Wizard: ≤90 Seconds on Mobile | 4-step: (1) Company+domain — manual entry (Apollo/Clearbit auto-enrichment removed from scope), inline conflict warning; (2) Contact; (3) Deal ACV+date+modules+type; (4) Confirm. LIVE projected commission updates as ACV typed. Immediate confirmation with Deal ID. Design target: 90s on mobile | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  | Most critical flow in entire portal. Wizard lookups implemented by GET /v1/partner/portal/{plans, plans/:planId, countries}. Not enumerated in PRD §8.5. countries returns 250 ISO rows with a case-insensitive partial `search`; feeds prospectCountry (register) and country (win-deal). | PARTNER_API_DEAL_REGISTRATION_PIPELINE_001: PASSED PARTNER_API_SECURITY_COMPLIANCE_002: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011: BLOCKED PARTNER_UI_COMMISSIONS_001: NOT_STARTED PARTNER_UI_MY_PIPELINE_001: NOT_STARTED PARTNER_UI_MY_PIPELINE_002: NOT_STARTED PARTNER_UI_MY_PIPELINE_003: NOT_STARTED PARTNER_UI_MY_PIPELINE_004: NOT_STARTED PARTNER_UI_MY_PIPELINE_006: NOT_STARTED PARTNER_UI_MY_PIPELINE_007: NOT_STARTED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED PARTNER_UI_MY_PIPELINE_010: NOT_STARTED PARTNER_UI_MY_PIPELINE_011: NOT_STARTED PARTNER_UI_MY_PIPELINE_012: NOT_STARTED PARTNER_UI_MY_PIPELINE_013: NOT_STARTED PARTNER_UI_MY_PIPELINE_019: NOT_STARTED PARTNER_UI_MY_PIPELINE_020: NOT_STARTED PARTNER_UI_MY_PIPELINE_021: NOT_STARTED PARTNER_UI_PARTNER_PORTAL_SHELL_002: NOT_STARTED PARTNER_UI_SECURITY_COMPLIANCE_003: NOT_STARTED PARTNER_API_PARTNER_PORTAL_009: PASSED PARTNER_API_PARTNER_PORTAL_010: FAILED (BUG-API-029)
4.4a | Live Commission Projection at Registration | As partner types ACV in Step 3, commission estimate updates in real time (tier rate × ACV). Shows deal protection duration. Answers 'is it worth my time to register?' | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  | Most powerful feature in registration flow | PARTNER_API_DEAL_REGISTRATION_PIPELINE_001: PASSED PARTNER_API_SECURITY_COMPLIANCE_002: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011: BLOCKED PARTNER_UI_COMMISSIONS_001: NOT_STARTED PARTNER_UI_MY_PIPELINE_001: NOT_STARTED PARTNER_UI_MY_PIPELINE_002: NOT_STARTED PARTNER_UI_MY_PIPELINE_003: NOT_STARTED PARTNER_UI_MY_PIPELINE_004: NOT_STARTED PARTNER_UI_MY_PIPELINE_006: NOT_STARTED PARTNER_UI_MY_PIPELINE_007: NOT_STARTED PARTNER_UI_MY_PIPELINE_008: NOT_STARTED PARTNER_UI_MY_PIPELINE_009: NOT_STARTED PARTNER_UI_MY_PIPELINE_010: NOT_STARTED PARTNER_UI_MY_PIPELINE_011: NOT_STARTED PARTNER_UI_MY_PIPELINE_012: NOT_STARTED PARTNER_UI_MY_PIPELINE_013: NOT_STARTED PARTNER_UI_MY_PIPELINE_019: NOT_STARTED PARTNER_UI_MY_PIPELINE_020: NOT_STARTED PARTNER_UI_MY_PIPELINE_021: NOT_STARTED PARTNER_UI_PARTNER_PORTAL_SHELL_002: NOT_STARTED PARTNER_UI_SECURITY_COMPLIANCE_003: NOT_STARTED
4.5 | My Pipeline — Deal List and Detail | Kanban-like list with status filter tabs (All/Registered/Approved/In Progress/Closing/Won/Lost/Rejected), search, deal type + module filters. Deal status icons (🔒 protected, ✅ approved, ⏳ pending, ⚠️ conflict — conflicting deals pinned to top of list). Edition column/tag shows "Custom" for deals with a requested/approved custom plan. Earning info shown only for Cosell and Referral deal types (not Reseller — BlazeUp doesn't capture partner's sell price, see 2.2a). Deal Detail: timeline, shared notes, commission projection, documents, BlazeUp rep contact. | High | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  |  | PARTNER_API_DEAL_COLLABORATION_001: BLOCKED PARTNER_API_DEAL_COLLABORATION_002: BLOCKED PARTNER_API_PIPELINE_MANAGEMENT_001: PASSED PARTNER_API_PIPELINE_MANAGEMENT_002: PASSED PARTNER_UI_MY_PIPELINE_014: NOT_STARTED PARTNER_UI_MY_PIPELINE_015: NOT_STARTED PARTNER_UI_MY_PIPELINE_023: NOT_STARTED PARTNER_UI_MY_PIPELINE_024: NOT_STARTED PARTNER_UI_MY_PIPELINE_025: NOT_STARTED PARTNER_UI_MY_PIPELINE_026: NOT_STARTED PARTNER_UI_MY_PIPELINE_027: NOT_STARTED PARTNER_UI_MY_PIPELINE_028: NOT_STARTED PARTNER_UI_MY_PIPELINE_029: NOT_STARTED PARTNER_API_PARTNER_PORTAL_001: PASSED PARTNER_API_PARTNER_PORTAL_002: PASSED PARTNER_API_PARTNER_PORTAL_003: PASSED PARTNER_API_PARTNER_PORTAL_004: PASSED
4.6 | My Clients — Client Health Dashboard | Book of business (post-close only). Health status (Healthy/At Risk/Inactive), renewal date, modules active. Client Health Card: MAU/DAU stats, module adoption %, support tickets (count+severity, content gated on consent), Blazey Insights panel, renewal pipeline, commission history. | High | Confirmed |  | 2026-05-27 | Not Started |  |  | Not Started |  |  |  | THE product moat | PARTNER_API_CLIENT_HEALTH_MSP_001: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_002: BLOCKED PARTNER_UI_MY_CLIENTS_001: NOT_STARTED PARTNER_UI_MY_CLIENTS_002: NOT_STARTED PARTNER_UI_MY_CLIENTS_003: NOT_STARTED PARTNER_UI_MY_CLIENTS_004: NOT_STARTED PARTNER_UI_MY_CLIENTS_007: NOT_STARTED PARTNER_UI_MY_CLIENTS_008: NOT_STARTED PARTNER_UI_MY_CLIENTS_009: NOT_STARTED PARTNER_UI_MY_CLIENTS_010: NOT_STARTED
4.7 | Commissions & Payouts — Full Transparency | Earned YTD / Pending / Forecast / Paid summary. Per-deal commission table with status (Cosell and Referral deals only — Reseller has no commission line item since BlazeUp doesn't capture partner's sell price, see 2.2a). Commission dispute handled outside system via support ticket — no in-portal dispute flow. Product-failure clawback waiver request flow. Payout details: SWIFT/ACH/NEFT/IMPS/Vietnamese bank. CSFLE-encrypted banking details. | High | Confirmed |  | 2026-05-27 | Done |  |  | Not Started |  |  |  | Dispute Commission dropped 22/06 MM — routed via support ticket. Forecast metric added per PP009. | PARTNER_API_COMMISSIONS_PAYOUTS_002: NOT_STARTED PARTNER_API_COMMISSIONS_PAYOUTS_003: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_004: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_012: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_016: BLOCKED PARTNER_UI_COMMISSIONS_002: NOT_STARTED PARTNER_UI_COMMISSIONS_003: NOT_STARTED PARTNER_UI_COMMISSIONS_004: NOT_STARTED PARTNER_UI_COMMISSIONS_005: NOT_STARTED PARTNER_UI_COMMISSIONS_007: NOT_STARTED PARTNER_UI_COMMISSIONS_009: NOT_STARTED
4.8 | Training & Certification Module | Training portal/LMS dropped from scope. SA manually assigns certificate per partner team member (SA Admin action). Completion still triggers blazeup.partner.certification.earned → tier re-evaluation. | Medium | Confirmed | OQ-8 resolved — no build/buy, manual SA assignment only | 2026-05-27 | Not Started |  |  | Not Started |  |  |  |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010: PASSED PARTNER_UI_TRAINING_001: NOT_STARTED PARTNER_UI_TRAINING_002: NOT_STARTED PARTNER_UI_TRAINING_003: NOT_STARTED
4.9 | Resources: Co-branded Materials + Sandbox | Co-branded pitch decks, product PDFs, battle cards (vs Workday/Darwinbox/Zoho/Salesforce), ROI calculator, pricing sheets, demo sandbox tenant ({slug}-demo.blazeup.ai), API docs for CRM integration. | Medium | Awaiting Confirmation | Sandbox data spec resolved (B5) |  | Not Started |  |  | Not Started |  |  | B5 resolved |  | PARTNER_API_RESOURCES_SANDBOX_001: BLOCKED PARTNER_API_RESOURCES_SANDBOX_002: BLOCKED PARTNER_API_RESOURCES_SANDBOX_003: BLOCKED PARTNER_UI_RESOURCES_001: NOT_STARTED PARTNER_UI_RESOURCES_002: NOT_STARTED PARTNER_UI_RESOURCES_003: NOT_STARTED PARTNER_UI_RESOURCES_004: NOT_STARTED PARTNER_UI_RESOURCES_005: NOT_STARTED
4.9a | Sandbox Demo Tenant + Reset Flow | 3 profiles: SMB (50 emp), Mid-market (200 emp), Enterprise (500 emp). Collections: employees, departments, leave_requests, expense_reports, crm_contacts, crm_deals, assets, tickets. On-demand reset (5 min SLA). Optional weekly auto-reset (default OFF). blazeup.partner.sandbox.reset_requested Kafka event. | Medium | Awaiting Confirmation | Locked — Renil 2026-05-15 (B5) |  | Not Started |  |  | Not Started |  |  | B5 resolved | Locked decision B5 | PARTNER_API_RESOURCES_SANDBOX_001: BLOCKED PARTNER_API_RESOURCES_SANDBOX_002: BLOCKED PARTNER_API_RESOURCES_SANDBOX_003: BLOCKED PARTNER_UI_RESOURCES_001: NOT_STARTED PARTNER_UI_RESOURCES_002: NOT_STARTED PARTNER_UI_RESOURCES_003: NOT_STARTED PARTNER_UI_RESOURCES_004: NOT_STARTED PARTNER_UI_RESOURCES_005: NOT_STARTED
4.10 | Partner Team Management + Referral Links | Team member list (Admin/Member roles), certifications per member, invite new member (Admin role only — Member cannot send invitations). Referral links: default link, per-user links, per-campaign links. Analytics per link: clicks, conversions, ARR attributed. | Medium | Confirmed |  | 2026-05-27 | Done |  |  | N/A |  |  |  |  | PARTNER_API_TEAM_REFERRAL_LINKS_001: BLOCKED PARTNER_API_TEAM_REFERRAL_LINKS_002: BLOCKED PARTNER_UI_PARTNER_TEAM_001: NOT_STARTED PARTNER_UI_PARTNER_TEAM_002: NOT_STARTED PARTNER_UI_PARTNER_TEAM_003: NOT_STARTED PARTNER_API_PARTNER_USERS_001: PASSED PARTNER_API_PARTNER_USERS_002: PASSED PARTNER_API_PARTNER_USERS_003: PASSED
4.11 | MSP Invoice & Refund Management | MSP-only section in Partner Portal. Displays invoices issued by BlazeUp each time the MSP provisions a new managed tenant (billingModel='partner_managed', see 7.3). MSP can view invoice history and status per managed client. MSP is authorized to approve full or partial refund requests raised by managed tenants — same approval authority as SA (see 9.2). | High | Confirmed | Team confirmed — MSP refund authority equivalent to SA | 2026-05-27 | Not Started |  |  | Not Started |  |  | 7.3 (invoice trigger on tenant provisioning), 9.2 (refund approval authority) | New feature — not in original PRD baseline
4.12 | Partner-facing Activity Log | New Activity Log feature for Partner Portal — separate from SA's internal activity log (5.1). Displays a log of partner-relevant actions/events (e.g. deal status changes, commission events, plan assignment, team changes). Content scope split by audience: which fields shown on Admin Portal vs which shown on Partner Portal still needs BA definition. | Medium | Awaiting Confirmation |  | 2026-05-27 | Not Started |  |  | Not Started |  |  | 5.1 | New feature — not in original PRD baseline
§5 — SA Partner Module (blazeup-subapp-sa-partners)
5.1 | SA Partner Directory | List all partners with tier/ARR/open deals/client counts/status. Filter by region/tier/type/status. Partner Profile drill-in: company info, team certs, deal history, commission ledger, territory, performance vs tier thresholds, internal notes, activity log. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  | Also covers POST /v1/sa/partner-users/:userId/unlock (SA clears login + MFA lockouts). Endpoint not enumerated in PRD §8.5 and the lockout POLICY is unspecified anywhere — see OQ-28. | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004: PASSED PARTNER_UI_SA_PARTNER_MODULE_003: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_004: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_005: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_006: NOT_STARTED PARTNER_API_PARTNER_USERS_015: NOT_STARTED PARTNER_API_PARTNER_USERS_016: NOT_STARTED
5.1a | Partner Application Review — 3-Stage FSM | Stage 1: SA Review (requires signed partner agreement attached). Stage 2: Legal Countersign (SA cannot advance until Legal records countersign). Stage 3: SA Final Approval → blazeup.partner.approved emitted. SA can Decline at any stage (mandatory reason logged). UI must surface all 3 stages as visible FSM. | Critical | Confirmed | Locked — Aashwij 2026-05-15 (B3) | 2026-05-27 | Not Started |  |  | Not Started |  | 2026-07-14 | B3 resolved | Locked decision B3 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004: PASSED PARTNER_UI_SA_PARTNER_MODULE_003: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_004: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_005: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_006: NOT_STARTED
5.2 | SA Deal Approval Queue | Pending Approval and Conflict Queue tabs. Per-deal card: conflict check result, rep assignment dropdown, Assign Plan section (choose Edition; if Custom, search + select the specific Plan). Approve+Assign stamps commissionRate+rateTableVersion on partner_deals. Deal protection clock starts. Co-sell override proposal (above $100K ACV) — Partner Portal responds via Agree/Disagree (not Approve). Rep gets CRM task. Partner notified. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  |  | PARTNER_API_DEAL_APPROVAL_QUEUE_001: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_004: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_005: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_006: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_007: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_008: FAILED PARTNER_API_DEAL_REGISTRATION_PIPELINE_009: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_012: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_013: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_014: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_016: PASSED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010: BLOCKED PARTNER_UI_MY_PIPELINE_005: NOT_STARTED PARTNER_UI_MY_PIPELINE_016: NOT_STARTED PARTNER_UI_MY_PIPELINE_017: NOT_STARTED PARTNER_UI_MY_PIPELINE_018: NOT_STARTED PARTNER_UI_MY_PIPELINE_030: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_001: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_002: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_007: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_008: NOT_STARTED
5.2a | Deal Protection: Auto-Extend Rule | On expiry: if ≥1 stage update in last 30 days AND never auto-extended → auto-extend once to 2× original window. Else: hard expiry → partner requests manual SA extension. protectionExtensionCount (max 1) + lastStageUpdateAt on partner_deals. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-20) | 2026-05-27 | Not Started |  |  | Done |  |  | Notification service currently only supports email and has only wired trigger-events for the TICKET module — need to add trigger-events for the PARTNER module for "Partner notified" to actually work (see notification-architecture.md §3.3). | Locked decision | PARTNER_API_DEAL_APPROVAL_QUEUE_001: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_004: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_005: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_006: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_007: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_008: FAILED PARTNER_API_DEAL_REGISTRATION_PIPELINE_009: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_012: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_013: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_014: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_016: PASSED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010: BLOCKED PARTNER_UI_MY_PIPELINE_005: NOT_STARTED PARTNER_UI_MY_PIPELINE_016: NOT_STARTED PARTNER_UI_MY_PIPELINE_017: NOT_STARTED PARTNER_UI_MY_PIPELINE_018: NOT_STARTED PARTNER_UI_MY_PIPELINE_030: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_001: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_002: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_007: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_008: NOT_STARTED
5.2b | Conflict Queue + Resolution UI | SA sees both parties, prospect contacted status, decision (Award A / Award B / Split N/A for direct). Reasoning field required. Both parties notified with reasoning. Logged to audit trail. Immutable. | High | Awaiting Confirmation | OQ-17 90-day re-registration mechanism TBD |  | N/A |  |  | Done |  |  | OQ-17 TBD |  | PARTNER_API_DEAL_APPROVAL_QUEUE_001: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_004: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_005: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_006: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_007: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_008: FAILED PARTNER_API_DEAL_REGISTRATION_PIPELINE_009: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_012: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_013: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_014: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_016: PASSED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010: BLOCKED PARTNER_UI_MY_PIPELINE_005: NOT_STARTED PARTNER_UI_MY_PIPELINE_016: NOT_STARTED PARTNER_UI_MY_PIPELINE_017: NOT_STARTED PARTNER_UI_MY_PIPELINE_018: NOT_STARTED PARTNER_UI_MY_PIPELINE_030: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_001: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_002: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_007: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_008: NOT_STARTED
5.3 | Commission Rate Table + SPIFF Programmes | SA-managed rate table (no code change to adjust rates). Versioned. Referral, Reseller margin, Co-sell rates per tier. SPIFF programmes with region/tier/date filters. 3-stage lifecycle model: NN/EN/EE rate bands per tier × deal-type. Clawback config: 12-month window, 50% of paid, waiver path. | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  | B6 architecture resolved | PARTNER_API_COMMISSIONS_PAYOUTS_001: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_004: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_005: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_006: NOT_STARTED PARTNER_API_COMMISSIONS_PAYOUTS_010: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_011: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_012: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_013: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006: BLOCKED PARTNER_UI_COMMISSIONS_005: NOT_STARTED PARTNER_UI_COMMISSIONS_007: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_009: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_010: NOT_STARTED PARTNER_API_PARTNER_PORTAL_005: PASSED PARTNER_API_PARTNER_PORTAL_006: PASSED
5.4 | Territory Management | Assign regions + verticals per partner. Exclusivity types: Exclusive (single partner), Preferred (first-registered wins), None (open market). Territory rules enforced on conflict resolution. | Medium | Confirmed |  | 2026-05-27 | Not Started |  |  | Done |  |  |  |  | PARTNER_UI_SA_PARTNER_MODULE_012: NOT_STARTED PARTNER_API_TERRITORIES_001: PASSED PARTNER_API_TERRITORIES_002: PASSED PARTNER_API_TERRITORIES_003: PASSED PARTNER_API_TERRITORIES_004: PASSED
5.5 | SA Analytics Dashboard | Partner-Sourced ARR, Deals Registered MTD, Approval Rate, Win Rate, Avg Deal Size vs direct, Avg Deal Velocity. Commission paid/pending/clawbacks/waiver grants. Top 5 partners by ARR. Tier distribution. | Medium | Confirmed |  | 2026-05-27 | Not Started |  |  | Not Started |  |  |  | Implemented by GET /v1/sa/deals/stats (SA-wide pipeline KPI + byProvisioningState watchdog block; filters partnerId/status/dealType/conflictStatus/search/provisioningState). Not enumerated in PRD §8.5. NOTE: its automation TCs sit under the PIPELINE_MANAGEMENT registry section, not DASHBOARD_DATA — requirement taxonomy and test-registry taxonomy differ here by design. | PARTNER_UI_DASHBOARD_006: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_011: NOT_STARTED PARTNER_API_PIPELINE_MANAGEMENT_012: NOT_STARTED PARTNER_API_PIPELINE_MANAGEMENT_013: NOT_STARTED
5.6 | SA Commission Ledger + Approval Workflow | All calculated commissions require SA approval before payout. Two-eye principle for amounts >$10K. Approve / Dispute / Request clarification per commission row. Clawback waiver review queue (30-day SLA). | High | Confirmed |  | 2026-05-27 | Not Started |  |  | Done |  |  |  |  | PARTNER_API_COMMISSIONS_PAYOUTS_007: BLOCKED PARTNER_UI_COMMISSIONS_003: NOT_STARTED PARTNER_UI_COMMISSIONS_006: NOT_STARTED
§6 — CRM Integration Architecture
6.1 | Event-Driven CRM Sync: partner events → dogfood CRM | All partner Kafka events auto-create/update opportunities in dogfood CRM. deal.registered → create opp (stage: Partner Deal Pending Approval). deal.approved → update opp + assign rep + create task. deal.won → close won + stamp ARR + tenant_id. deal.lost → close lost. | Critical | Confirmed |  |  | N/A |  |  | Done |  |  |  | §6.2 full event map | PARTNER_API_CRM_INTEGRATION_001: BLOCKED
6.2 | Opportunity Record Schema: attribution block | Opportunity carries full attribution: partnerId, partnerName, partnerTier (locked at close), dealType, commissionRate (locked at approval), rateTableVersion, commissionAmount, cosellSplit (if co-sell). | High | Planned |  |  | N/A |  |  | Not Started |  |  |  | commissionRate locked at APPROVAL not registration | PARTNER_API_CRM_INTEGRATION_001: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_008: FAILED PARTNER_API_DEAL_REGISTRATION_PIPELINE_010: PASSED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_007: BLOCKED PARTNER_UI_SA_PARTNER_MODULE_008: NOT_STARTED PARTNER_API_DEAL_REGISTRATION_PIPELINE_018: NOT_STARTED PARTNER_API_DEAL_REGISTRATION_PIPELINE_019: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_020: PASSED
§7 — Tenant Provisioning on Deal Close
7.1 | Referral Close → Provision Flow | Partner marks Won OR BlazeUp rep closes in CRM → Kafka blazeup.partner.deal.won → ms-sa-partners calculates commission + calls SA /internal/tenants/provision with attribution block → blazeup.tenant.provisioned → CRM closed + CSM project created + partner portal updated + commission queued. | Critical | Confirmed |  | 2026-05-27 | N/A |  |  | Done |  |  |  |  | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_007: BLOCKED
7.2 | Reseller Close: billing.model='reseller' | Same as referral flow but billing.model='reseller'. BlazeUp invoices partner at discount. Partner manages client billing independently. BlazeUp never captures partner's sell price. | High | Confirmed |  | 2026-05-27 | N/A |  |  | Not Started |  |  |  |  | PARTNER_API_COMMISSIONS_PAYOUTS_011: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_002: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_003: BLOCKED
7.3 | MSP Provisioning Flow | MSP uses + Add Managed Client. Fills client details + MSP ticket-content consent toggle (default OFF). ms-sa-partners calls provision API with billingModel='partner_managed' + mspTicketContentConsent block. MSP gets scoped admin token. | High | Planned |  |  | Not Started |  |  | Not Started |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_006: BLOCKED PARTNER_UI_MY_CLIENTS_005: NOT_STARTED PARTNER_UI_MY_CLIENTS_006: NOT_STARTED
7.4 | Expansion Close: Existing Tenant | No new tenant. Additional modules/seats provisioned on existing tenant — restricted to Reseller & MSP, partner self-sets plan/pricing via their own Custom Plan (no SA price gate). Subscription line items updated in ms-billing. Expansion commission on delta ARR using NN/EN/EE classification. Co-sell: pending — new OQ. | High | Confirmed | Expansion is now confirmed for Reseller & MSP only (partner self-sets plan/price). Is Co-sell eligible for Expansion, and if so, under what mechanism (since Co-sell partners can't self-set pricing)? | 2026-05-27 | Not Started |  |  | Not Started |  |  | B6 architecture resolved |  | PARTNER_API_COMMISSIONS_PAYOUTS_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_004: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006: BLOCKED
7.5 | Tenant Attribution Block (Permanent) | Every partner-sourced tenant carries permanent attribution: source, partnerId, partnerName, partnerTier (at close), dealId, commissionStructure{rate, rateTableVersion, clawbackExpiresAt, productFailureWaiver?}, billingModel, attributionHistory[] (SA overrides, two-eye approval, immutable history). | Critical | Confirmed | Locked — Renil 2026-05-15 (B4, B6) | 2026-05-27 | N/A |  |  | N/A |  |  | B4 resolved | attributionHistory[] never deleted — only superseded | PARTNER_API_CLIENT_HEALTH_MSP_007: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_007: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_008: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_009: BLOCKED PARTNER_UI_COMMISSIONS_006: NOT_STARTED
§8 — Technical Architecture
8.1 | New Services/Repos: 5 Artifacts | blazeup-microservice-sa-partners (BE), blazeup-hostapp-partner (FE host), blazeup-subapp-sa-partners (SA subapp), blazeup-subapp-partner-dashboard (partner subapp), blazeup-subapp-partner-training (partner subapp). | Critical | Confirmed |  | 2026-05-27 | Done |  |  | Done |  |  |  |  | —
8.2 | MongoDB Collections: 8 Collections | partner_accounts, partner_deals, partner_commissions, partner_territories, partner_certifications, partner_referral_links, partner_rate_table (NN/EN/EE bands), partner_conflicts. | Critical | Confirmed |  | 2026-05-27 | N/A |  |  | Done |  |  |  |  | PARTNER_API_COMMISSIONS_PAYOUTS_001: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_006: NOT_STARTED PARTNER_API_COMMISSIONS_PAYOUTS_010: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_005: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_007: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006: BLOCKED PARTNER_UI_SA_PARTNER_MODULE_009: NOT_STARTED
8.3 | Kafka Events: ~20 Events | Full list: registered, approved, tier.changed, deal.registered/approved/rejected/conflict_raised/protection_extended/won/lost/expired, commission.earned/paid/waiver_decided, client.health_alert/transferred, msp_ticket_consent.changed, sandbox.reset_requested. | Critical | Confirmed |  | 2026-05-27 | N/A |  |  | Done |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_005: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_007: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_009: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_005: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_009: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_005: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_006: BLOCKED PARTNER_API_EVENT_ARCHITECTURE_001: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010: PASSED PARTNER_API_RESOURCES_SANDBOX_001: BLOCKED PARTNER_API_RESOURCES_SANDBOX_003: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002: BLOCKED PARTNER_UI_RESOURCES_001: NOT_STARTED PARTNER_UI_RESOURCES_002: NOT_STARTED PARTNER_UI_TRAINING_002: NOT_STARTED
8.4 | Referral Attribution Service | blazeup.ai/ref/{slug} → server writes Redis attr:{sessionToken} TTL 30 days + sets first-party cookie __blazeup_ref. On signup: resolve attribution from Redis, stamp tenant.attribution, fire commission. First-touch wins. Edge cases: multiple clicks (first-touch), no cookie (no attribution), >30 days (expired). | High | Rejected / On Hold |  | 2026-05-27 | N/A |  |  | Not Started |  |  |  | R4 mitigation | PARTNER_API_COMMISSIONS_PAYOUTS_008: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_009: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_001: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_002: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_003: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_004: BLOCKED PARTNER_API_TEAM_REFERRAL_LINKS_002: BLOCKED PARTNER_UI_PARTNER_TEAM_002: NOT_STARTED
8.5 | REST API: ~25 Endpoints | SA-only internal endpoints (partner CRUD, deal approval/reject/extend, conflict resolve, commission approve/waiver, rate table). Partner-JWT-gated endpoints (dashboard, deals, clients/health/tickets, commissions/dispute/waiver, referral links). See §8.5 for full list. | Critical | Confirmed |  | 2026-05-27 | N/A |  |  | Done |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_001: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_002: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_002: NOT_STARTED PARTNER_API_COMMISSIONS_PAYOUTS_003: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_004: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_005: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_013: BLOCKED PARTNER_API_DASHBOARD_DATA_001: PASSED PARTNER_API_DEAL_APPROVAL_QUEUE_001: PASSED PARTNER_API_DEAL_COLLABORATION_001: BLOCKED PARTNER_API_DEAL_COLLABORATION_002: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_001: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_002: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_003: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_008: FAILED PARTNER_API_DEAL_REGISTRATION_PIPELINE_015: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_016: PASSED PARTNER_API_DEAL_REGISTRATION_PIPELINE_017: BLOCKED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002: PASSED PARTNER_API_PIPELINE_MANAGEMENT_001: PASSED PARTNER_API_PIPELINE_MANAGEMENT_002: PASSED PARTNER_API_TEAM_REFERRAL_LINKS_001: BLOCKED PARTNER_API_TEAM_REFERRAL_LINKS_002: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010: BLOCKED PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011: BLOCKED PARTNER_UI_MY_PIPELINE_016: NOT_STARTED PARTNER_UI_MY_PIPELINE_019: NOT_STARTED PARTNER_UI_MY_PIPELINE_030: NOT_STARTED
8.6 | Redis Caching Keys | partners:account:{id} (1h), partners:rate_table:current (24h), partners:rate:{tenantId}:{tier} (1h), partners:deal:{dealId}:protection (TTL=protectionExpiresAt), partners:attr:{sessionToken} (30d), partners:conflict:{domain} (7d). | Medium | Confirmed |  | 2026-05-27 | N/A |  |  | Not Started |  |  |  |  | PARTNER_API_COMMISSIONS_PAYOUTS_006: NOT_STARTED PARTNER_API_COMMISSIONS_PAYOUTS_008: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_014: BLOCKED PARTNER_API_REFERRAL_ATTRIBUTION_001: BLOCKED
§9 — Security & Compliance
9.1 | Partner Portal Auth: Separate JWT Issuer | Distinct JWT issuer from tenant and SA. 8h access token, 30-day refresh. MFA: required for PARTNER_ORG_ADMIN. Tier-based (Advanced+) per this PRD but OQ-14 conflicts with sa-portal-architecture-v2.6.md §14.8 (role-based). Session scoped to partnerId. | Critical | Awaiting Confirmation | OQ-14 MFA policy conflict unresolved (Renil owed) |  | N/A |  |  | Done |  |  | B1 Auth Phase 0 | OQ-14 must resolve before MFA enforcement logic finalised | PARTNER_API_AUTH_ACCESS_CONTROL_001: PASSED PARTNER_API_AUTH_ACCESS_CONTROL_002: PASSED PARTNER_API_AUTH_ACCESS_CONTROL_003: PASSED PARTNER_API_AUTH_ACCESS_CONTROL_004: NOT_STARTED PARTNER_API_PIPELINE_MANAGEMENT_001: PASSED PARTNER_UI_SECURITY_COMPLIANCE_001: NOT_STARTED
9.2 | MSP Access Scope + PartnerScopeGuard | PartnerScopeGuard in EVERY MS. MSP can: configure modules, manage users, see ticket count+severity, create/edit own Custom Plan (module bundle + pricing + seat), manage own Plan List (scoped to plans they created — no visibility or edit rights on SA-created plans). MSP CANNOT: see ticket content (until client opt-in), access payroll/salary/health data, export data, impersonate users. Consent stored on tenant record. Revocation immediate. | Critical | Planned | Locked — Renil 2026-05-08 (OQ-22) Custom Plan self-service authority extended to Reseller |  | N/A |  |  | Not Started |  |  |  | Locked decision | PARTNER_API_AUTH_ACCESS_CONTROL_005: BLOCKED PARTNER_API_AUTH_ACCESS_CONTROL_006: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_003: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_004: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_005: BLOCKED PARTNER_API_CLIENT_HEALTH_MSP_009: BLOCKED PARTNER_UI_MY_CLIENTS_006: NOT_STARTED
9.3 | Data Residency: PDPL/PDPA Compliant | Partner prospect data stored in SA region (us-west1 today). UAE/Saudi: Middle East region when available. Prospect contact data (domain, name, email only) never transferred cross-region without consent. | High | Planned |  |  | N/A |  |  | Not Started |  |  |  |  | PARTNER_API_COMMISSIONS_PAYOUTS_016: BLOCKED PARTNER_API_SECURITY_COMPLIANCE_002: BLOCKED PARTNER_API_SECURITY_COMPLIANCE_003: BLOCKED PARTNER_UI_SECURITY_COMPLIANCE_003: NOT_STARTED
9.4 | Audit Trail: All SA Actions Immutable | sa_audit_log collection (Tier J). Covers: deal approval/rejection, protection extension (auto+manual), conflict resolution, co-sell split override, commission approval/dispute, waiver decision, MSP consent grant/revoke, territory changes, rate table modifications (versioned — every version preserved). | High | Confirmed |  | 2026-05-27 | N/A |  |  | Done |  |  |  |  | PARTNER_API_CLIENT_HEALTH_MSP_009: BLOCKED PARTNER_API_COMMISSIONS_PAYOUTS_012: BLOCKED PARTNER_API_DEAL_REGISTRATION_PIPELINE_009: PASSED PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004: PASSED PARTNER_API_SECURITY_COMPLIANCE_001: BLOCKED PARTNER_UI_MY_PIPELINE_015: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_001: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_002: NOT_STARTED PARTNER_UI_SA_PARTNER_MODULE_006: NOT_STARTED PARTNER_UI_SECURITY_COMPLIANCE_002: NOT_STARTED PARTNER_UI_SECURITY_COMPLIANCE_004: NOT_STARTED PARTNER_API_AUDIT_LOG_001: PASSED PARTNER_API_AUDIT_LOG_002: PASSED PARTNER_API_AUDIT_LOG_003: PASSED PARTNER_API_AUDIT_LOG_004: PASSED
§10 — Effort Estimates
10.1 | ms-sa-partners Core | Collections, deal FSM, APIs, Kafka events, commission engine | Critical | Confirmed |  | 2026-05-27 | N/A |  |  | Done | ~4 weeks |  |  | Critical path | —
10.2 | ms-sa-partners Dogfood CRM Bridge | DogfoodCrmBridge consumer, opportunity create/update flows | Critical | Planned |  |  | N/A |  |  | Not Started | ~3 days |  |  |  | —
10.3 | ms-sa-partners Referral Attribution | Link tracking, Redis attribution, self-signup path | High | Rejected / On Hold | PO confirmed: we wont have the self-signup path |  | N/A |  |  | Not Started | ~1 week |  |  |  | —
10.4 | ms-sa-partners Renil-Locked Surface | Auto-extend cron+activity gate, co-sell split override, product-failure waiver, MSP ticket-consent guard, managerAllocation field | High | Confirmed | Locked — Renil 2026-05-08 | 2026-05-27 | N/A |  |  | Done | ~1 week |  |  | Added due to Renil lock-ins | —
10.5 | blazeup-hostapp-partner | Portal shell, auth, nav, federation scaffold | Critical | Confirmed |  | 2026-05-27 | Done | ~1 week |  | N/A |  |  | B1 Auth |  | —
10.6 | Partner Portal Subapps (Batch 1) | Dashboard · Deal Registration · Pipeline · Client Health (with ticket-content gating) | Critical | Confirmed |  | 2026-05-27 | Not Started | ~4 weeks |  | N/A |  |  |  |  | —
10.7 | Partner Portal Subapps (Batch 2) | Commissions (incl. waiver request UI) · Resources · Team · Settings— Training subapp removed (certificate assignment moved to SA Admin, not a partner-facing subapp) | High | Confirmed |  | 2026-05-27 | Not Started | ~3 weeks |  | N/A |  |  |  |  | —
10.8 | blazeup-subapp-sa-partners | Partner directory · Deal approval (cosell-override + extension UI) · Conflict queue · Territories · Waiver review queue | Critical | Confirmed |  | 2026-05-27 | Not Started | ~2 weeks |  | N/A |  |  |  |  | —
10.9 | SA Analytics + Commission Ledger | Analytics dashboard · Commission approval workflow · Waiver-tracking metric | High | Confirmed |  | 2026-05-27 | Not Started | ~2 weeks |  | N/A |  |  |  |  | —
10.10 | Blazey Partner Assistant | 4 tools: commission query, deal status, tier projection, client health. + skill file. | Medium | Planned |  |  | Not Started | ~1 week |  | N/A |  |  |  |  | PARTNER_UI_DASHBOARD_008: NOT_STARTED PARTNER_UI_DASHBOARD_009: NOT_STARTED
§12 — Open Questions Impact on Features
OQ-8 | Training Platform: Build vs Buy | Build on dogfood LMS OR buy (Docebo / Thought Industries) for v1. Aashwij still owed. Affects §4.8 scope and time-to-launch. | Medium | Confirmed | Resolved 08/06 MM — training portal dropped, SA manually assigns certificates" |  | N/A |  |  | Not Started | If buy: integration only; if build: full LMS in blazeup-subapp-partner-training |  | OQ-8 Aashwij | Non-blocking but should land before training sprint | —
OQ-14 | MFA Enforcement Policy | sa-portal-architecture-v2.6.md §14.8: role-based (PARTNER_ORG_ADMIN). This PRD §9.1: tier-based (Advanced+). Which is authoritative? Or both? Renil owed. | High | Rejected / On Hold | Renil owed | 2026-05-27 | N/A |  |  | Not Started | partner-iam MFA enforcement logic cannot be finalised until resolved |  | OQ-14 Renil | Non-blocking but must land before partner-iam sprint | PARTNER_API_AUTH_ACCESS_CONTROL_004: NOT_STARTED
OQ-15 | Grace Quarter Definition for Tier Downgrade | Full next quarter after announcement OR remainder of current quarter? Aashwij owed. Affects tier FSM timing. | Low | Rejected / On Hold | Aashwij owed | 2026-05-27 | N/A |  |  | Not Started | Tier FSM downgrade timing |  | OQ-15 Aashwij |  | —
OQ-17 | Conflict-Loser 90-Day Re-registration | Auto-unlock + notification when 90 days elapsed, OR manual partner re-submit with no system support? Aashwij owed. | Medium | Rejected / On Hold | Aashwij owed | 2026-05-27 | Not Started | Re-registration notification UI |  | Not Started | partner_conflicts auto-expiry + deal FSM |  | OQ-17 Aashwij |  | —
OQ-18 | Rate-Table Change Retroactivity | Confirm rates lock at deal APPROVAL (not registration, not invoice). PRD §6.3 and §5.2 both assert locked at approval; OQ-5 v0.4 corrected this. Treat as confirmed pending Renil sign-off. | High | Planned | Renil sign-off pending |  | N/A |  |  | Not Started | Commission engine version-pin behaviour: rateTableVersion stamped at approval |  | OQ-18 Renil |  | PARTNER_UI_SECURITY_COMPLIANCE_004: NOT_STARTED
§13 — Plan & Catalog Management
13.1 | Published Plan Selection at Onboarding | After Deal marked Won → tenant created immediately → partner manually enters company info → selects an existing Published Plan (replaces "Module of Interest" selection). Form branches by deal type: Reseller flow differs from Referral/Co-sell flow. Submitted to SA Portal for review. | High | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.2 | Custom Plan Request (Edge Case) | If no published plan fits: partner selects desired modules + client's estimated budget → submits as custom plan request → SA sees request, creates a new plan → communicates with partner → partner approves or requests changes. | High | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.3 | Partner Request New Plan Form (fields) | Estimated client's budget (USD): per month (changed from per year). Edition field removed. New field: Billing cycle. Component review pending. | Medium | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.4 | Plan & Catalog Activation Rule | Edition Starter / Pro / Enterprise: only 1 active plan per edition at a time. Edition Custom: multiple active plans allowed (scoped per partner — each Reseller/MSP sees only plans they created, see §9.2/2.2a). | Critical | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.5 | Plan Request Processing Flow | Partner submits deal (request new plan) → system creates a draft plan → Admin submits to Finance (not handled yet — see OQ-22) → plan published with Edition = Custom. | High | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.6 | Plan-Assigned Indicator for Partner (PP031) | Partner Portal shows a visual indicator when Admin has assigned the plan the partner requested. | Medium | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.7 | Edit Custom Plan (SA) | New edit flow for custom requested plans. In the Edit side drawer: Edition field removed. | Medium | Confirmed |  | 2026-07-09 | Not Started |  |  | Not Started
13.8 | No-Edit-After-Publish (Bump-Version Rule) | A published plan cannot be edited. To change it, use bump-version to create a new draft, then edit the draft. Applies to custom plans once assigned to a tenant. | High | Confirmed | Kenny/Dave |  | Not Started |  |  | Not Started |  |  |  | Not in PRD yet (P6)
13.9 | Change Plan for Tenant (no "edit plan" flow) | No "edit plan" flow — only change-plan-for-tenant: archive current plan -> keep the same object ID -&gt; create new plan -&gt; change plan for tenant. Currently SA-manual; tenant team planning automation. | High | Confirmed | Dave / tenant team |  | Not Started |  |  | Not Started |  |  | Clarify "keep object ID" wording (old ID vs same format) | SA-manual now (P1/P2)
13.1 | Change Plan Billing ↔ Tenant Sync | On change: call tenant API to store the new plan for billing -> billing applies at start of next billing month -&gt; billing emits back to tenant to update the platform. | High | Confirmed | Jacob / tenant / billing |  | N/A |  |  | Not Started |  |  |  | Flow may not cover all cases (P1)
13.11 | Commission on Change Plan | Commission is locked per-deal. Change-plan does NOT recalculate commission (tentative). Impact on Commission module not yet assessed. | Medium | Awaiting | Dave / Jacob |  | N/A |  |  | Not Started |  |  | Final decision deferred | P3 deferred; P5 impact TBD
13.12 | Change-Plan Open Decisions | (a) Notify partner by email on change-plan that affects commission — no owner, undecided. (b) Does bump-version publish the plan to Kafka? — unanswered, confirm with Kenny. | Medium | Awaiting | Kenny/Dave |  | N/A |  |  | N/A |  |  |  | P4 open; P7 unanswered

## ⚠️ Risk Register
BlazeUp Partner Platform — Risk Register (PRD §Risk Flags)
Risk ID | Severity | Risk Description | Impact | Mitigation | Status | Owner | Notes
R1 | CRITICAL | Deal Conflict — two partners (or partner + direct inbound) register the same prospect | Commission disputes, partner trust destroyed, channel conflict | First-registered-wins rule + SA conflict queue + 5-business-day SLA for resolution | Pending |  | OQ-17: 90-day re-registration mechanism TBD
R2 | HIGH | Commission Opacity — partners don't trust what they'll earn until after deal closes | Low deal registration adoption | Show projected commission at registration time, before submission, updated live as ACV is typed | Pending |  | Live commission projection in §4.4 Step 3
R3 | HIGH | MSP Billing Ambiguity — partner-managed tenants billed to partner vs end client | Revenue leakage + tax/VAT complications across Vietnam/UAE/India | Explicit billing.model: 'direct'¦'reseller'¦'partner_managed' on every partner-sourced tenant; set at deal registration, immutable after provisioning | Pending
R4 | HIGH | Referral Attribution Loss — prospect clicks link, signs up days later in different browser | Partner loses commission on a valid referral | First-touch partner_id captured server-side on link click; stored with 30-day TTL; survives browser sessions | Pending |  | §8.4 Redis attribution service
R5 | MEDIUM | Pack Partner vs Channel Partner Conflation | Wrong commission structure applied; incorrect portal access | Two distinct account types; a partner can hold both; managed independently in SA | Pending |  | §3 Scenario H — dual account type
R6 | MEDIUM | Clawback Rules Unclear at Deal Close | Partner disputes clawback when client churns at month 10 | Clawback policy + product-failure waiver path must be in partner agreement AND displayed at commission approval time | Pending |  | §5.3 clawback config — Locked Renil 2026-05-08
R7 | MEDIUM | PDPA/PDPL Compliance for Partner-Held Prospect Data | Partners in Vietnam/UAE uploading prospect data to deal registration | Partner agreement + DPA required per region; prospect data minimised at registration — domain + name + email only | Pending | Legal/Compliance | §9.3; OQ-17 (v0.4) GDPR erasure spec pending Legal
R8 | LOW | Tier Downgrade Psychology — partner drops from Advanced to Select | Partner disengagement | Downgrade is quarterly, announced 30 days in advance; give partner a grace quarter to recover | Pending |  | OQ-15 grace quarter definition TBD

## ❓ Open Questions
BlazeUp Partner Platform — Open Questions & Blockers (PRD §12)
ID | Category | Question / Decision | Owner | Blocks / Impact | Status | Decision (if resolved) | Target Date
B1 | BLOCKING | Auth Hardening Phase 0 — PRs #633–#641 must merge before any partner JWT class, OAuth 2.0 server, or partner-issued tokens go live. | Auth team | Partner auth surfaces only (all non-auth coding proceeds in parallel) | In Progress | Engineer working directly with Auth team. Non-auth coding proceeds now. Auth surfaces gated on PR merge. | ~Week 1-2
B2 | BLOCKING | First-admin enrollment flow on partner approval. | Auth team | partner-iam implementation | Resolved | Follow tenant creation model (§tenant-creation-module-spec-v1.1.md §4.6+§6.6). PENDING_ACTIVATION user → activation email → self-set password. Token TTL deferred to Auth team standard. | Resolved 2026-05-15
B3 | BLOCKING | Partner-org approval workflow stages — single SA step or staged workflow? | Aashwij + SA subapp team | SA partner application review UI (§5.1) | Resolved | 3-stage FSM: (1) SA Review (signed agreement required), (2) Legal Countersign, (3) SA Final Approval. SA can Decline at any stage with mandatory reason. | Resolved 2026-05-15
B4 | BLOCKING | Partner-managed tenant linking edge cases: no registration, pre-programme tenants, MSP handoff, SA attribution override. | — | tenant.attribution schema (§7.5) | Resolved | (a) No registration = no commission. (b) Prospective attribution for pre-programme tenants — future only, written justification. (c) MSP handoff: SA-only, both parties agree, blazeup.partner.client.transferred. (d) SA override: two-eye approval + attributionHistory[]. | Resolved 2026-05-15
B5 | BLOCKING | blazeup-microservice-sandbox-data spec — profiles, collections, reset policy. | Khoa (implementation) | Partner sandbox provisioning §4.9 | Resolved | 3 profiles: SMB/Mid-market/Enterprise. Collections: employees, departments, leave_requests, expense_reports, crm_contacts, crm_deals, assets, tickets. On-demand reset (5 min). Optional weekly auto-reset (default OFF). blazeup.partner.sandbox.reset_requested event. | Resolved 2026-05-15
B6 | BLOCKING | Expansion deal commission rate — how is expansion ARR commissioned? | Commission engine team | Commission engine Scenario F (Expansion) | Resolved (rates TBD) | 3-stage lifecycle: NN (Net New, full rate for SA-configured window) → EN (Existing customer Net New licenses, lower rate) → EE (Existing customer Existing licenses, lowest/zero). All rates SA-configurable before launch. partner_rate_table stores all 3 bands per tier × deal-type. | Resolved 2026-05-15
OQ-8 | Non-Blocking | Training platform — build on dogfood LMS vs buy (Docebo/Thought Industries) for v1? | Aashwij | Training subapp scope (§4.8), time-to-launch | Resolved | Skip training portal — SA manually assigns certificates for v1 | Before training sprint
OQ-14 | Non-Blocking | TOTP/MFA requirement conflict: sa-portal-architecture-v2.6.md §14.8 says role-based (PARTNER_ORG_ADMIN mandatory); this PRD §9.1 says tier-based (Advanced+ mandatory). Which is authoritative? | Renil | partner-iam MFA enforcement logic | Open |  | Before partner-iam sprint
OQ-15 | Non-Blocking | Grace quarter definition for tier downgrade — full next quarter after announcement, or remainder of current quarter? | Aashwij | Tier FSM timing | Open |  | Before tier engine sprint
OQ-17 | Non-Blocking | Conflict-loser 90-day re-registration — auto-unlock + notification OR manual partner re-submit? | Aashwij | Deal FSM, partner_conflicts design | Open |  | Before conflict queue sprint
OQ-18 | Non-Blocking | Rate-table retroactivity — confirm rates lock at deal APPROVAL (not registration, not invoice). PRD §6.3 and OQ-5 v0.4 both assert approval-lock. | Renil | Commission engine version-pin behaviour | Pending sign-off | PRD asserts: locked at approval. rateTableVersion stamped on approve action. | Before commission engine sprint
OQ-17v4 | Legal/Compliance | GDPR partner-org erasure spec — which fields can be pseudonymised vs retained? (Commission records: 7-year US / 8-year India retention obligations.) | Legal + Compliance | Data retention schema for partner_commissions and partner_accounts | Open |  | Before launch
OQ-18v4 | Legal/Compliance | Impersonation audit — when SA staff impersonates a tenant referred by a partner, does the partner get active notification (email/in-portal) or audit log only? | Legal + Compliance | auth.impersonation.partner-notified Kafka event | Open |  | Before launch
OQ-24 | Non-Blocking | Expansion is confirmed for Reseller & MSP only (partner self-sets plan/price). Is Co-sell eligible for Expansion, and if so under what mechanism (Co-sell partners can't self-set pricing)? | Renil | feature/row bị block, ví dụ: 3-F, 7.4 — Expansion commission flow cho Co-sell | Open |  | Before launch
OQ-26 | Non-Blocking | Partner Team invitation flow — activation/token handling mechanism not yet defined. Needs redesign | Renil | 4.10 Partner Team Management | Open |  | Before launch
OQ-27 | Non-Blocking | The Finance approval step for draft custom plans (Admin submit → Finance) is explicitly noted as "not handled yet." Who owns building this, and what's the interim process before it's built? | Renil | Plan & Catalog / Assign a Plan flow (§13) | Open |  | Before launch
OQ-28 | Non-Blocking | Partner login lockout policy is unspecified. §9.1 does not mention lockout and §5.1 does not mention unlock, yet the behaviour ships: measured 2026-09-17 at 4 consecutive failed logins → locked for 30 minutes, cleared by POST /v1/sa/partner-users/:userId/unlock (SA) or POST /v1/partner/directory/users/:userId/unlock (partner admin). Both clear login AND MFA lockouts together. Confirm: (a) is 4/30min the intended threshold, (b) should login and MFA lockouts really be cleared by the same call, (c) should a partner admin be able to unlock without SA? | Renil | §5.1 SA Partner Directory, §9.1 Partner Portal Auth. Automation can assert the measured behaviour but not that it is correct — if BE changes the threshold the tests go red with no way to tell which side is wrong. | Open |  | Before launch

## 🗃️ Data Models
BlazeUp Partner Platform — MongoDB Collections & Key Schema Fields (PRD §8.2, §7.5)
Collection | Field / Block | Type | Required | Description | Notes / Constraints | Status
partner_accounts
partner_accounts | tenantId (BlazeUp SA) | ObjectId | Yes | Links partner account to their BlazeUp SA tenant |  | Pending
partner_accounts | name, slug, type, tier, status | String | Yes | Slug used in referral links. type: referral¦reseller¦SI¦MSP. tier: Registered¦Select¦Advanced¦Premier |  | Pending
partner_accounts | managerAllocation | 'dedicated'¦'shared' | Yes | Dedicated at $1.5M ARR within Premier; shared (max 1:3) otherwise. Locked Renil 2026-05-08. | Reviewed annually | Pending
partner_accounts | regions[], verticals[] | String[] | No | Territory coverage — linked to partner_territories for exclusivity |  | Pending
partner_accounts | agreementSignedAt | Date | Yes | Required before SA can advance application from Stage 1 | B3 flow | Pending
partner_accounts | certifications[], contacts[], referralLinks[], apiKeys[] | Array | No | Supporting arrays |  | Pending
partner_deals
partner_deals | partnerId, prospectDomain, dealType | ObjectId / String | Yes | Core deal identity. dealType: referral¦reseller¦cosell | Domain used for conflict check | Pending
partner_deals | estimatedACV, closedACV, expectedCloseDate | Number / Date | Yes | ACV used for commission projection at registration time | closedACV set on close | Pending
partner_deals | stage | String FSM | Yes | Registered→Approved→InProgress→Closing→Won/Lost/Expired |  | Pending
partner_deals | protectionExpiresAt, protectionExtensionCount | Date / Number | Yes | protectionExtensionCount max 1 (auto-extend once only). Locked Renil 2026-05-08. | OQ-20 | Pending
partner_deals | lastStageUpdateAt | Date | Yes | Activity gate for auto-extend: must have ≥1 stage update in last 30 days. Locked Renil 2026-05-08. | OQ-20 | Pending
partner_deals | commissionRate, rateTableVersion | Number / String | Yes | Stamped at APPROVAL (not registration). Locked per OQ-5 v0.4 / §6.3. | Version-pinned forever | Pending
partner_deals | cosellSplit?: {partnerPct, blazeupPct, overrideApproved} | Object | No | Populated for co-sell deals. Override requires partner written acceptance. Locked at approval. | Scenario C | Pending
partner_deals | billingModel | 'direct'¦'reseller'¦'partner_managed' | Yes | Set at deal registration. Immutable after tenant provisioning. | R3 mitigation | Pending
partner_commissions
partner_commissions | status | Enum | Yes | 'pending'¦'approved'¦'paid'¦'disputed'¦'clawback'¦'clawback_waived' | clawback_waived: new status — Renil 2026-05-08 | Pending
partner_commissions | clawbackWaiver?: {requestedAt, decision, evidence[]} | Object | No | Product-failure waiver block. evidence[] = linked support tickets / incident reports. SA reviews in 30 days. | Locked Renil 2026-05-08 | Pending
partner_commissions | payoutBatchId | ObjectId | No | Groups commissions paid in same payout run |  | Pending
partner_rate_table
partner_rate_table | version, effectiveFrom | String / Date | Yes | Every version preserved. commissionRate + rateTableVersion stamped on partner_deals at approval. |  | Pending
partner_rate_table | rates: { tier × dealType → { nn, en, ee } } | Nested Object | Yes | NN: Net New (full rate, SA-configured window years). EN: Existing customer Net New licenses (lower rate). EE: Existing customer Existing licenses (lowest/zero rate). | B6 architecture resolved — specific rates SA-configurable before launch | Pending
partner_rate_table | spiffProgrammes[] | Array | No | Bonus rate, regions[], tiers[], validFrom, validTo |  | Pending
tenant.attribution (on Tenant record)
tenant.attribution | source | Enum | Yes | 'partner_referral'¦'partner_reseller'¦'partner_cosell'¦'partner_msp'¦'partner_link'¦'direct'¦'inbound' |  | Pending
tenant.attribution | partnerTier | String | Yes | Tier at deal CLOSE — locked forever | Do not update on tier change | Pending
tenant.attribution | commissionStructure.rateTableVersion | String | Yes | Added per OQ-5 v0.4 / Renil 2026-05-08 |  | Pending
tenant.attribution | commissionStructure.productFailureWaiver? | Object | No | {requestedAt, requestedBy, decision: 'pending'¦'granted'¦'denied', decidedAt?, decidedBy?, evidence: ObjectId[]} | Locked Renil 2026-05-08 | Pending
tenant.attribution | attributionHistory[] | Array | No | Preserved on ANY SA override or MSP handoff. Never deleted. Fields: partnerId, source, effectiveFrom, effectiveTo, changedBy, reason (mandatory), approvedBy (two-eye). | B4 resolved — Renil 2026-05-15 | Pending
tenant.attribution | billingModel | Enum | Yes | 'direct'¦'reseller'¦'partner_managed'. Set at deal registration, immutable after provisioning. | R3 mitigation | Pending
tenant.mspTicketContentConsent (MSP tenants only)
tenant.mspTicketContentConsent | granted | Boolean | Yes | Default FALSE. Client admin can toggle ON at provisioning or later. | Locked Renil 2026-05-08 / OQ-22 | Pending
tenant.mspTicketContentConsent | grantedAt, grantedBy, revokedAt, revokedBy | Date / ObjectId | No | Full audit trail. Revocation immediate. Emits blazeup.partner.msp_ticket_consent.changed. | PDPA/PDPL legal basis | Pending

## 📡 Kafka Events
BlazeUp Partner Platform — Kafka Events (PRD §8.3)
Event Name | Category | Trigger / Condition | Key Consumers | Payload Notes | Status | Notes
blazeup.partner.registered | Partner | Partner account created (pending SA approval) | ms-notification (welcome email) | Standard envelope + partnerId, type, regions | Pending
blazeup.partner.approved | Partner | SA completed 3-stage approval (B3). PARTNER_ORG_ADMIN user created. | ms-notification (activation email), partner-iam | partnerId, tier, primaryContactEmail | Pending | B3 resolved — 3-stage FSM
blazeup.partner.tier.changed | Partner | Quarterly tier recalculation — upgrade immediate, downgrade 30-day notice | partner portal (immediate update), SA analytics | partnerId, oldTier, newTier, effectiveDate | Pending
blazeup.partner.deal.registered | Deal | Partner submits deal registration | ms-sa-partners (conflict check), dogfood CRM (create opp) | dealId, partnerId, domain, dealType, estimatedACV | Pending
blazeup.partner.deal.approved | Deal | SA approves deal; commissionRate + rateTableVersion stamped; protection clock starts | dogfood CRM (update opp + assign rep + task), partner portal (notification) | dealId, commissionRate, rateTableVersion, protectionExpiresAt, assignedRepId | Pending | Rate locked at this moment
blazeup.partner.deal.rejected | Deal | SA rejects deal registration | partner portal (notification with reason) | dealId, reason (mandatory) | Pending
blazeup.partner.deal.conflict_raised | Deal | Two parties register same domain | SA conflict queue, both parties notified | dealId, party1Id, party2Id, domain | Pending | R1 mitigation
blazeup.partner.deal.protection_extended | Deal | Auto-extend fires: ≥1 stage update in 30 days AND first extension | dogfood CRM (update protectionExpiresAt), partner portal (notification) | dealId, originalExpiry, newExpiry, extensionType: 'auto'¦'manual' | Pending | Locked Renil 2026-05-08 (OQ-20)
blazeup.partner.deal.won | Deal | Partner marks Won in portal OR BlazeUp rep closes in dogfood CRM | ms-sa-partners (commission calc + provision), dogfood CRM (close won), billing | dealId, tenantId, closedACV | Pending
blazeup.partner.deal.lost | Deal | SA marks deal Lost with reason | dogfood CRM (close lost), partner portal (notification) | dealId, closeReason | Pending
blazeup.partner.deal.expired | Deal | Protection window elapsed without activity or already auto-extended once | dogfood CRM (mark Stale + task), partner portal (expiry notification) | dealId, expiredAt | Pending
blazeup.partner.commission.earned | Commission | Commission calculated on deal close | SA commission ledger (pending approval queue) | commissionId, dealId, amount, rate, basis (NN/EN/EE) | Pending
blazeup.partner.commission.paid | Commission | SA approves commission + payout processed | partner portal (notification), accounting system | commissionId, paidAt, payoutBatchId | Pending
blazeup.partner.commission.waiver_decided | Commission | SA makes product-failure waiver decision | partner portal (notification), commission ledger | commissionId, decision: 'granted'¦'denied', amount, decidedBy | Pending | Locked Renil 2026-05-08
blazeup.partner.client.health_alert | Client | Client health signal drops (At Risk / Inactive threshold crossed) | dogfood CRM (task on account), partner portal (action required card) | tenantId, partnerId, oldStatus, newStatus, signals{} | Pending | The moat — native health data
blazeup.partner.client.transferred | Client | SA completes MSP handoff — attribution.partnerId updated | dogfood CRM (update account), both MSP portals, attribution history | tenantId, fromPartnerId, toPartnerId, reason, approvedBy | Pending | Locked Renil 2026-05-15 (B4)
blazeup.partner.msp_ticket_consent.changed | MSP | Client tenant admin grants or revokes MSP ticket-content consent | PartnerScopeGuard (immediate effect), audit log | tenantId, partnerId, granted: bool, actorId, timestamp | Pending | Locked Renil 2026-05-08 (OQ-22). PDPA/PDPL audit.
blazeup.partner.sandbox.reset_requested | Sandbox | Partner clicks Reset Demo in portal — sandbox re-seeds within 5 min | blazeup-microservice-sandbox-data (truncate + re-seed) | tenantId, partnerId, profile: 'smb'¦'midmarket'¦'enterprise' | Pending | Locked Renil 2026-05-15 (B5)
blazeup.partner.certification.earned | Training | Partner team member completes certification module | Tier qualification engine (re-evaluate), partner portal (badge update) | partnerId, userId, certificationType, earnedAt | Pending

## 🔌 API Endpoints
BlazeUp Partner Platform — REST API Endpoints (PRD §8.5)
Method | Endpoint | Auth | Category | Description | Key Notes | FE Uses? | Status
GET | /internal/partners | SA-JWT | SA Partner | List all partners (filterable by tier/type/region/status) |  | No | Pending
POST | /internal/partners | SA-JWT | SA Partner | Create partner account |  | No | Pending
PATCH | /internal/partners/:id | SA-JWT | SA Partner | Update partner account (tier, territories, notes, managerAllocation) |  | No | Pending
POST | /internal/partners/:id/approve | SA-JWT | SA Partner | Advance partner application through 3-stage FSM (B3). Records legal countersign or final approval. | 3-stage: SA Review → Legal Countersign → SA Final Approval | No | Pending
GET | /internal/partners/:id/commissions | SA-JWT | SA Partner | Full commission ledger for partner (earned, pending, paid, disputed, clawback) |  | No | Pending
POST | /internal/partners/:id/commissions/:cid/approve | SA-JWT | SA Commission | Approve commission payout. Two-eye required for >$10K. | Two-eye principle for amounts >$10K | No | Pending
POST | /internal/partners/:id/commissions/:cid/waiver-decision | SA-JWT | SA Commission | Record product-failure waiver decision. 30-day SLA. Decision final + logged. | Locked Renil 2026-05-08 | No | Pending
GET | /internal/deals | SA-JWT | SA Deal | All partner deals (filterable). Includes pending approval queue. |  | No | Pending
PATCH | /internal/deals/:id/approve | SA-JWT | SA Deal | Approve deal. Stamps commissionRate + rateTableVersion. Starts protection clock. Optionally proposes cosellSplit for co-sell >$100K ACV. | Rate locked at this moment. cosellSplit pending partner acceptance. | No | Pending
PATCH | /internal/deals/:id/reject | SA-JWT | SA Deal | Reject deal with mandatory reason |  | No | Pending
PATCH | /internal/deals/:id/protection-extend | SA-JWT | SA Deal | Manual SA extension after auto-extend exhausted (requires written reasoning) | Locked Renil 2026-05-08 (OQ-20) | No | Pending
GET | /internal/deals/conflicts | SA-JWT | SA Deal | Conflict queue — deals with competing registrations |  | No | Pending
PATCH | /internal/deals/conflicts/:id/resolve | SA-JWT | SA Deal | Resolve conflict — award to party A/B, mandatory reasoning, both notified, logged immutably | R1 mitigation | No | Pending
GET | /internal/commission/rates | SA-JWT | SA Commission | Current rate table (all versions available) |  | No | Pending
PUT | /internal/commission/rates | SA-JWT | SA Commission | Update rate table — creates new version, preserves all previous. NN/EN/EE rates per tier × deal-type. | B6 resolved — versioned | No | Pending
POST | /internal/commission/spiff | SA-JWT | SA Commission | Create SPIFF programme with regions, tiers, dates, bonus rate |  | No | Pending
GET | /v1/partner/dashboard | Partner-JWT | Partner Portal | Dashboard stats: pipeline, commissions, clients, tier progress, action required items |  | Yes | Pending
POST | /v1/partner/deals | Partner-JWT | Partner Portal | Register a new deal. Triggers conflict check + enrichment. Returns Deal ID + status. | Most critical endpoint. <2s response required. | Yes | Pending
GET | /v1/partner/deals | Partner-JWT | Partner Portal | List own deals with filter/search. Includes deal protection status. |  | Yes | Pending
PATCH | /v1/partner/deals/:id | Partner-JWT | Partner Portal | Update deal (notes, documents, stage update). Updates lastStageUpdateAt. | lastStageUpdateAt drives auto-extend gate | Yes | Pending
POST | /v1/partner/deals/:id/cosell-split-accept | Partner-JWT | Partner Portal | Partner formally accepts SA-proposed co-sell split override. Written acceptance recorded. | Locked Renil 2026-05-08 (Scenario C) | Yes | Pending
POST | /v1/partner/deals/:id/protection-extend-request | Partner-JWT | Partner Portal | Request manual SA extension after hard expiry. SA reviews with reasoning required. | Locked Renil 2026-05-08 (OQ-20) | Yes | Pending
GET | /v1/partner/clients | Partner-JWT | Partner Portal | List post-close clients with health status, ARR, renewal date, modules active |  | Yes | Pending
GET | /v1/partner/clients/:tenantId/health | Partner-JWT | Partner Portal | Detailed health metrics: MAU/DAU, module adoption %, last login, open tickets | The moat endpoint | Yes | Pending
GET | /v1/partner/clients/:tenantId/tickets | Partner-JWT | Partner Portal | Ticket count + severity (always). Ticket content ONLY if mspTicketContentConsent.granted=true. Sentinel response when restricted. | PartnerScopeGuard enforced. Locked Renil 2026-05-08 (OQ-22) | Yes | Pending
GET | /v1/partner/commissions | Partner-JWT | Partner Portal | Full commission history: earned, pending, paid, disputed, clawback |  | Yes | Pending
POST | /v1/partner/commissions/:id/dispute | Partner-JWT | Partner Portal | Raise commission dispute (one text field). SA Slack notification. 5-day SLA. | No form, no ticket number | Yes | Pending
POST | /v1/partner/commissions/:id/waiver | Partner-JWT | Partner Portal | Request product-failure waiver with evidence (linked support tickets / incident reports). SA 30-day SLA. | Locked Renil 2026-05-08 | Yes | Pending
GET | /v1/partner/referral-links | Partner-JWT | Partner Portal | List all referral links with click/conversion/ARR analytics per link |  | Yes | Pending
POST | /v1/partner/referral-links | Partner-JWT | Partner Portal | Create campaign referral link |  | Yes | Pending

## API Dev(Actual)
BlazeUp SA-Partners API — Dev Actual ¦ Source: https://api.stg.blazeup.ai/sa-partners-api/api-docs ¦ Captured: 2026-05-27
# | Method | Path | Auth | Tag / Category | Req Mapping | Status | Notes
Legend: 🟢 Path changed (req→dev, same function) 🟡 Path + Method changed 🔵 Dev-only (not in requirement) 🔴 In requirement only (not yet in dev) ⚫ Deprecated
Global / Health & Infra
1 | GET | /sa-partners-api/health | None | Health | — | 🔵 Dev only | Service liveness check
2 | POST | /sa-partners-api/tenant | x-api-key | Health | — | 🔵 Dev only | Internal: add tenant to service
3 | DELETE | /sa-partners-api/cache/clear | x-api-key | Health | — | 🔵 Dev only | Internal: clear Redis cache
4 | GET | /sa-partners-api/cache/{id} | x-api-key | Health | — | 🔵 Dev only | Internal: inspect cache entry
Partner Auth
5 | POST | /v1/partner/auth/login | None | Partner Auth | — | 🔵 Dev only | Partner portal login — not in PRD §8.5
6 | POST | /v1/partner/auth/refresh | None | Partner Auth | — | 🔵 Dev only | Refresh access token
7 | POST | /v1/partner/auth/logout | JWT | Partner Auth | — | 🔵 Dev only | Invalidate refresh token
8 | GET | /v1/partner/auth/me | JWT | Partner Auth | — | 🔵 Dev only | Get current partner user profile
9 | POST | /v1/partner/auth/change-password | JWT | Partner Auth | — | 🔵 Dev only | Change password
10 | GET | /v1/partner/auth/users | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use GET /v1/sa/partner-users
11 | POST | /v1/partner/auth/invite | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use POST /v1/sa/partner-users
12 | POST | /v1/partner/auth/users/{userId}/reset-password | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use POST /v1/sa/partner-users/{userId}/reset-password
SA — Partners Management
13 | GET | /v1/sa/partners | JWT | Partners | GET /internal/partners | 🟢 Path changed | Path: /internal/ → /v1/sa/
14 | POST | /v1/sa/partners | JWT | Partners | POST /internal/partners | 🟢 Path changed | Path: /internal/ → /v1/sa/
15 | GET | /v1/sa/partners/{id} | JWT | Partners | — | 🔵 Dev only | Get single partner — not in requirement
16 | PATCH | /v1/sa/partners/{id} | JWT | Partners | PATCH /internal/partners/:id | 🟢 Path changed | Path: /internal/ → /v1/sa/
17 | DELETE | /v1/sa/partners/{id} | JWT | Partners | — | 🔵 Dev only | Soft delete — not in requirement
18 | POST | /v1/sa/partners/{id}/approve | JWT | Partners | POST /internal/partners/:id/approve | 🟢 Path changed | Path: /internal/ → /v1/sa/
19 | POST | /v1/sa/partners/{id}/upgrade-tier | JWT | Partners | — | 🔵 Dev only | Tier upgrade/downgrade — not in requirement
20 | POST | /v1/sa/partners/{id}/deactivate | JWT | Partners | — | 🔵 Dev only | Suspend partner — not in requirement
SA — Partner Users
21 | GET | /v1/sa/partner-users | JWT | SA Partner Users | — | 🔵 Dev only | List portal users for a partner
22 | POST | /v1/sa/partner-users | JWT | SA Partner Users | — | 🔵 Dev only | Invite portal user
23 | POST | /v1/sa/partner-users/{userId}/reset-password | JWT | SA Partner Users | — | 🔵 Dev only | Reset portal user password
24 | POST | /v1/sa/partner-users/{userId}/unlock | JWT | SA Partner Users | — | 🔵 Dev only | SA clears login + MFA lockouts. 200 even when not locked; ghost id → 400 "User X not found". Lockout threshold unspecified — OQ-28
SA — Deals
25 | POST | /v1/sa/deals | JWT | SA Partner Deals | — | 🔵 Dev only | SA registers deal — not in requirement
26 | GET | /v1/sa/deals | JWT | SA Partner Deals | GET /internal/deals | 🟢 Path changed | Path: /internal/ → /v1/sa/; conflict queue is now a filter param, not separate endpoint
27 | GET | /v1/sa/deals/{id} | JWT | SA Partner Deals | — | 🔵 Dev only | Get single deal by ID — not in requirement
28 | GET | /v1/sa/deals/stats | JWT | SA Partner Deals | — | 🔵 Dev only | SA-wide pipeline KPI + byProvisioningState. Measured 2026-09-24: total 1411, overdue 81
29 | POST | /v1/sa/deals/{id}/approve | JWT | SA Partner Deals | PATCH /internal/deals/:id/approve | 🟡 Path + Method | Method: PATCH→POST; path: /internal/→/v1/sa/
30 | POST | /v1/sa/deals/{id}/reject | JWT | SA Partner Deals | PATCH /internal/deals/:id/reject | 🟡 Path + Method | Method: PATCH→POST; path: /internal/→/v1/sa/
31 | POST | /v1/sa/deals/{id}/win | JWT | Partner Deals | — | 🔵 Dev only | Mark deal won — not in requirement
32 | POST | /v1/sa/deals/{id}/lose | JWT | SA Partner Deals | — | 🔵 Dev only | Mark deal lost — not in requirement
33 | POST | /v1/sa/deals/{id}/resolve-conflict | JWT | SA Partner Deals | PATCH /internal/deals/conflicts/:id/resolve | 🟡 Path + Method | Method: PATCH→POST; path restructured; /conflicts/ removed from path
34 | POST | /v1/sa/deals/{id}/extend-protection | JWT | SA Partner Deals | PATCH /internal/deals/:id/protection-extend | 🟡 Path + Method | Method: PATCH→POST; renamed protection-extend→extend-protection
SA — Commissions
35 | GET | /v1/sa/commissions | JWT | SA Partner Commissions | GET /internal/SA Partners/:id/commissions | 🟢 Path changed | Flattened: was nested under partner, now flat list with filter
36 | GET | /v1/sa/commissions/summary | JWT | SA Partner Commissions | — | 🔵 Dev only | Payout summary stats — not in requirement
37 | GET | /v1/sa/commissions/{id} | JWT | SA Partner Commissions | — | 🔵 Dev only | Get single commission — not in requirement
38 | POST | /v1/sa/commissions/{id}/approve-payout | JWT | SA Partner Commissions | POST /internal/partners/:id/commissions/:cid/approve | 🟢 Path changed | Path flattened + renamed approve→approve-payout
39 | POST | /v1/sa/commissions/{id}/dispute | JWT | SA Partner Commissions | — | 🔵 Dev only | SA flags commission as disputed — not in requirement
40 | POST | /v1/sa/commissions/{id}/clawback | JWT | SA Partner Commissions | POST /internal/partners/:id/commissions/:cid/waiver-decision | 🟡 Path + Method | ⚠️ Possible mismatch: req=waiver-decision, dev=clawback — confirm scope with dev
SA — Rate Table
41 | GET | /v1/sa/rate-table | JWT | SA Partner Rate Table | GET /internal/commission/rates | 🟢 Path changed | Path renamed; /commission/rates → /rate-table
42 | POST | /v1/sa/rate-table | JWT | SA Partner Rate Table | PUT /internal/commission/rates | 🟡 Path + Method | Method: PUT→POST; path renamed
SA — Territories
43 | POST | /v1/sa/territories | JWT | SA Partner Territories | — | 🔵 Dev only | Assign territory — not in requirement
44 | GET | /v1/sa/territories | JWT | SA Partner Territories | — | 🔵 Dev only | List territories — not in requirement
45 | GET | /v1/sa/territories/{id} | JWT | SA Partner Territories | — | 🔵 Dev only | Get territory — not in requirement
46 | DELETE | /v1/sa/territories/{id} | JWT | SA Partner Territories | — | 🔵 Dev only | Remove territory — not in requirement
SA — Certifications
47 | POST | /v1/sa/partner-users/{userId}/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | Grant/renew certification — not in requirement
48 | DELETE | /v1/sa/partner-users/{userId}/certifications/{certificationType} | JWT | SA Partner Certifications | — | 🔵 Dev only | Revoke certification — not in requirement
49 | GET | /v1/sa/partners/{partnerId}/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | List partner team certifications — not in requirement
50 | GET | /v1/sa/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | List certifications expiring soon — not in requirement
SA — Audit Log
51 | GET | /v1/sa/audit-logs | JWT | SA Audit Log | — | 🔵 Dev only | List audit log entries — not in requirement (§9.4 covers requirement side)
52 | GET | /v1/sa/audit-logs/stats | JWT | SA Audit Log | — | 🔵 Dev only | Audit KPI stats (24h window)
53 | GET | /v1/sa/audit-logs/export | JWT | SA Audit Log | — | 🔵 Dev only | Export audit log CSV/JSON max 10,000 rows
54 | GET | /v1/sa/audit-logs/{id} | JWT | SA Audit Log | — | 🔵 Dev only | Get single audit log entry
Partner Portal
55 | GET | /v1/partner/portal/dashboard | JWT | Partner Portal | GET /v1/partner/dashboard | 🟢 Path changed | Added /portal/ segment to path
56 | GET | /v1/partner/portal/profile | JWT | Partner Portal | — | 🔵 Dev only | Own partner profile — not in requirement
57 | GET | /v1/partner/portal/deals | JWT | Partner Portal | GET /v1/partner/deals | 🟢 Path changed | Added /portal/ segment
58 | POST | /v1/partner/portal/deals | JWT | Partner Portal | POST /v1/partner/deals | 🟢 Path changed | Added /portal/ segment
59 | GET | /v1/partner/portal/deals/{id} | JWT | Partner Portal | — | 🔵 Dev only | Get deal detail — not in requirement
60 | GET | /v1/partner/portal/certifications | JWT | Partner Portal | — | 🔵 Dev only | Own certifications — not in requirement
61 | GET | /v1/partner/portal/team/certifications | JWT | Partner Portal | — | 🔵 Dev only | Team certifications (admin) — not in requirement
62 | GET | /v1/partner/portal/commissions | JWT | Partner Portal | GET /v1/partner/commissions | 🟢 Path changed | Added /portal/ segment
63 | GET | /v1/partner/portal/commissions/summary | JWT | Partner Portal | — | 🔵 Dev only | Own commission summary — not in requirement
64 | POST | /v1/partner/portal/commissions/{id}/dispute | JWT | Partner Portal | POST /v1/partner/commissions/:id/dispute | 🟢 Path changed | Added /portal/ segment
65 | GET | /v1/partner/portal/territories | JWT | Partner Portal | — | 🔵 Dev only | Own territories — not in requirement
66 | GET | /v1/partner/portal/rates | JWT | Partner Portal | — | 🔵 Dev only | Commission rates for own tier — not in requirement
67 | GET | /v1/partner/portal/countries | JWT | Partner Portal | — | 🔵 Dev only | 250 ISO countries; search = partial, case-insensitive. Deal-registration / win-deal country picker
68 | GET | /v1/partner/portal/deals/stats | JWT | Partner Portal | — | 🔵 Dev only | Own pipeline KPI, JWT-scoped. Correctly omits byProvisioningState (SA-only)
🔴 In Requirement ONLY — Not Yet in Dev
65 | — | /internal/deals/conflicts [GET] | SA-JWT | SA Deal | GET /internal/deals/conflicts | 🔴 Req only (missing) | Dedicated conflict queue endpoint — dev uses filter param on GET /v1/sa/deals instead
66 | — | /v1/partner/deals/:id [PATCH] | Partner-JWT | Partner Portal | PATCH /v1/partner/deals/:id | 🔴 Req only (missing) | Update deal notes/docs/stage — dev only has GET deal detail, no PATCH
67 | — | /v1/partner/deals/:id/cosell-split-accept [POST] | Partner-JWT | Partner Portal | POST /v1/partner/deals/:id/cosell-split-accept | 🔴 Req only (missing) | Scenario C — co-sell split acceptance not implemented
68 | — | /v1/partner/deals/:id/protection-extend-request [POST] | Partner-JWT | Partner Portal | POST /v1/partner/deals/:id/protection-extend-request | 🔴 Req only (missing) | Manual extension request by partner — not in dev
69 | — | /v1/partner/clients [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients | 🔴 Req only (missing) | ⚠️ Entire My Clients section missing from dev
70 | — | /v1/partner/clients/:tenantId/health [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients/:tenantId/health | 🔴 Req only (missing) | ⚠️ Client health metrics — core product moat feature not in dev
71 | — | /v1/partner/clients/:tenantId/tickets [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients/:tenantId/tickets | 🔴 Req only (missing) | ⚠️ MSP ticket visibility — not in dev
72 | — | /v1/partner/commissions/:id/waiver [POST] | Partner-JWT | Partner Portal | POST /v1/partner/commissions/:id/waiver | 🔴 Req only (missing) | Product-failure waiver request by partner — not in dev
73 | — | /v1/partner/referral-links [GET] | Partner-JWT | Partner Portal | GET /v1/partner/referral-links | 🔴 Req only (missing) | Referral links list + analytics — not in dev
74 | — | /v1/partner/referral-links [POST] | Partner-JWT | Partner Portal | POST /v1/partner/referral-links | 🔴 Req only (missing) | Create campaign referral link — not in dev
75 | — | /internal/commission/spiff [POST] | SA-JWT | SA Commission | POST /internal/commission/spiff | 🔴 Req only (missing) | SPIFF programme management — not in dev
SUMMARY
Total Dev Endpoints | 75
Total Requirement Endpoints | 30
🟢 Path/structure changed (matched) | 14
🟡 Path + Method changed | 6
🔵 Dev-only (new, not in requirement) | 45
🔴 Requirement-only (not yet in dev) | 11
⚫ Deprecated | 3