## 📋 Overview
BlazeUp Partner Platform — Requirements Tracker
PRD v1.8 · 2026-05-15 · Author: BlazeUp Admin
Document Status | PRD — All 6 BLOCKING items resolved. Build can start.
PRD Version | v1.8 (supersedes v1.1)
Last Updated | 2026-05-15
Author | BlazeUp Admin
Scope | Channel Partners only (Referral, Reseller/VAR, SI, MSP). Pack Partners are out-of-scope (see marketplace-pack-architecture-v1.1.md).
Critical Path | ms-sa-partners core + Renil-locked surface + CRM bridge + portal deal registration + SA approval queue = ~7 weeks to v1
Full Build ETA | ~14 weeks (all pages + SA module + attribution)
Auth Gate | B1 — Auth Hardening Phase 0 PRs #633–#641 must merge before partner auth surfaces go live. All non-auth coding proceeds in parallel.
Key Architecture | BlazeUp does NOT build a separate SA CRM. Dogfood tenant at blazeup.blazeup.ai is the only CRM. Partner deals auto-appear as opportunities with source='partner_registered'.
Repo / Services | blazeup-microservice-sa-partners · blazeup-hostapp-partner (pp- prefix) · blazeup-subapp-sa-partners · blazeup-subapp-partner-dashboard · blazeup-subapp-partner-training
Partner Portal URL | partner.blazeup.ai
SHEET INDEX
📋 Overview | This sheet — PRD metadata and index
🎯 Feature Requirements | All features by section/number with FE·BE status, confirm flag, notes
⚠️ Risk Register | 8 risk flags (R1–R8) with severity, impact, mitigation and tracking
❓ Open Questions | Blocking (B1-B6), non-blocking (OQ), and Legal/Compliance items
🗃️ Data Models | MongoDB collections and key schema fields
📡 Kafka Events | All Kafka event names, purpose, triggers, consumers
🔌 API Endpoints | All REST API routes with method, auth, description, status

## API Dev(Actual)
BlazeUp SA-Partners API — Dev Actual ¦ Source: https://api.stg.blazeup.ai/sa-partners-api/api-docs ¦ Captured: 2026-05-27
# | Method | Path | Auth | Tag / Category | Req Mapping | Status | Notes
Legend: 🟢 Path changed (req→dev, same function) 🟡 Path + Method changed 🔵 Dev-only (not in requirement) 🔴 In requirement only (not yet in dev) ⚫ Deprecated
Global / Health & Infra
1 | GET | /sa-partners-api/health | None | Health | — | 🔵 Dev only | Service liveness check
2 | POST | /sa-partners-api/tenant | x-api-key | Health | — | 🔵 Dev only | Internal: add tenant to service
3 | DELETE | /sa-partners-api/cache/clear | x-api-key | Health | — | 🔵 Dev only | Internal: clear Redis cache
4 | GET | /sa-partners-api/cache/{id} | x-api-key | Health | — | 🔵 Dev only | Internal: inspect cache entry
Partner Auth
5 | POST | /v1/partner/auth/login | None | Partner Auth | — | 🔵 Dev only | Partner portal login — not in PRD §8.5
6 | POST | /v1/partner/auth/refresh | None | Partner Auth | — | 🔵 Dev only | Refresh access token
7 | POST | /v1/partner/auth/logout | JWT | Partner Auth | — | 🔵 Dev only | Invalidate refresh token
8 | GET | /v1/partner/auth/me | JWT | Partner Auth | — | 🔵 Dev only | Get current partner user profile
9 | POST | /v1/partner/auth/change-password | JWT | Partner Auth | — | 🔵 Dev only | Change password
10 | GET | /v1/partner/auth/users | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use GET /v1/sa/partner-users
11 | POST | /v1/partner/auth/invite | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use POST /v1/sa/partner-users
12 | POST | /v1/partner/auth/users/{userId}/reset-password | JWT | Partner Auth | — | ⚫ Deprecated | Deprecated → use POST /v1/sa/partner-users/{userId}/reset-password
SA — Partners Management
13 | GET | /v1/sa/partners | JWT | Partners | GET /internal/partners | 🟢 Path changed | Path: /internal/ → /v1/sa/
14 | POST | /v1/sa/partners | JWT | Partners | POST /internal/partners | 🟢 Path changed | Path: /internal/ → /v1/sa/
15 | GET | /v1/sa/partners/{id} | JWT | Partners | — | 🔵 Dev only | Get single partner — not in requirement
16 | PATCH | /v1/sa/partners/{id} | JWT | Partners | PATCH /internal/partners/:id | 🟢 Path changed | Path: /internal/ → /v1/sa/
17 | DELETE | /v1/sa/partners/{id} | JWT | Partners | — | 🔵 Dev only | Soft delete — not in requirement
18 | POST | /v1/sa/partners/{id}/approve | JWT | Partners | POST /internal/partners/:id/approve | 🟢 Path changed | Path: /internal/ → /v1/sa/
19 | POST | /v1/sa/partners/{id}/upgrade-tier | JWT | Partners | — | 🔵 Dev only | Tier upgrade/downgrade — not in requirement
20 | POST | /v1/sa/partners/{id}/deactivate | JWT | Partners | — | 🔵 Dev only | Suspend partner — not in requirement
SA — Partner Users
21 | GET | /v1/sa/partner-users | JWT | SA Partner Users | — | 🔵 Dev only | List portal users for a partner
22 | POST | /v1/sa/partner-users | JWT | SA Partner Users | — | 🔵 Dev only | Invite portal user
23 | POST | /v1/sa/partner-users/{userId}/reset-password | JWT | SA Partner Users | — | 🔵 Dev only | Reset portal user password
SA — Deals
24 | POST | /v1/sa/deals | JWT | Partner Deals | — | 🔵 Dev only | SA registers deal — not in requirement
25 | GET | /v1/sa/deals | JWT | Partner Deals | GET /internal/deals | 🟢 Path changed | Path: /internal/ → /v1/sa/; conflict queue is now a filter param, not separate endpoint
26 | GET | /v1/sa/deals/{id} | JWT | Partner Deals | — | 🔵 Dev only | Get single deal by ID — not in requirement
27 | POST | /v1/sa/deals/{id}/approve | JWT | Partner Deals | PATCH /internal/deals/:id/approve | 🟡 Path + Method | Method: PATCH→POST; path: /internal/→/v1/sa/
28 | POST | /v1/sa/deals/{id}/reject | JWT | Partner Deals | PATCH /internal/deals/:id/reject | 🟡 Path + Method | Method: PATCH→POST; path: /internal/→/v1/sa/
29 | POST | /v1/sa/deals/{id}/win | JWT | Partner Deals | — | 🔵 Dev only | Mark deal won — not in requirement
30 | POST | /v1/sa/deals/{id}/lose | JWT | Partner Deals | — | 🔵 Dev only | Mark deal lost — not in requirement
31 | POST | /v1/sa/deals/{id}/resolve-conflict | JWT | Partner Deals | PATCH /internal/deals/conflicts/:id/resolve | 🟡 Path + Method | Method: PATCH→POST; path restructured; /conflicts/ removed from path
32 | POST | /v1/sa/deals/{id}/extend-protection | JWT | Partner Deals | PATCH /internal/deals/:id/protection-extend | 🟡 Path + Method | Method: PATCH→POST; renamed protection-extend→extend-protection
SA — Commissions
33 | GET | /v1/sa/commissions | JWT | Partner Commissions | GET /internal/partners/:id/commissions | 🟢 Path changed | Flattened: was nested under partner, now flat list with filter
34 | GET | /v1/sa/commissions/summary | JWT | Partner Commissions | — | 🔵 Dev only | Payout summary stats — not in requirement
35 | GET | /v1/sa/commissions/{id} | JWT | Partner Commissions | — | 🔵 Dev only | Get single commission — not in requirement
36 | POST | /v1/sa/commissions/{id}/approve-payout | JWT | Partner Commissions | POST /internal/partners/:id/commissions/:cid/approve | 🟢 Path changed | Path flattened + renamed approve→approve-payout
37 | POST | /v1/sa/commissions/{id}/dispute | JWT | Partner Commissions | — | 🔵 Dev only | SA flags commission as disputed — not in requirement
38 | POST | /v1/sa/commissions/{id}/clawback | JWT | Partner Commissions | POST /internal/partners/:id/commissions/:cid/waiver-decision | 🟡 Path + Method | ⚠️ Possible mismatch: req=waiver-decision, dev=clawback — confirm scope with dev
SA — Rate Table
39 | GET | /v1/sa/rate-table | JWT | Partner Rate Table | GET /internal/commission/rates | 🟢 Path changed | Path renamed; /commission/rates → /rate-table
40 | POST | /v1/sa/rate-table | JWT | Partner Rate Table | PUT /internal/commission/rates | 🟡 Path + Method | Method: PUT→POST; path renamed
SA — Territories
41 | POST | /v1/sa/territories | JWT | Partner Territories | — | 🔵 Dev only | Assign territory — not in requirement
42 | GET | /v1/sa/territories | JWT | Partner Territories | — | 🔵 Dev only | List territories — not in requirement
43 | GET | /v1/sa/territories/{id} | JWT | Partner Territories | — | 🔵 Dev only | Get territory — not in requirement
44 | DELETE | /v1/sa/territories/{id} | JWT | Partner Territories | — | 🔵 Dev only | Remove territory — not in requirement
SA — Certifications
45 | POST | /v1/sa/partner-users/{userId}/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | Grant/renew certification — not in requirement
46 | DELETE | /v1/sa/partner-users/{userId}/certifications/{certificationType} | JWT | SA Partner Certifications | — | 🔵 Dev only | Revoke certification — not in requirement
47 | GET | /v1/sa/partners/{partnerId}/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | List partner team certifications — not in requirement
48 | GET | /v1/sa/certifications | JWT | SA Partner Certifications | — | 🔵 Dev only | List certifications expiring soon — not in requirement
SA — Audit Log
49 | GET | /v1/sa/audit-logs | JWT | SA Audit Log | — | 🔵 Dev only | List audit log entries — not in requirement (§9.4 covers requirement side)
50 | GET | /v1/sa/audit-logs/stats | JWT | SA Audit Log | — | 🔵 Dev only | Audit KPI stats (24h window)
51 | GET | /v1/sa/audit-logs/export | JWT | SA Audit Log | — | 🔵 Dev only | Export audit log CSV/JSON max 10,000 rows
52 | GET | /v1/sa/audit-logs/{id} | JWT | SA Audit Log | — | 🔵 Dev only | Get single audit log entry
Partner Portal
53 | GET | /v1/partner/portal/dashboard | JWT | Partner Portal | GET /v1/partner/dashboard | 🟢 Path changed | Added /portal/ segment to path
54 | GET | /v1/partner/portal/profile | JWT | Partner Portal | — | 🔵 Dev only | Own partner profile — not in requirement
55 | GET | /v1/partner/portal/deals | JWT | Partner Portal | GET /v1/partner/deals | 🟢 Path changed | Added /portal/ segment
56 | POST | /v1/partner/portal/deals | JWT | Partner Portal | POST /v1/partner/deals | 🟢 Path changed | Added /portal/ segment
57 | GET | /v1/partner/portal/deals/{id} | JWT | Partner Portal | — | 🔵 Dev only | Get deal detail — not in requirement
58 | GET | /v1/partner/portal/certifications | JWT | Partner Portal | — | 🔵 Dev only | Own certifications — not in requirement
59 | GET | /v1/partner/portal/team/certifications | JWT | Partner Portal | — | 🔵 Dev only | Team certifications (admin) — not in requirement
60 | GET | /v1/partner/portal/commissions | JWT | Partner Portal | GET /v1/partner/commissions | 🟢 Path changed | Added /portal/ segment
61 | GET | /v1/partner/portal/commissions/summary | JWT | Partner Portal | — | 🔵 Dev only | Own commission summary — not in requirement
62 | POST | /v1/partner/portal/commissions/{id}/dispute | JWT | Partner Portal | POST /v1/partner/commissions/:id/dispute | 🟢 Path changed | Added /portal/ segment
63 | GET | /v1/partner/portal/territories | JWT | Partner Portal | — | 🔵 Dev only | Own territories — not in requirement
64 | GET | /v1/partner/portal/rates | JWT | Partner Portal | — | 🔵 Dev only | Commission rates for own tier — not in requirement
🔴 In Requirement ONLY — Not Yet in Dev
65 | — | /internal/deals/conflicts [GET] | SA-JWT | SA Deal | GET /internal/deals/conflicts | 🔴 Req only (missing) | Dedicated conflict queue endpoint — dev uses filter param on GET /v1/sa/deals instead
66 | — | /v1/partner/deals/:id [PATCH] | Partner-JWT | Partner Portal | PATCH /v1/partner/deals/:id | 🔴 Req only (missing) | Update deal notes/docs/stage — dev only has GET deal detail, no PATCH
67 | — | /v1/partner/deals/:id/cosell-split-accept [POST] | Partner-JWT | Partner Portal | POST /v1/partner/deals/:id/cosell-split-accept | 🔴 Req only (missing) | Scenario C — co-sell split acceptance not implemented
68 | — | /v1/partner/deals/:id/protection-extend-request [POST] | Partner-JWT | Partner Portal | POST /v1/partner/deals/:id/protection-extend-request | 🔴 Req only (missing) | Manual extension request by partner — not in dev
69 | — | /v1/partner/clients [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients | 🔴 Req only (missing) | ⚠️ Entire My Clients section missing from dev
70 | — | /v1/partner/clients/:tenantId/health [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients/:tenantId/health | 🔴 Req only (missing) | ⚠️ Client health metrics — core product moat feature not in dev
71 | — | /v1/partner/clients/:tenantId/tickets [GET] | Partner-JWT | Partner Portal | GET /v1/partner/clients/:tenantId/tickets | 🔴 Req only (missing) | ⚠️ MSP ticket visibility — not in dev
72 | — | /v1/partner/commissions/:id/waiver [POST] | Partner-JWT | Partner Portal | POST /v1/partner/commissions/:id/waiver | 🔴 Req only (missing) | Product-failure waiver request by partner — not in dev
73 | — | /v1/partner/referral-links [GET] | Partner-JWT | Partner Portal | GET /v1/partner/referral-links | 🔴 Req only (missing) | Referral links list + analytics — not in dev
74 | — | /v1/partner/referral-links [POST] | Partner-JWT | Partner Portal | POST /v1/partner/referral-links | 🔴 Req only (missing) | Create campaign referral link — not in dev
75 | — | /internal/commission/spiff [POST] | SA-JWT | SA Commission | POST /internal/commission/spiff | 🔴 Req only (missing) | SPIFF programme management — not in dev
SUMMARY
Total Dev Endpoints | 71
Total Requirement Endpoints | 30
🟢 Path/structure changed (matched) | 14
🟡 Path + Method changed | 6
🔵 Dev-only (new, not in requirement) | 41
🔴 Requirement-only (not yet in dev) | 11
⚫ Deprecated | 3

## 🎯 Feature Requirements
Section # | Feature / Requirement | Description / Details | Priority | Confirmed? | Confirm Note / Owner | FE Status | FE Note | BE Status | BE Note | Blocker / Dependency | Effort Estimate | Remarks | Test Case IDs
§1 — Context & Strategic Fit
1.1 | Foundational Architecture: No SA CRM | BlazeUp does NOT build a separate SA CRM. Dogfood tenant (blazeup.blazeup.ai) is the only CRM. Partner-registered deals appear as opportunities with source='partner_registered'. Architectural invariant — not a product decision. | Critical | Confirmed |  | N/A | No UI needed — architectural constraint | N/A | Ensure deal events flow to dogfood CRM ms-crm | B1 Auth Phase 0 | — | §6 CRM Integration governs this | —
1.2 | Two Partner Populations: Channel vs Pack | Channel Partners (Resellers, referral agents, SIs, MSPs) live at partner.blazeup.ai. Pack Partners (ISVs) are managed in SA Tier K. A company can hold both; managed independently with separate credentialing and portals. | Critical | Rejected / On Hold |  | In Progress | Separate host app for partner portal | In Progress | Separate JWT issuer, separate partner_accounts collection |  | — | This PRD covers Channel Partners only | PARTNER_API_COMMISSIONS_PAYOUTS_015
1.3 | Product Moat: Native Client Health Data | Partner portal exposes client DAU/MAU trend, module adoption depth, renewal date, AI-generated upsell signals — because BlazeUp IS the platform. No integration needed. Primary retention lever for channel programme. | High | Planned |  | Not Started | Client Health Card UI (§4.6) | Not Started | Read from platform analytics service |  | — |  | PARTNER_API_CLIENT_HEALTH_MSP_002 PARTNER_UI_MY_CLIENTS_003 PARTNER_UI_MY_CLIENTS_008 PARTNER_UI_MY_CLIENTS_010
§2 — Partner Programme Structure
2.1 | 4-Tier Partner Tiers: Registered / Select / Advanced / Premier | Registered ($0), Select ($50K ARR), Advanced ($200K ARR), Premier ($750K ARR). Tier calc: trailing-12M ARR sourced through BlazeUp, computed on first day of each quarter. Upgrade immediate; downgrade with 30-day notice + grace quarter. | Critical | Confirmed |  | Done | Tier progress bar on dashboard (§4.3) | Done | Quarterly cron job to calc T12M ARR + tier FSM + Kafka event |  | 1 week (tier engine) |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_008 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_009 PARTNER_UI_DASHBOARD_003 PARTNER_UI_DASHBOARD_005 PARTNER_UI_DASHBOARD_006
2.1a | PSM Allocation: Dedicated at $1.5M within Premier | Dedicated PSM only at $1.5M ARR within Premier tier. Below $1.5M: shared PSM at max 1:3 ratio. Advanced tier also uses shared pool (1:3). Reviewed annually. managerAllocation field on partner_accounts. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-25) | In Progress |  | In Progress | partner_accounts.managerAllocation: 'dedicated' ¦ 'shared' |  | — | Locked decision | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_008 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_009 PARTNER_UI_DASHBOARD_003 PARTNER_UI_DASHBOARD_005 PARTNER_UI_DASHBOARD_006
2.2 | 4 Partner Types: Referral / Reseller/VAR / SI / MSP | Referral (billing: direct), Reseller/VAR (billing: reseller), SI (billing: direct), MSP (billing: partner_managed). Type selected at registration. Determines deal flows and billing models available. | Critical | Confirmed | Focus on a flow with a simple partner type first | Done | Type selector at registration, billing model display | Done | type field on partner_accounts, billingModel on deals |  | — |  | PARTNER_API_CLIENT_HEALTH_MSP_008 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_009
2.2a | Reseller Pricing Authority | Reseller sets own end-client price. BlazeUp invoices partner at tier discount. BlazeUp does NOT capture partner's sell price anywhere. Standard VAR norm. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-19) | In Progress | No UI for partner sell price — must NOT be captured | Done | No sell-price field on any record |  | — | Locked decision | PARTNER_API_CLIENT_HEALTH_MSP_008 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_009
2.2b | MSP Tier Qualification: Total ARR Managed | MSP trailing-12M ARR for tier qualification = total ARR managed (all client subscriptions billed through them), NOT only net-new logos. Reflects ongoing managed relationship value. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-21) | Done | Display total managed ARR in tier progress | In Progress | T12M ARR calc for MSPs sums all managed subscriptions |  | — | Locked decision | PARTNER_API_CLIENT_HEALTH_MSP_008 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_009
2.3 | Deal Types: Referral / Reseller / Co-sell | Referral (tier referral rate × Y1 ACV), Reseller (margin = list − discount), Co-sell (70/30 default split; override above $100K ACV requires partner agreement in writing, locked at approval). | Critical | Confirmed | Focus on a flow with a simple deal type first | In Progress | Deal type selector in registration wizard | Done | dealType field on partner_deals; commission engine handles all 3 types |  | 3 weeks (commission engine) | §3 Scenarios A/B/C | PARTNER_API_DEAL_REGISTRATION_PIPELINE_011 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_010
2.4 | Certification Programme: 4 Certifications | BlazeUp Sales Certified (4h), HR Specialist (6h), CRM Specialist (4h), Implementation Certified (12h). Completion triggers tier re-evaluation. Delivered inside partner portal training module. | Medium | Confirmed | Training platform decision pending (OQ-8 Aashwij) Note from Dave: We can implement with a simple way | Not Started | Training module with progress tracking (§4.8) | Done | partner_certifications collection; blazeup.partner.certification.earned event | OQ-8 training platform (build vs buy) TBD | 2 weeks |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010 PARTNER_UI_TRAINING_001 PARTNER_UI_TRAINING_002
§3 — Deal Scenarios (A–I)
3-A | Scenario A: Pure Referral | Partner introduces prospect, steps back. Registers deal. BlazeUp sales owns close. Commission = tier referral rate × Y1 ACV. Partner sees read-only pipeline view. BlazeUp rep visible with name/photo; partner can message on deal thread. | Critical | Confirmed | Focus on this scenario first | Done | Read-only deal view, rep photo/contact, deal thread | Done | Deal FSM: Registered→Approved→Won/Lost; commission calc |  | Core (4 weeks) |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_001 PARTNER_UI_MY_PIPELINE_029
3-B | Scenario B: Reseller-Led | Partner sells independently. Registers deal upfront. Marks Won when client signs. Tenant provisioned. BlazeUp invoices partner at reseller discount. Partner invoices client at their own price (not captured by BlazeUp). | Critical | Confirmed | Focus on this scenario second | Done | Won/Lost marking in portal | Done | billing.model='reseller', invoice to partner at discount |  | Core |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_002 PARTNER_UI_MY_PIPELINE_009
3-C | Scenario C: Co-sell (Collaborative) | Partner registers + selects Co-sell. BlazeUp assigns rep within 1 business day. Shared deal record with notes, docs, stage updates. Default 70/30 split. Override above $100K ACV: SA proposes → partner accepts in portal. Split locked at approval. | Critical | Confirmed | Locked — Renil 2026-05-08 (OQ-23) | Not Started | Co-sell split accept UI, shared notes/docs | In Progress | cosellSplit{} on partner_deals; /v1/partner/deals/:id/cosell-split-accept endpoint |  | 1 week (Renil surface) | Locked decision | PARTNER_API_DEAL_REGISTRATION_PIPELINE_003 PARTNER_API_DEAL_REGISTRATION_PIPELINE_011 PARTNER_API_DEAL_REGISTRATION_PIPELINE_012 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010 PARTNER_UI_MY_PIPELINE_010 PARTNER_UI_MY_PIPELINE_016 PARTNER_UI_MY_PIPELINE_017 PARTNER_UI_MY_PIPELINE_018 PARTNER_UI_MY_PIPELINE_027
3-D | Scenario D: Deal Conflict Resolution | Two parties register same domain. Rules in order: (1) prospect confirmed engagement with first party wins; (2) first-registered wins; (3) SA mediates within 5 business days. Loser can re-register after 90 days if no deal closes. | Critical | Confirmed | OQ-17 (90-day auto-unlock vs manual) still open | Not Started | Conflict warning at registration; conflict queue display | Done | partner_conflicts collection; conflict queue API; domain uniqueness check | OQ-17 re-registration mechanism TBD | Core |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_004 PARTNER_API_DEAL_REGISTRATION_PIPELINE_009 PARTNER_API_DEAL_REGISTRATION_PIPELINE_013 PARTNER_API_DEAL_REGISTRATION_PIPELINE_014 PARTNER_API_DEAL_REGISTRATION_PIPELINE_017 PARTNER_UI_MY_PIPELINE_004 PARTNER_UI_MY_PIPELINE_005 PARTNER_UI_MY_PIPELINE_021 PARTNER_UI_SA_PARTNER_MODULE_001 PARTNER_UI_SA_PARTNER_MODULE_002
3-E | Scenario E: Referral Link Attribution (No Registration) | Partner shares blazeup.ai/ref/{slug}. Server captures partner_id on first click (30-day TTL, server-side, survives browser close/incognito/device change). On signup: tenant attributed automatically. Commission triggered. Partner notified. | High | Rejected / On Hold |  | N/A | Referral link management in Settings (§4.10) | Not Started | Redis attr:{sessionToken}, first-touch wins, /v1/tenants/provision reads cookie |  | 1 week (attribution service) | R4 risk mitigation | PARTNER_API_COMMISSIONS_PAYOUTS_008 PARTNER_API_COMMISSIONS_PAYOUTS_009 PARTNER_API_REFERRAL_ATTRIBUTION_001
3-F | Scenario F: Expansion at Existing Client | Partner registers expansion deal against existing tenant_id. On close: modules/seats added to existing tenant (no new tenant). Expansion commission applies on delta ARR using EN/EE stage of lifecycle model. | High | Confirmed | OQ-16 expansion rate — architecture resolved (B6), specific rates TBD (SA-configurable) | Not Started | Expansion deal registration with tenant_id picker | In Progress | Expansion provisioning path; NN/EN/EE classification at commission calc time | B6 resolved — rates SA-configurable before launch | Core | Locked decision B6 | PARTNER_API_COMMISSIONS_PAYOUTS_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_004 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006 PARTNER_UI_MY_CLIENTS_004
3-G | Scenario G: MSP Model (Partner Manages Client) | MSP provisions tenants on behalf of clients. BlazeUp invoices MSP. MSP has scoped admin access: configure modules, manage users, raise tickets, view health. Hard limits: no payroll data, no PII above ceiling, no export. Ticket content gated on client opt-in (default OFF). | High | Confirmed | Locked — Renil 2026-05-08 (OQ-22) | Not Started | Managed Clients view, scoped admin UI, consent toggle | In Progress | PartnerScopeGuard in every MS; mspTicketContentConsent on tenant record; /v1/partner/clients/:id/tickets |  | Core |  | PARTNER_API_AUTH_ACCESS_CONTROL_005 PARTNER_API_CLIENT_HEALTH_MSP_003 PARTNER_API_CLIENT_HEALTH_MSP_004 PARTNER_API_CLIENT_HEALTH_MSP_006 PARTNER_API_CLIENT_HEALTH_MSP_007 PARTNER_API_CLIENT_HEALTH_MSP_009 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_009 PARTNER_UI_MY_CLIENTS_005 PARTNER_UI_MY_CLIENTS_006
3-H | Scenario H: Tech Partner Also Resells (Dual Account) | Pack partner + channel partner under one login. Two separate dashboards with a switcher. Revenue share (pack) and channel commissions tracked in completely separate ledgers. | Medium | Planned |  | Not Started | Account switcher UI, dual dashboard | In Progress | Two account types on same user; separate ledgers |  | — | Lower priority — complex edge case | PARTNER_API_COMMISSIONS_PAYOUTS_015
3-I | Scenario I: Multi-Partner Influenced Deal | Two partners touched same prospect; neither registered. Policy: no registration = no commission (absolute rule, no exceptions). If both registered → Scenario D conflict. Incentive to register early. | Medium | Planned |  | N/A | No special UI — policy enforced at commission calc | In Progress | Commission engine: require deal_id for attribution |  | — |  | PARTNER_API_DEAL_REGISTRATION_PIPELINE_015 PARTNER_UI_MY_PIPELINE_022
§4 — Partner Portal (partner.blazeup.ai)
4.1 | Portal Technical Shell: blazeup-hostapp-partner | New repo, Tailwind prefix pp-. Module Federation host. Separate JWT issuer from tenant and SA. Shared singletons: react, react-dom, react-router aligned with tenant host versions. | Critical | Confirmed |  | Not Started | blazeup-hostapp-partner repo, federation scaffold, nav | In Progress | Separate JWT issuer (distinct iss claim) partner-iam/ scaffolded: login/refresh/logout/me/change-password at /v1/partner/auth/*; PartnerUser schema + partner-jwt.guard.ts; separate JWT issuer (distinct iss claim) gated on B1 Auth Phase 0 | B1 Auth Phase 0 | 1 week |  | PARTNER_API_AUTH_ACCESS_CONTROL_001 PARTNER_API_AUTH_ACCESS_CONTROL_002 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003 PARTNER_UI_DASHBOARD_001 PARTNER_UI_PARTNER_PORTAL_SHELL_002
4.2 | Portal IA: 9 Top-Level Routes | / Home, /deals My Pipeline, /deals/register, /deals/:id, /clients My Clients, /clients/:id, /commissions, /training, /resources, /team, /settings, /support | Critical | Confirmed |  | Not Started | All 9 route shells and navigation | N/A |  |  | 1 week (shell) |  | PARTNER_UI_DASHBOARD_001 PARTNER_UI_PARTNER_PORTAL_SHELL_001
4.3 | Dashboard / Home — Actionable Metrics | Pipeline total/count, Commission earned/pending, Active clients count + renewals <30d, Tier progress bar, ACTION REQUIRED section (co-sell tasks, renewal alerts, dispute resolutions), Mini pipeline kanban, Blazey AI assistant. | High | Confirmed |  | Not Started | Dashboard layout per wireframe in §4.3 | Not Started | /v1/partner/dashboard endpoint aggregating all stats |  | Part of 4-week portal sprint | No vanity metrics — every number must be actionable | PARTNER_API_DASHBOARD_DATA_001 PARTNER_UI_COMMISSIONS_008 PARTNER_UI_DASHBOARD_002 PARTNER_UI_DASHBOARD_003 PARTNER_UI_DASHBOARD_004 PARTNER_UI_DASHBOARD_005 PARTNER_UI_DASHBOARD_007 PARTNER_UI_MY_CLIENTS_001 PARTNER_UI_MY_PIPELINE_023
4.4 | Deal Registration Wizard: ≤90 Seconds on Mobile | 4-step: (1) Company+domain (auto-enrichment via Apollo/Clearbit), inline conflict warning; (2) Contact; (3) Deal ACV+date+modules+type; (4) Confirm. LIVE projected commission updates as ACV typed. Immediate confirmation with Deal ID. Design target: 90s on mobile. | Critical | Confirmed |  | Not Started | 4-step wizard, mobile-optimised, live commission calc | Done | POST /v1/partner/deals, conflict pre-check on domain, enrichment API call |  | Part of 4-week portal sprint | Most critical flow in entire portal | PARTNER_API_DEAL_REGISTRATION_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_001 PARTNER_API_SECURITY_COMPLIANCE_002 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011 PARTNER_UI_COMMISSIONS_001 PARTNER_UI_MY_PIPELINE_001 PARTNER_UI_MY_PIPELINE_002 PARTNER_UI_MY_PIPELINE_003 PARTNER_UI_MY_PIPELINE_004 PARTNER_UI_MY_PIPELINE_006 PARTNER_UI_MY_PIPELINE_007 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_009 PARTNER_UI_MY_PIPELINE_010 PARTNER_UI_MY_PIPELINE_011 PARTNER_UI_MY_PIPELINE_012 PARTNER_UI_MY_PIPELINE_013 PARTNER_UI_MY_PIPELINE_019 PARTNER_UI_MY_PIPELINE_020 PARTNER_UI_MY_PIPELINE_021 PARTNER_UI_PARTNER_PORTAL_SHELL_002 PARTNER_UI_SECURITY_COMPLIANCE_003
4.4a | Live Commission Projection at Registration | As partner types ACV in Step 3, commission estimate updates in real time (tier rate × ACV). Shows deal protection duration. Answers 'is it worth my time to register?' | Critical | Confirmed |  | Not Started | Real-time commission calc display in Step 3 | In Progress | Commission rate table lookup (Redis cache) called client-side or via lightweight endpoint |  | — | Most powerful feature in registration flow | PARTNER_API_DEAL_REGISTRATION_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_001 PARTNER_API_SECURITY_COMPLIANCE_002 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011 PARTNER_UI_COMMISSIONS_001 PARTNER_UI_MY_PIPELINE_001 PARTNER_UI_MY_PIPELINE_002 PARTNER_UI_MY_PIPELINE_003 PARTNER_UI_MY_PIPELINE_004 PARTNER_UI_MY_PIPELINE_006 PARTNER_UI_MY_PIPELINE_007 PARTNER_UI_MY_PIPELINE_008 PARTNER_UI_MY_PIPELINE_009 PARTNER_UI_MY_PIPELINE_010 PARTNER_UI_MY_PIPELINE_011 PARTNER_UI_MY_PIPELINE_012 PARTNER_UI_MY_PIPELINE_013 PARTNER_UI_MY_PIPELINE_019 PARTNER_UI_MY_PIPELINE_020 PARTNER_UI_MY_PIPELINE_021 PARTNER_UI_PARTNER_PORTAL_SHELL_002 PARTNER_UI_SECURITY_COMPLIANCE_003
4.5 | My Pipeline — Deal List and Detail | Kanban-like list with status filter tabs (All/Registered/Approved/In Progress/Closing/Won/Lost), search, deal type + module filters. Deal status icons (🔒 protected, ✅ approved, ⏳ pending). Deal Detail: timeline, shared notes, commission projection, documents, BlazeUp rep contact. | High | Confirmed |  | Not Started | Pipeline list, filter tabs, deal detail view per §4.5 wireframe | Done | GET /v1/partner/deals, PATCH /v1/partner/deals/:id (notes/docs) |  | Part of 4-week portal sprint |  | PARTNER_API_DEAL_COLLABORATION_001 PARTNER_API_DEAL_COLLABORATION_002 PARTNER_API_PIPELINE_MANAGEMENT_001 PARTNER_API_PIPELINE_MANAGEMENT_002 PARTNER_UI_MY_PIPELINE_014 PARTNER_UI_MY_PIPELINE_015 PARTNER_UI_MY_PIPELINE_023 PARTNER_UI_MY_PIPELINE_024 PARTNER_UI_MY_PIPELINE_025 PARTNER_UI_MY_PIPELINE_026 PARTNER_UI_MY_PIPELINE_027 PARTNER_UI_MY_PIPELINE_028 PARTNER_UI_MY_PIPELINE_029
4.6 | My Clients — Client Health Dashboard | Book of business (post-close only). Health status (Healthy/At Risk/Inactive), renewal date, modules active. Client Health Card: MAU/DAU stats, module adoption %, support tickets (count+severity, content gated on consent), Blazey Insights panel, renewal pipeline, commission history. | High | Confirmed |  | Not Started | Clients list + health card per §4.6 wireframe | Not Started | GET /v1/partner/clients + GET /v1/partner/clients/:id/health + /tickets |  | Part of 4-week portal sprint | THE product moat | PARTNER_API_CLIENT_HEALTH_MSP_001 PARTNER_API_CLIENT_HEALTH_MSP_002 PARTNER_UI_MY_CLIENTS_001 PARTNER_UI_MY_CLIENTS_002 PARTNER_UI_MY_CLIENTS_003 PARTNER_UI_MY_CLIENTS_004 PARTNER_UI_MY_CLIENTS_007 PARTNER_UI_MY_CLIENTS_008 PARTNER_UI_MY_CLIENTS_009 PARTNER_UI_MY_CLIENTS_010
4.7 | Commissions & Payouts — Full Transparency | Earned YTD / Pending / Paid summary. Per-deal commission table with status. Dispute flow (one text field → submit). Product-failure clawback waiver request flow. Payout details: SWIFT/ACH/NEFT/IMPS/Vietnamese bank. CSFLE-encrypted banking details. | High | Confirmed |  | Not Started | Commissions page per §4.7 wireframe, dispute and waiver request UI | In Progress | partner_commissions collection; POST /v1/partner/commissions/:id/dispute + /waiver |  | Part of 3-week portal sprint |  | PARTNER_API_COMMISSIONS_PAYOUTS_002 PARTNER_API_COMMISSIONS_PAYOUTS_003 PARTNER_API_COMMISSIONS_PAYOUTS_004 PARTNER_API_COMMISSIONS_PAYOUTS_012 PARTNER_API_COMMISSIONS_PAYOUTS_016 PARTNER_UI_COMMISSIONS_002 PARTNER_UI_COMMISSIONS_003 PARTNER_UI_COMMISSIONS_004 PARTNER_UI_COMMISSIONS_005 PARTNER_UI_COMMISSIONS_007 PARTNER_UI_COMMISSIONS_009
4.8 | Training & Certification Module | Progress tracking for 4 certifications. Learning path UI with continue button. Completion triggers blazeup.partner.certification.earned → tier re-evaluation. | Medium | Confirmed | OQ-8 training platform build vs buy — Aashwij still owed | Not Started | Training UI per §4.8 | In Progress | partner_certifications collection; certification.earned Kafka event | OQ-8 unresolved | Part of 3-week sprint |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010 PARTNER_UI_TRAINING_001 PARTNER_UI_TRAINING_002 PARTNER_UI_TRAINING_003
4.9 | Resources: Co-branded Materials + Sandbox | Co-branded pitch decks, product PDFs, battle cards (vs Workday/Darwinbox/Zoho/Salesforce), ROI calculator, pricing sheets, demo sandbox tenant ({slug}-demo.blazeup.ai), API docs for CRM integration. | Medium | Planned | Sandbox data spec resolved (B5) | Not Started | Resources page, sandbox reset button | Not Started | Sandbox provisioning via blazeup-microservice-sandbox-data; reset via Kafka event | B5 resolved | Part of 3-week sprint |  | PARTNER_API_RESOURCES_SANDBOX_001 PARTNER_API_RESOURCES_SANDBOX_002 PARTNER_API_RESOURCES_SANDBOX_003 PARTNER_UI_RESOURCES_001 PARTNER_UI_RESOURCES_002 PARTNER_UI_RESOURCES_003 PARTNER_UI_RESOURCES_004 PARTNER_UI_RESOURCES_005
4.9a | Sandbox Demo Tenant + Reset Flow | 3 profiles: SMB (50 emp), Mid-market (200 emp), Enterprise (500 emp). Collections: employees, departments, leave_requests, expense_reports, crm_contacts, crm_deals, assets, tickets. On-demand reset (5 min SLA). Optional weekly auto-reset (default OFF). blazeup.partner.sandbox.reset_requested Kafka event. | Medium | Planned | Locked — Renil 2026-05-15 (B5) | Not Started | Profile selector + Reset Demo button in portal | Not Started | blazeup-microservice-sandbox-data; reset event consumer | B5 resolved | — | Locked decision B5 | PARTNER_API_RESOURCES_SANDBOX_001 PARTNER_API_RESOURCES_SANDBOX_002 PARTNER_API_RESOURCES_SANDBOX_003 PARTNER_UI_RESOURCES_001 PARTNER_UI_RESOURCES_002 PARTNER_UI_RESOURCES_003 PARTNER_UI_RESOURCES_004 PARTNER_UI_RESOURCES_005
4.10 | Partner Team Management + Referral Links | Team member list (Admin/Member roles), certifications per member, invite new member. Referral links: default link, per-user links, per-campaign links. Analytics per link: clicks, conversions, ARR attributed. | Medium | Confirmed |  | Not Started | Team page, referral links management per §4.10 | In Progress | partner_referral_links collection; GET/POST /v1/partner/referral-links |  | Part of 3-week sprint |  | PARTNER_API_TEAM_REFERRAL_LINKS_001 PARTNER_API_TEAM_REFERRAL_LINKS_002 PARTNER_UI_PARTNER_TEAM_001 PARTNER_UI_PARTNER_TEAM_002 PARTNER_UI_PARTNER_TEAM_003
§5 — SA Partner Module (blazeup-subapp-sa-partners)
5.1 | SA Partner Directory | List all partners with tier/ARR/open deals/client counts/status. Filter by region/tier/type/status. Partner Profile drill-in: company info, team certs, deal history, commission ledger, territory, performance vs tier thresholds, internal notes, activity log. | Critical | Confirmed |  | N/A |  | Done | GET /internal/partners, partner_accounts collection |  | Part of 3.5-week SA sprint |  | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004 PARTNER_UI_SA_PARTNER_MODULE_003 PARTNER_UI_SA_PARTNER_MODULE_004 PARTNER_UI_SA_PARTNER_MODULE_005 PARTNER_UI_SA_PARTNER_MODULE_006
5.1a | Partner Application Review — 3-Stage FSM | Stage 1: SA Review (requires signed partner agreement attached). Stage 2: Legal Countersign (SA cannot advance until Legal records countersign). Stage 3: SA Final Approval → blazeup.partner.approved emitted. SA can Decline at any stage (mandatory reason logged). UI must surface all 3 stages as visible FSM. | Critical | Confirmed | Locked — Aashwij 2026-05-15 (B3) | N/A |  | In Progress | 3-stage workflow FSM on partner_accounts.status; countersign record | B3 resolved | Part of 3.5-week SA sprint | Locked decision B3 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004 PARTNER_UI_SA_PARTNER_MODULE_003 PARTNER_UI_SA_PARTNER_MODULE_004 PARTNER_UI_SA_PARTNER_MODULE_005 PARTNER_UI_SA_PARTNER_MODULE_006
5.2 | SA Deal Approval Queue | Pending Approval and Conflict Queue tabs. Per-deal card: conflict check result, enrichment data, rep assignment dropdown. Approve+Assign stamps commissionRate+rateTableVersion on partner_deals. Deal protection clock starts. Co-sell override proposal (above $100K ACV). Rep gets CRM task. Partner notified. | Critical | Confirmed |  | N/A |  | Done | PATCH /internal/deals/:id/approve (with cosellSplit proposal); Kafka events |  | Part of 3.5-week SA sprint |  | PARTNER_API_DEAL_APPROVAL_QUEUE_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_004 PARTNER_API_DEAL_REGISTRATION_PIPELINE_005 PARTNER_API_DEAL_REGISTRATION_PIPELINE_006 PARTNER_API_DEAL_REGISTRATION_PIPELINE_007 PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 PARTNER_API_DEAL_REGISTRATION_PIPELINE_009 PARTNER_API_DEAL_REGISTRATION_PIPELINE_012 PARTNER_API_DEAL_REGISTRATION_PIPELINE_013 PARTNER_API_DEAL_REGISTRATION_PIPELINE_014 PARTNER_API_DEAL_REGISTRATION_PIPELINE_016 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010 PARTNER_UI_MY_PIPELINE_005 PARTNER_UI_MY_PIPELINE_016 PARTNER_UI_MY_PIPELINE_017 PARTNER_UI_MY_PIPELINE_018 PARTNER_UI_MY_PIPELINE_030 PARTNER_UI_SA_PARTNER_MODULE_001 PARTNER_UI_SA_PARTNER_MODULE_002 PARTNER_UI_SA_PARTNER_MODULE_007 PARTNER_UI_SA_PARTNER_MODULE_008
5.2a | Deal Protection: Auto-Extend Rule | On expiry: if ≥1 stage update in last 30 days AND never auto-extended → auto-extend once to 2× original window. Else: hard expiry → partner requests manual SA extension. protectionExtensionCount (max 1) + lastStageUpdateAt on partner_deals. | High | Confirmed | Locked — Renil 2026-05-08 (OQ-20) | N/A |  | Done | Cron job + activity check; partner_deals.protectionExtensionCount + lastStageUpdateAt; blazeup.partner.deal.protection_extended event |  | 1 week (Renil surface) | Locked decision | PARTNER_API_DEAL_APPROVAL_QUEUE_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_004 PARTNER_API_DEAL_REGISTRATION_PIPELINE_005 PARTNER_API_DEAL_REGISTRATION_PIPELINE_006 PARTNER_API_DEAL_REGISTRATION_PIPELINE_007 PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 PARTNER_API_DEAL_REGISTRATION_PIPELINE_009 PARTNER_API_DEAL_REGISTRATION_PIPELINE_012 PARTNER_API_DEAL_REGISTRATION_PIPELINE_013 PARTNER_API_DEAL_REGISTRATION_PIPELINE_014 PARTNER_API_DEAL_REGISTRATION_PIPELINE_016 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010 PARTNER_UI_MY_PIPELINE_005 PARTNER_UI_MY_PIPELINE_016 PARTNER_UI_MY_PIPELINE_017 PARTNER_UI_MY_PIPELINE_018 PARTNER_UI_MY_PIPELINE_030 PARTNER_UI_SA_PARTNER_MODULE_001 PARTNER_UI_SA_PARTNER_MODULE_002 PARTNER_UI_SA_PARTNER_MODULE_007 PARTNER_UI_SA_PARTNER_MODULE_008
5.2b | Conflict Queue + Resolution UI | SA sees both parties, prospect contacted status, decision (Award A / Award B / Split N/A for direct). Reasoning field required. Both parties notified with reasoning. Logged to audit trail. Immutable. | High | Planned | OQ-17 90-day re-registration mechanism TBD | N/A |  | Done | partner_conflicts collection; PATCH /internal/deals/conflicts/:id/resolve | OQ-17 TBD | Part of 3.5-week SA sprint |  | PARTNER_API_DEAL_APPROVAL_QUEUE_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_004 PARTNER_API_DEAL_REGISTRATION_PIPELINE_005 PARTNER_API_DEAL_REGISTRATION_PIPELINE_006 PARTNER_API_DEAL_REGISTRATION_PIPELINE_007 PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 PARTNER_API_DEAL_REGISTRATION_PIPELINE_009 PARTNER_API_DEAL_REGISTRATION_PIPELINE_012 PARTNER_API_DEAL_REGISTRATION_PIPELINE_013 PARTNER_API_DEAL_REGISTRATION_PIPELINE_014 PARTNER_API_DEAL_REGISTRATION_PIPELINE_016 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010 PARTNER_UI_MY_PIPELINE_005 PARTNER_UI_MY_PIPELINE_016 PARTNER_UI_MY_PIPELINE_017 PARTNER_UI_MY_PIPELINE_018 PARTNER_UI_MY_PIPELINE_030 PARTNER_UI_SA_PARTNER_MODULE_001 PARTNER_UI_SA_PARTNER_MODULE_002 PARTNER_UI_SA_PARTNER_MODULE_007 PARTNER_UI_SA_PARTNER_MODULE_008
5.3 | Commission Rate Table + SPIFF Programmes | SA-managed rate table (no code change to adjust rates). Versioned. Referral, Reseller margin, Co-sell rates per tier. SPIFF programmes with region/tier/date filters. 3-stage lifecycle model: NN/EN/EE rate bands per tier × deal-type. Clawback config: 12-month window, 50% of paid, waiver path. | Critical | Confirmed |  | N/A |  | Done | partner_rate_table collection (NN/EN/EE bands); PUT /internal/commission/rates (versioned); POST /internal/commission/spiff |  | Part of commission engine (4 weeks) | B6 architecture resolved | PARTNER_API_COMMISSIONS_PAYOUTS_001 PARTNER_API_COMMISSIONS_PAYOUTS_004 PARTNER_API_COMMISSIONS_PAYOUTS_005 PARTNER_API_COMMISSIONS_PAYOUTS_006 PARTNER_API_COMMISSIONS_PAYOUTS_010 PARTNER_API_COMMISSIONS_PAYOUTS_011 PARTNER_API_COMMISSIONS_PAYOUTS_012 PARTNER_API_COMMISSIONS_PAYOUTS_013 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006 PARTNER_UI_COMMISSIONS_005 PARTNER_UI_COMMISSIONS_007 PARTNER_UI_SA_PARTNER_MODULE_009 PARTNER_UI_SA_PARTNER_MODULE_010
5.4 | Territory Management | Assign regions + verticals per partner. Exclusivity types: Exclusive (single partner), Preferred (first-registered wins), None (open market). Territory rules enforced on conflict resolution. | Medium | Confirmed |  | N/A |  | Done | partner_territories collection |  | Part of 3.5-week SA sprint |  | PARTNER_UI_SA_PARTNER_MODULE_012
5.5 | SA Analytics Dashboard | Partner-Sourced ARR, Deals Registered MTD, Approval Rate, Win Rate, Avg Deal Size vs direct, Avg Deal Velocity. Commission paid/pending/clawbacks/waiver grants. Top 5 partners by ARR. Tier distribution. | Medium | Confirmed |  | N/A |  | Not Started | Analytics aggregation queries on partner_deals + partner_commissions |  | 2 weeks |  | PARTNER_UI_DASHBOARD_006 PARTNER_UI_SA_PARTNER_MODULE_011
5.6 | SA Commission Ledger + Approval Workflow | All calculated commissions require SA approval before payout. Two-eye principle for amounts >$10K. Approve / Dispute / Request clarification per commission row. Clawback waiver review queue (30-day SLA). | High | Confirmed |  | N/A |  | Done | partner_commissions collection; POST /internal/partners/:id/commissions/:cid/approve + /waiver-decision |  | 2 weeks |  | PARTNER_API_COMMISSIONS_PAYOUTS_007 PARTNER_UI_COMMISSIONS_003 PARTNER_UI_COMMISSIONS_006
§6 — CRM Integration Architecture
6.1 | Event-Driven CRM Sync: partner events → dogfood CRM | All partner Kafka events auto-create/update opportunities in dogfood CRM. deal.registered → create opp (stage: Partner Deal Pending Approval). deal.approved → update opp + assign rep + create task. deal.won → close won + stamp ARR + tenant_id. deal.lost → close lost. | Critical | Planned |  | N/A |  | In Progress | DogfoodCrmBridge consumer service; publishes to ms-crm internal APIs |  | 3 days (CRM bridge) | §6.2 full event map | PARTNER_API_CRM_INTEGRATION_001
6.2 | Opportunity Record Schema: attribution block | Opportunity carries full attribution: partnerId, partnerName, partnerTier (locked at close), dealType, commissionRate (locked at approval), rateTableVersion, commissionAmount, cosellSplit (if co-sell). | High | Planned |  | N/A |  | In Progress | CRM opportunity schema per §6.3 TypeScript definition |  | Part of CRM bridge (3 days) | commissionRate locked at APPROVAL not registration | PARTNER_API_CRM_INTEGRATION_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 PARTNER_API_DEAL_REGISTRATION_PIPELINE_010 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_007 PARTNER_UI_SA_PARTNER_MODULE_008
§7 — Tenant Provisioning on Deal Close
7.1 | Referral Close → Provision Flow | Partner marks Won OR BlazeUp rep closes in CRM → Kafka blazeup.partner.deal.won → ms-sa-partners calculates commission + calls SA /internal/tenants/provision with attribution block → blazeup.tenant.provisioned → CRM closed + CSM project created + partner portal updated + commission queued. | Critical | Confirmed |  | N/A |  | In Progress | Provision chain per §7.1 flow diagram |  | Core (4 weeks) |  | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_007
7.2 | Reseller Close: billing.model='reseller' | Same as referral flow but billing.model='reseller'. BlazeUp invoices partner at discount. Partner manages client billing independently. BlazeUp never captures partner's sell price. | High | Confirmed |  | N/A |  | In Progress | billing.model on tenant record; invoice addressed to partner |  | Core |  | PARTNER_API_COMMISSIONS_PAYOUTS_011 PARTNER_API_DEAL_REGISTRATION_PIPELINE_002 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_006 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_003
7.3 | MSP Provisioning Flow | MSP uses + Add Managed Client. Fills client details + MSP ticket-content consent toggle (default OFF). ms-sa-partners calls provision API with billingModel='partner_managed' + mspTicketContentConsent block. MSP gets scoped admin token. | High | Planned |  | Not Started | + Add Managed Client button + provisioning form | In Progress | Provision API with partner_managed billing; mspTicketContentConsent on tenant |  | Core |  | PARTNER_API_CLIENT_HEALTH_MSP_006 PARTNER_UI_MY_CLIENTS_005 PARTNER_UI_MY_CLIENTS_006
7.4 | Expansion Close: Existing Tenant | No new tenant. Additional modules/seats provisioned on existing tenant. Subscription line items updated in ms-billing. Expansion commission on delta ARR using NN/EN/EE classification. | High | Confirmed |  | Not Started | Expansion deal flow in portal | In Progress | Expansion provision path; NN/EN/EE classification logic | B6 architecture resolved | Core |  | PARTNER_API_COMMISSIONS_PAYOUTS_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_004 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006
7.5 | Tenant Attribution Block (Permanent) | Every partner-sourced tenant carries permanent attribution: source, partnerId, partnerName, partnerTier (at close), dealId, commissionStructure{rate, rateTableVersion, clawbackExpiresAt, productFailureWaiver?}, billingModel, attributionHistory[] (SA overrides, two-eye approval, immutable history). | Critical | Confirmed | Locked — Renil 2026-05-15 (B4, B6) | N/A |  | In Progress | tenant.attribution schema per §7.5 TypeScript definition. attributionHistory[] for SA overrides. | B4 resolved | Core | attributionHistory[] never deleted — only superseded | PARTNER_API_CLIENT_HEALTH_MSP_007 PARTNER_API_COMMISSIONS_PAYOUTS_007 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_008 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_009 PARTNER_UI_COMMISSIONS_006
§8 — Technical Architecture
8.1 | New Services/Repos: 5 Artifacts | blazeup-microservice-sa-partners (BE), blazeup-hostapp-partner (FE host), blazeup-subapp-sa-partners (SA subapp), blazeup-subapp-partner-dashboard (partner subapp), blazeup-subapp-partner-training (partner subapp). | Critical | Confirmed |  | Not Started | 3 FE repos to be created | Done | 1 BE microservice to be created |  | — |  | —
8.2 | MongoDB Collections: 8 Collections | partner_accounts, partner_deals, partner_commissions, partner_territories, partner_certifications, partner_referral_links, partner_rate_table (NN/EN/EE bands), partner_conflicts. | Critical | Confirmed |  | N/A |  | Done | All schemas in §8.2 |  | Core (4 weeks) |  | PARTNER_API_COMMISSIONS_PAYOUTS_001 PARTNER_API_COMMISSIONS_PAYOUTS_006 PARTNER_API_COMMISSIONS_PAYOUTS_010 PARTNER_API_DEAL_REGISTRATION_PIPELINE_005 PARTNER_API_DEAL_REGISTRATION_PIPELINE_007 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_005 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_006 PARTNER_UI_SA_PARTNER_MODULE_009
8.3 | Kafka Events: ~20 Events | Full list: registered, approved, tier.changed, deal.registered/approved/rejected/conflict_raised/protection_extended/won/lost/expired, commission.earned/paid/waiver_decided, client.health_alert/transferred, msp_ticket_consent.changed, sandbox.reset_requested. | Critical | Confirmed |  | N/A |  | Done | All events + standard BlazeUp envelope (eventId, schemaVersion, etc.) |  | Core |  | PARTNER_API_CLIENT_HEALTH_MSP_005 PARTNER_API_CLIENT_HEALTH_MSP_007 PARTNER_API_CLIENT_HEALTH_MSP_009 PARTNER_API_COMMISSIONS_PAYOUTS_005 PARTNER_API_COMMISSIONS_PAYOUTS_009 PARTNER_API_DEAL_REGISTRATION_PIPELINE_005 PARTNER_API_DEAL_REGISTRATION_PIPELINE_006 PARTNER_API_EVENT_ARCHITECTURE_001 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_005 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_007 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_010 PARTNER_API_RESOURCES_SANDBOX_001 PARTNER_API_RESOURCES_SANDBOX_003 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 PARTNER_UI_RESOURCES_001 PARTNER_UI_RESOURCES_002 PARTNER_UI_TRAINING_002
8.4 | Referral Attribution Service | blazeup.ai/ref/{slug} → server writes Redis attr:{sessionToken} TTL 30 days + sets first-party cookie __blazeup_ref. On signup: resolve attribution from Redis, stamp tenant.attribution, fire commission. First-touch wins. Edge cases: multiple clicks (first-touch), no cookie (no attribution), >30 days (expired). | High | Rejected / On Hold |  | N/A |  | Not Started | Redis key partners:attr:{sessionToken} TTL 30 days; attribution resolution in /v1/tenants/provision |  | 1 week | R4 mitigation | PARTNER_API_COMMISSIONS_PAYOUTS_008 PARTNER_API_COMMISSIONS_PAYOUTS_009 PARTNER_API_REFERRAL_ATTRIBUTION_001 PARTNER_API_REFERRAL_ATTRIBUTION_002 PARTNER_API_REFERRAL_ATTRIBUTION_003 PARTNER_API_REFERRAL_ATTRIBUTION_004 PARTNER_API_TEAM_REFERRAL_LINKS_002 PARTNER_UI_PARTNER_TEAM_002
8.5 | REST API: ~25 Endpoints | SA-only internal endpoints (partner CRUD, deal approval/reject/extend, conflict resolve, commission approve/waiver, rate table). Partner-JWT-gated endpoints (dashboard, deals, clients/health/tickets, commissions/dispute/waiver, referral links). See §8.5 for full list. | Critical | Confirmed |  | N/A |  | In Progress | All routes per §8.5 |  | Core + 1 week Renil surface |  | PARTNER_API_CLIENT_HEALTH_MSP_001 PARTNER_API_CLIENT_HEALTH_MSP_002 PARTNER_API_COMMISSIONS_PAYOUTS_002 PARTNER_API_COMMISSIONS_PAYOUTS_003 PARTNER_API_COMMISSIONS_PAYOUTS_004 PARTNER_API_COMMISSIONS_PAYOUTS_005 PARTNER_API_COMMISSIONS_PAYOUTS_013 PARTNER_API_DASHBOARD_DATA_001 PARTNER_API_DEAL_APPROVAL_QUEUE_001 PARTNER_API_DEAL_COLLABORATION_001 PARTNER_API_DEAL_COLLABORATION_002 PARTNER_API_DEAL_REGISTRATION_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_001 PARTNER_API_DEAL_REGISTRATION_PIPELINE_002 PARTNER_API_DEAL_REGISTRATION_PIPELINE_003 PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 PARTNER_API_DEAL_REGISTRATION_PIPELINE_015 PARTNER_API_DEAL_REGISTRATION_PIPELINE_016 PARTNER_API_DEAL_REGISTRATION_PIPELINE_017 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_001 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002 PARTNER_API_PIPELINE_MANAGEMENT_001 PARTNER_API_PIPELINE_MANAGEMENT_002 PARTNER_API_TEAM_REFERRAL_LINKS_001 PARTNER_API_TEAM_REFERRAL_LINKS_002 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_001 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_010 PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_011 PARTNER_UI_MY_PIPELINE_016 PARTNER_UI_MY_PIPELINE_019 PARTNER_UI_MY_PIPELINE_030
8.6 | Redis Caching Keys | partners:account:{id} (1h), partners:rate_table:current (24h), partners:rate:{tenantId}:{tier} (1h), partners:deal:{dealId}:protection (TTL=protectionExpiresAt), partners:attr:{sessionToken} (30d), partners:conflict:{domain} (7d). | Medium | Confirmed |  | N/A |  | Not Started | 6 Redis key patterns per §8.6 |  | Core |  | PARTNER_API_COMMISSIONS_PAYOUTS_006 PARTNER_API_COMMISSIONS_PAYOUTS_008 PARTNER_API_COMMISSIONS_PAYOUTS_014 PARTNER_API_REFERRAL_ATTRIBUTION_001
§9 — Security & Compliance
9.1 | Partner Portal Auth: Separate JWT Issuer | Distinct JWT issuer from tenant and SA. 8h access token, 30-day refresh. MFA: required for PARTNER_ORG_ADMIN. Tier-based (Advanced+) per this PRD but OQ-14 conflicts with sa-portal-architecture-v2.6.md §14.8 (role-based). Session scoped to partnerId. | Critical | Awaiting Confirmation | OQ-14 MFA policy conflict unresolved (Renil owed) | N/A |  | In Progress | Separate JWT issuer; partner-iam module | B1 Auth Phase 0 | Part of auth sprint (B1) | OQ-14 must resolve before MFA enforcement logic finalised | PARTNER_API_AUTH_ACCESS_CONTROL_001 PARTNER_API_AUTH_ACCESS_CONTROL_002 PARTNER_API_AUTH_ACCESS_CONTROL_003 PARTNER_API_AUTH_ACCESS_CONTROL_004 PARTNER_API_PIPELINE_MANAGEMENT_001 PARTNER_UI_SECURITY_COMPLIANCE_001
9.2 | MSP Access Scope + PartnerScopeGuard | PartnerScopeGuard in EVERY MS. MSP can: configure modules, manage users, see ticket count+severity. MSP CANNOT: see ticket content (until client opt-in), access payroll/salary/health data, export data, impersonate users. Consent stored on tenant record. Revocation immediate. | Critical | Planned | Locked — Renil 2026-05-08 (OQ-22) | N/A |  | Not Started | PartnerScopeGuard middleware; mspTicketContentConsent check on every ticket body request; sentinel response when restricted |  | Core | Locked decision | PARTNER_API_AUTH_ACCESS_CONTROL_005 PARTNER_API_AUTH_ACCESS_CONTROL_006 PARTNER_API_CLIENT_HEALTH_MSP_003 PARTNER_API_CLIENT_HEALTH_MSP_004 PARTNER_API_CLIENT_HEALTH_MSP_005 PARTNER_API_CLIENT_HEALTH_MSP_009 PARTNER_UI_MY_CLIENTS_006
9.3 | Data Residency: PDPL/PDPA Compliant | Partner prospect data stored in SA region (us-west1 today). UAE/Saudi: Middle East region when available. Prospect contact data (domain, name, email only) never transferred cross-region without consent. | High | Planned |  | N/A |  | Not Started | Region-aware storage for partner_deals; prospect data minimised |  | — |  | PARTNER_API_COMMISSIONS_PAYOUTS_016 PARTNER_API_SECURITY_COMPLIANCE_002 PARTNER_API_SECURITY_COMPLIANCE_003 PARTNER_UI_SECURITY_COMPLIANCE_003
9.4 | Audit Trail: All SA Actions Immutable | sa_audit_log collection (Tier J). Covers: deal approval/rejection, protection extension (auto+manual), conflict resolution, co-sell split override, commission approval/dispute, waiver decision, MSP consent grant/revoke, territory changes, rate table modifications (versioned — every version preserved). | High | Confirmed |  | N/A |  | Done | Append-only audit log writes on all SA actions |  | Core |  | PARTNER_API_CLIENT_HEALTH_MSP_009 PARTNER_API_COMMISSIONS_PAYOUTS_012 PARTNER_API_DEAL_REGISTRATION_PIPELINE_009 PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_004 PARTNER_API_SECURITY_COMPLIANCE_001 PARTNER_UI_MY_PIPELINE_015 PARTNER_UI_SA_PARTNER_MODULE_001 PARTNER_UI_SA_PARTNER_MODULE_002 PARTNER_UI_SA_PARTNER_MODULE_006 PARTNER_UI_SECURITY_COMPLIANCE_002 PARTNER_UI_SECURITY_COMPLIANCE_004
§10 — Effort Estimates
10.1 | ms-sa-partners Core | Collections, deal FSM, APIs, Kafka events, commission engine | Critical | Confirmed |  | N/A |  | Done | ~4 weeks |  | 4 weeks | Critical path | —
10.2 | ms-sa-partners Dogfood CRM Bridge | DogfoodCrmBridge consumer, opportunity create/update flows | Critical | Planned |  | N/A |  | In Progress | ~3 days |  | 3 days |  | —
10.3 | ms-sa-partners Referral Attribution | Link tracking, Redis attribution, self-signup path | High | Rejected / On Hold | PO confirmed: we wont have the self-signup path | N/A |  | Not Started | ~1 week |  | 1 week |  | —
10.4 | ms-sa-partners Renil-Locked Surface | Auto-extend cron+activity gate, co-sell split override, product-failure waiver, MSP ticket-consent guard, managerAllocation field | High | Confirmed | Locked — Renil 2026-05-08 | N/A |  | In Progress | ~1 week |  | 1 week | Added due to Renil lock-ins | —
10.5 | blazeup-hostapp-partner | Portal shell, auth, nav, federation scaffold | Critical | Confirmed |  | Not Started | ~1 week | N/A |  | B1 Auth | 1 week |  | —
10.6 | Partner Portal Subapps (Batch 1) | Dashboard · Deal Registration · Pipeline · Client Health (with ticket-content gating) | Critical | Confirmed |  | Not Started | ~4 weeks | N/A |  |  | 4 weeks |  | —
10.7 | Partner Portal Subapps (Batch 2) | Commissions (incl. waiver request UI) · Training · Resources · Team · Settings | High | Confirmed |  | Not Started | ~3 weeks | N/A |  |  | 3 weeks |  | —
10.8 | blazeup-subapp-sa-partners | Partner directory · Deal approval (cosell-override + extension UI) · Conflict queue · Territories · Waiver review queue | Critical | Confirmed |  | Not Started | ~3.5 weeks | N/A |  |  | 3.5 weeks |  | —
10.9 | SA Analytics + Commission Ledger | Analytics dashboard · Commission approval workflow · Waiver-tracking metric | High | Confirmed |  | Not Started | ~2 weeks | N/A |  |  | 2 weeks |  | —
10.10 | Blazey Partner Assistant | 4 tools: commission query, deal status, tier projection, client health. + skill file. | Medium | Planned |  | Not Started | ~1 week | N/A |  |  | 1 week |  | —
§12 — Open Questions Impact on Features
OQ-8 | Training Platform: Build vs Buy | Build on dogfood LMS OR buy (Docebo / Thought Industries) for v1. Aashwij still owed. Affects §4.8 scope and time-to-launch. | Medium | Planned | Aashwij owed | Not Started | Training module scope depends on this | Not Started | If buy: integration only; if build: full LMS in blazeup-subapp-partner-training | OQ-8 Aashwij | — | Non-blocking but should land before training sprint | —
OQ-14 | MFA Enforcement Policy | sa-portal-architecture-v2.6.md §14.8: role-based (PARTNER_ORG_ADMIN). This PRD §9.1: tier-based (Advanced+). Which is authoritative? Or both? Renil owed. | High | Rejected / On Hold | Renil owed | N/A |  | Not Started | partner-iam MFA enforcement logic cannot be finalised until resolved | OQ-14 Renil | — | Non-blocking but must land before partner-iam sprint | PARTNER_API_AUTH_ACCESS_CONTROL_004
OQ-15 | Grace Quarter Definition for Tier Downgrade | Full next quarter after announcement OR remainder of current quarter? Aashwij owed. Affects tier FSM timing. | Low | Rejected / On Hold | Aashwij owed | N/A |  | Not Started | Tier FSM downgrade timing | OQ-15 Aashwij | — |  | —
OQ-17 | Conflict-Loser 90-Day Re-registration | Auto-unlock + notification when 90 days elapsed, OR manual partner re-submit with no system support? Aashwij owed. | Medium | Rejected / On Hold | Aashwij owed | Not Started | Re-registration notification UI | Not Started | partner_conflicts auto-expiry + deal FSM | OQ-17 Aashwij | — |  | —
OQ-18 | Rate-Table Change Retroactivity | Confirm rates lock at deal APPROVAL (not registration, not invoice). PRD §6.3 and §5.2 both assert locked at approval; OQ-5 v0.4 corrected this. Treat as confirmed pending Renil sign-off. | High | Planned | Renil sign-off pending | N/A |  | Not Started | Commission engine version-pin behaviour: rateTableVersion stamped at approval | OQ-18 Renil | — |  | PARTNER_UI_SECURITY_COMPLIANCE_004

## ⚠️ Risk Register
BlazeUp Partner Platform — Risk Register (PRD §Risk Flags)
Risk ID | Severity | Risk Description | Impact | Mitigation | Status | Owner | Notes
R1 | CRITICAL | Deal Conflict — two partners (or partner + direct inbound) register the same prospect | Commission disputes, partner trust destroyed, channel conflict | First-registered-wins rule + SA conflict queue + 5-business-day SLA for resolution | Pending |  | OQ-17: 90-day re-registration mechanism TBD
R2 | HIGH | Commission Opacity — partners don't trust what they'll earn until after deal closes | Low deal registration adoption | Show projected commission at registration time, before submission, updated live as ACV is typed | Pending |  | Live commission projection in §4.4 Step 3
R3 | HIGH | MSP Billing Ambiguity — partner-managed tenants billed to partner vs end client | Revenue leakage + tax/VAT complications across Vietnam/UAE/India | Explicit billing.model: 'direct'¦'reseller'¦'partner_managed' on every partner-sourced tenant; set at deal registration, immutable after provisioning | Pending
R4 | HIGH | Referral Attribution Loss — prospect clicks link, signs up days later in different browser | Partner loses commission on a valid referral | First-touch partner_id captured server-side on link click; stored with 30-day TTL; survives browser sessions | Pending |  | §8.4 Redis attribution service
R5 | MEDIUM | Pack Partner vs Channel Partner Conflation | Wrong commission structure applied; incorrect portal access | Two distinct account types; a partner can hold both; managed independently in SA | Pending |  | §3 Scenario H — dual account type
R6 | MEDIUM | Clawback Rules Unclear at Deal Close | Partner disputes clawback when client churns at month 10 | Clawback policy + product-failure waiver path must be in partner agreement AND displayed at commission approval time | Pending |  | §5.3 clawback config — Locked Renil 2026-05-08
R7 | MEDIUM | PDPA/PDPL Compliance for Partner-Held Prospect Data | Partners in Vietnam/UAE uploading prospect data to deal registration | Partner agreement + DPA required per region; prospect data minimised at registration — domain + name + email only | Pending | Legal/Compliance | §9.3; OQ-17 (v0.4) GDPR erasure spec pending Legal
R8 | LOW | Tier Downgrade Psychology — partner drops from Advanced to Select | Partner disengagement | Downgrade is quarterly, announced 30 days in advance; give partner a grace quarter to recover | Pending |  | OQ-15 grace quarter definition TBD

## ❓ Open Questions
BlazeUp Partner Platform — Open Questions & Blockers (PRD §12)
ID | Category | Question / Decision | Owner | Blocks / Impact | Status | Decision (if resolved) | Target Date
B1 | BLOCKING | Auth Hardening Phase 0 — PRs #633–#641 must merge before any partner JWT class, OAuth 2.0 server, or partner-issued tokens go live. | Auth team | Partner auth surfaces only (all non-auth coding proceeds in parallel) | In Progress | Engineer working directly with Auth team. Non-auth coding proceeds now. Auth surfaces gated on PR merge. | ~Week 1-2
B2 | BLOCKING | First-admin enrollment flow on partner approval. | Auth team | partner-iam implementation | Resolved | Follow tenant creation model (§tenant-creation-module-spec-v1.1.md §4.6+§6.6). PENDING_ACTIVATION user → activation email → self-set password. Token TTL deferred to Auth team standard. | Resolved 2026-05-15
B3 | BLOCKING | Partner-org approval workflow stages — single SA step or staged workflow? | Aashwij + SA subapp team | SA partner application review UI (§5.1) | Resolved | 3-stage FSM: (1) SA Review (signed agreement required), (2) Legal Countersign, (3) SA Final Approval. SA can Decline at any stage with mandatory reason. | Resolved 2026-05-15
B4 | BLOCKING | Partner-managed tenant linking edge cases: no registration, pre-programme tenants, MSP handoff, SA attribution override. | — | tenant.attribution schema (§7.5) | Resolved | (a) No registration = no commission. (b) Prospective attribution for pre-programme tenants — future only, written justification. (c) MSP handoff: SA-only, both parties agree, blazeup.partner.client.transferred. (d) SA override: two-eye approval + attributionHistory[]. | Resolved 2026-05-15
B5 | BLOCKING | blazeup-microservice-sandbox-data spec — profiles, collections, reset policy. | Khoa (implementation) | Partner sandbox provisioning §4.9 | Resolved | 3 profiles: SMB/Mid-market/Enterprise. Collections: employees, departments, leave_requests, expense_reports, crm_contacts, crm_deals, assets, tickets. On-demand reset (5 min). Optional weekly auto-reset (default OFF). blazeup.partner.sandbox.reset_requested event. | Resolved 2026-05-15
B6 | BLOCKING | Expansion deal commission rate — how is expansion ARR commissioned? | Commission engine team | Commission engine Scenario F (Expansion) | Resolved (rates TBD) | 3-stage lifecycle: NN (Net New, full rate for SA-configured window) → EN (Existing customer Net New licenses, lower rate) → EE (Existing customer Existing licenses, lowest/zero). All rates SA-configurable before launch. partner_rate_table stores all 3 bands per tier × deal-type. | Resolved 2026-05-15
OQ-8 | Non-Blocking | Training platform — build on dogfood LMS vs buy (Docebo/Thought Industries) for v1? | Aashwij | Training subapp scope (§4.8), time-to-launch | Open |  | Before training sprint
OQ-14 | Non-Blocking | TOTP/MFA requirement conflict: sa-portal-architecture-v2.6.md §14.8 says role-based (PARTNER_ORG_ADMIN mandatory); this PRD §9.1 says tier-based (Advanced+ mandatory). Which is authoritative? | Renil | partner-iam MFA enforcement logic | Open |  | Before partner-iam sprint
OQ-15 | Non-Blocking | Grace quarter definition for tier downgrade — full next quarter after announcement, or remainder of current quarter? | Aashwij | Tier FSM timing | Open |  | Before tier engine sprint
OQ-17 | Non-Blocking | Conflict-loser 90-day re-registration — auto-unlock + notification OR manual partner re-submit? | Aashwij | Deal FSM, partner_conflicts design | Open |  | Before conflict queue sprint
OQ-18 | Non-Blocking | Rate-table retroactivity — confirm rates lock at deal APPROVAL (not registration, not invoice). PRD §6.3 and OQ-5 v0.4 both assert approval-lock. | Renil | Commission engine version-pin behaviour | Pending sign-off | PRD asserts: locked at approval. rateTableVersion stamped on approve action. | Before commission engine sprint
OQ-17v4 | Legal/Compliance | GDPR partner-org erasure spec — which fields can be pseudonymised vs retained? (Commission records: 7-year US / 8-year India retention obligations.) | Legal + Compliance | Data retention schema for partner_commissions and partner_accounts | Open |  | Before launch
OQ-18v4 | Legal/Compliance | Impersonation audit — when SA staff impersonates a tenant referred by a partner, does the partner get active notification (email/in-portal) or audit log only? | Legal + Compliance | auth.impersonation.partner-notified Kafka event | Open |  | Before launch

## 🗃️ Data Models
BlazeUp Partner Platform — MongoDB Collections & Key Schema Fields (PRD §8.2, §7.5)
Collection | Field / Block | Type | Required | Description | Notes / Constraints | Status
partner_accounts
partner_accounts | tenantId (BlazeUp SA) | ObjectId | Yes | Links partner account to their BlazeUp SA tenant |  | Pending
partner_accounts | name, slug, type, tier, status | String | Yes | Slug used in referral links. type: referral¦reseller¦SI¦MSP. tier: Registered¦Select¦Advanced¦Premier |  | Pending
partner_accounts | managerAllocation | 'dedicated'¦'shared' | Yes | Dedicated at $1.5M ARR within Premier; shared (max 1:3) otherwise. Locked Renil 2026-05-08. | Reviewed annually | Pending
partner_accounts | regions[], verticals[] | String[] | No | Territory coverage — linked to partner_territories for exclusivity |  | Pending
partner_accounts | agreementSignedAt | Date | Yes | Required before SA can advance application from Stage 1 | B3 flow | Pending
partner_accounts | certifications[], contacts[], referralLinks[], apiKeys[] | Array | No | Supporting arrays |  | Pending
partner_deals
partner_deals | partnerId, prospectDomain, dealType | ObjectId / String | Yes | Core deal identity. dealType: referral¦reseller¦cosell | Domain used for conflict check | Pending
partner_deals | estimatedACV, closedACV, expectedCloseDate | Number / Date | Yes | ACV used for commission projection at registration time | closedACV set on close | Pending
partner_deals | stage | String FSM | Yes | Registered→Approved→InProgress→Closing→Won/Lost/Expired |  | Pending
partner_deals | protectionExpiresAt, protectionExtensionCount | Date / Number | Yes | protectionExtensionCount max 1 (auto-extend once only). Locked Renil 2026-05-08. | OQ-20 | Pending
partner_deals | lastStageUpdateAt | Date | Yes | Activity gate for auto-extend: must have ≥1 stage update in last 30 days. Locked Renil 2026-05-08. | OQ-20 | Pending
partner_deals | commissionRate, rateTableVersion | Number / String | Yes | Stamped at APPROVAL (not registration). Locked per OQ-5 v0.4 / §6.3. | Version-pinned forever | Pending
partner_deals | cosellSplit?: {partnerPct, blazeupPct, overrideApproved} | Object | No | Populated for co-sell deals. Override requires partner written acceptance. Locked at approval. | Scenario C | Pending
partner_deals | billingModel | 'direct'¦'reseller'¦'partner_managed' | Yes | Set at deal registration. Immutable after tenant provisioning. | R3 mitigation | Pending
partner_commissions
partner_commissions | status | Enum | Yes | 'pending'¦'approved'¦'paid'¦'disputed'¦'clawback'¦'clawback_waived' | clawback_waived: new status — Renil 2026-05-08 | Pending
partner_commissions | clawbackWaiver?: {requestedAt, decision, evidence[]} | Object | No | Product-failure waiver block. evidence[] = linked support tickets / incident reports. SA reviews in 30 days. | Locked Renil 2026-05-08 | Pending
partner_commissions | payoutBatchId | ObjectId | No | Groups commissions paid in same payout run |  | Pending
partner_rate_table
partner_rate_table | version, effectiveFrom | String / Date | Yes | Every version preserved. commissionRate + rateTableVersion stamped on partner_deals at approval. |  | Pending
partner_rate_table | rates: { tier × dealType → { nn, en, ee } } | Nested Object | Yes | NN: Net New (full rate, SA-configured window years). EN: Existing customer Net New licenses (lower rate). EE: Existing customer Existing licenses (lowest/zero rate). | B6 architecture resolved — specific rates SA-configurable before launch | Pending
partner_rate_table | spiffProgrammes[] | Array | No | Bonus rate, regions[], tiers[], validFrom, validTo |  | Pending
tenant.attribution (on Tenant record)
tenant.attribution | source | Enum | Yes | 'partner_referral'¦'partner_reseller'¦'partner_cosell'¦'partner_msp'¦'partner_link'¦'direct'¦'inbound' |  | Pending
tenant.attribution | partnerTier | String | Yes | Tier at deal CLOSE — locked forever | Do not update on tier change | Pending
tenant.attribution | commissionStructure.rateTableVersion | String | Yes | Added per OQ-5 v0.4 / Renil 2026-05-08 |  | Pending
tenant.attribution | commissionStructure.productFailureWaiver? | Object | No | {requestedAt, requestedBy, decision: 'pending'¦'granted'¦'denied', decidedAt?, decidedBy?, evidence: ObjectId[]} | Locked Renil 2026-05-08 | Pending
tenant.attribution | attributionHistory[] | Array | No | Preserved on ANY SA override or MSP handoff. Never deleted. Fields: partnerId, source, effectiveFrom, effectiveTo, changedBy, reason (mandatory), approvedBy (two-eye). | B4 resolved — Renil 2026-05-15 | Pending
tenant.attribution | billingModel | Enum | Yes | 'direct'¦'reseller'¦'partner_managed'. Set at deal registration, immutable after provisioning. | R3 mitigation | Pending
tenant.mspTicketContentConsent (MSP tenants only)
tenant.mspTicketContentConsent | granted | Boolean | Yes | Default FALSE. Client admin can toggle ON at provisioning or later. | Locked Renil 2026-05-08 / OQ-22 | Pending
tenant.mspTicketContentConsent | grantedAt, grantedBy, revokedAt, revokedBy | Date / ObjectId | No | Full audit trail. Revocation immediate. Emits blazeup.partner.msp_ticket_consent.changed. | PDPA/PDPL legal basis | Pending

## 📡 Kafka Events
BlazeUp Partner Platform — Kafka Events (PRD §8.3)
Event Name | Category | Trigger / Condition | Key Consumers | Payload Notes | Status | Notes
blazeup.partner.registered | Partner | Partner account created (pending SA approval) | ms-notification (welcome email) | Standard envelope + partnerId, type, regions | Pending
blazeup.partner.approved | Partner | SA completed 3-stage approval (B3). PARTNER_ORG_ADMIN user created. | ms-notification (activation email), partner-iam | partnerId, tier, primaryContactEmail | Pending | B3 resolved — 3-stage FSM
blazeup.partner.tier.changed | Partner | Quarterly tier recalculation — upgrade immediate, downgrade 30-day notice | partner portal (immediate update), SA analytics | partnerId, oldTier, newTier, effectiveDate | Pending
blazeup.partner.deal.registered | Deal | Partner submits deal registration | ms-sa-partners (conflict check), dogfood CRM (create opp) | dealId, partnerId, domain, dealType, estimatedACV | Pending
blazeup.partner.deal.approved | Deal | SA approves deal; commissionRate + rateTableVersion stamped; protection clock starts | dogfood CRM (update opp + assign rep + task), partner portal (notification) | dealId, commissionRate, rateTableVersion, protectionExpiresAt, assignedRepId | Pending | Rate locked at this moment
blazeup.partner.deal.rejected | Deal | SA rejects deal registration | partner portal (notification with reason) | dealId, reason (mandatory) | Pending
blazeup.partner.deal.conflict_raised | Deal | Two parties register same domain | SA conflict queue, both parties notified | dealId, party1Id, party2Id, domain | Pending | R1 mitigation
blazeup.partner.deal.protection_extended | Deal | Auto-extend fires: ≥1 stage update in 30 days AND first extension | dogfood CRM (update protectionExpiresAt), partner portal (notification) | dealId, originalExpiry, newExpiry, extensionType: 'auto'¦'manual' | Pending | Locked Renil 2026-05-08 (OQ-20)
blazeup.partner.deal.won | Deal | Partner marks Won in portal OR BlazeUp rep closes in dogfood CRM | ms-sa-partners (commission calc + provision), dogfood CRM (close won), billing | dealId, tenantId, closedACV | Pending
blazeup.partner.deal.lost | Deal | SA marks deal Lost with reason | dogfood CRM (close lost), partner portal (notification) | dealId, closeReason | Pending
blazeup.partner.deal.expired | Deal | Protection window elapsed without activity or already auto-extended once | dogfood CRM (mark Stale + task), partner portal (expiry notification) | dealId, expiredAt | Pending
blazeup.partner.commission.earned | Commission | Commission calculated on deal close | SA commission ledger (pending approval queue) | commissionId, dealId, amount, rate, basis (NN/EN/EE) | Pending
blazeup.partner.commission.paid | Commission | SA approves commission + payout processed | partner portal (notification), accounting system | commissionId, paidAt, payoutBatchId | Pending
blazeup.partner.commission.waiver_decided | Commission | SA makes product-failure waiver decision | partner portal (notification), commission ledger | commissionId, decision: 'granted'¦'denied', amount, decidedBy | Pending | Locked Renil 2026-05-08
blazeup.partner.client.health_alert | Client | Client health signal drops (At Risk / Inactive threshold crossed) | dogfood CRM (task on account), partner portal (action required card) | tenantId, partnerId, oldStatus, newStatus, signals{} | Pending | The moat — native health data
blazeup.partner.client.transferred | Client | SA completes MSP handoff — attribution.partnerId updated | dogfood CRM (update account), both MSP portals, attribution history | tenantId, fromPartnerId, toPartnerId, reason, approvedBy | Pending | Locked Renil 2026-05-15 (B4)
blazeup.partner.msp_ticket_consent.changed | MSP | Client tenant admin grants or revokes MSP ticket-content consent | PartnerScopeGuard (immediate effect), audit log | tenantId, partnerId, granted: bool, actorId, timestamp | Pending | Locked Renil 2026-05-08 (OQ-22). PDPA/PDPL audit.
blazeup.partner.sandbox.reset_requested | Sandbox | Partner clicks Reset Demo in portal — sandbox re-seeds within 5 min | blazeup-microservice-sandbox-data (truncate + re-seed) | tenantId, partnerId, profile: 'smb'¦'midmarket'¦'enterprise' | Pending | Locked Renil 2026-05-15 (B5)
blazeup.partner.certification.earned | Training | Partner team member completes certification module | Tier qualification engine (re-evaluate), partner portal (badge update) | partnerId, userId, certificationType, earnedAt | Pending

## 🔌 API Endpoints
BlazeUp Partner Platform — REST API Endpoints (PRD §8.5)
Method | Endpoint | Auth | Category | Description | Key Notes | FE Uses? | Status
GET | /internal/partners | SA-JWT | SA Partner | List all partners (filterable by tier/type/region/status) |  | No | Pending
POST | /internal/partners | SA-JWT | SA Partner | Create partner account |  | No | Pending
PATCH | /internal/partners/:id | SA-JWT | SA Partner | Update partner account (tier, territories, notes, managerAllocation) |  | No | Pending
POST | /internal/partners/:id/approve | SA-JWT | SA Partner | Advance partner application through 3-stage FSM (B3). Records legal countersign or final approval. | 3-stage: SA Review → Legal Countersign → SA Final Approval | No | Pending
GET | /internal/partners/:id/commissions | SA-JWT | SA Partner | Full commission ledger for partner (earned, pending, paid, disputed, clawback) |  | No | Pending
POST | /internal/partners/:id/commissions/:cid/approve | SA-JWT | SA Commission | Approve commission payout. Two-eye required for >$10K. | Two-eye principle for amounts >$10K | No | Pending
POST | /internal/partners/:id/commissions/:cid/waiver-decision | SA-JWT | SA Commission | Record product-failure waiver decision. 30-day SLA. Decision final + logged. | Locked Renil 2026-05-08 | No | Pending
GET | /internal/deals | SA-JWT | SA Deal | All partner deals (filterable). Includes pending approval queue. |  | No | Pending
PATCH | /internal/deals/:id/approve | SA-JWT | SA Deal | Approve deal. Stamps commissionRate + rateTableVersion. Starts protection clock. Optionally proposes cosellSplit for co-sell >$100K ACV. | Rate locked at this moment. cosellSplit pending partner acceptance. | No | Pending
PATCH | /internal/deals/:id/reject | SA-JWT | SA Deal | Reject deal with mandatory reason |  | No | Pending
PATCH | /internal/deals/:id/protection-extend | SA-JWT | SA Deal | Manual SA extension after auto-extend exhausted (requires written reasoning) | Locked Renil 2026-05-08 (OQ-20) | No | Pending
GET | /internal/deals/conflicts | SA-JWT | SA Deal | Conflict queue — deals with competing registrations |  | No | Pending
PATCH | /internal/deals/conflicts/:id/resolve | SA-JWT | SA Deal | Resolve conflict — award to party A/B, mandatory reasoning, both notified, logged immutably | R1 mitigation | No | Pending
GET | /internal/commission/rates | SA-JWT | SA Commission | Current rate table (all versions available) |  | No | Pending
PUT | /internal/commission/rates | SA-JWT | SA Commission | Update rate table — creates new version, preserves all previous. NN/EN/EE rates per tier × deal-type. | B6 resolved — versioned | No | Pending
POST | /internal/commission/spiff | SA-JWT | SA Commission | Create SPIFF programme with regions, tiers, dates, bonus rate |  | No | Pending
GET | /v1/partner/dashboard | Partner-JWT | Partner Portal | Dashboard stats: pipeline, commissions, clients, tier progress, action required items |  | Yes | Pending
POST | /v1/partner/deals | Partner-JWT | Partner Portal | Register a new deal. Triggers conflict check + enrichment. Returns Deal ID + status. | Most critical endpoint. <2s response required. | Yes | Pending
GET | /v1/partner/deals | Partner-JWT | Partner Portal | List own deals with filter/search. Includes deal protection status. |  | Yes | Pending
PATCH | /v1/partner/deals/:id | Partner-JWT | Partner Portal | Update deal (notes, documents, stage update). Updates lastStageUpdateAt. | lastStageUpdateAt drives auto-extend gate | Yes | Pending
POST | /v1/partner/deals/:id/cosell-split-accept | Partner-JWT | Partner Portal | Partner formally accepts SA-proposed co-sell split override. Written acceptance recorded. | Locked Renil 2026-05-08 (Scenario C) | Yes | Pending
POST | /v1/partner/deals/:id/protection-extend-request | Partner-JWT | Partner Portal | Request manual SA extension after hard expiry. SA reviews with reasoning required. | Locked Renil 2026-05-08 (OQ-20) | Yes | Pending
GET | /v1/partner/clients | Partner-JWT | Partner Portal | List post-close clients with health status, ARR, renewal date, modules active |  | Yes | Pending
GET | /v1/partner/clients/:tenantId/health | Partner-JWT | Partner Portal | Detailed health metrics: MAU/DAU, module adoption %, last login, open tickets | The moat endpoint | Yes | Pending
GET | /v1/partner/clients/:tenantId/tickets | Partner-JWT | Partner Portal | Ticket count + severity (always). Ticket content ONLY if mspTicketContentConsent.granted=true. Sentinel response when restricted. | PartnerScopeGuard enforced. Locked Renil 2026-05-08 (OQ-22) | Yes | Pending
GET | /v1/partner/commissions | Partner-JWT | Partner Portal | Full commission history: earned, pending, paid, disputed, clawback |  | Yes | Pending
POST | /v1/partner/commissions/:id/dispute | Partner-JWT | Partner Portal | Raise commission dispute (one text field). SA Slack notification. 5-day SLA. | No form, no ticket number | Yes | Pending
POST | /v1/partner/commissions/:id/waiver | Partner-JWT | Partner Portal | Request product-failure waiver with evidence (linked support tickets / incident reports). SA 30-day SLA. | Locked Renil 2026-05-08 | Yes | Pending
GET | /v1/partner/referral-links | Partner-JWT | Partner Portal | List all referral links with click/conversion/ARR analytics per link |  | Yes | Pending
POST | /v1/partner/referral-links | Partner-JWT | Partner Portal | Create campaign referral link |  | Yes | Pending