## T7_Partner
ID | User Story Name | Feature Group | Sub-Group | Description | Actor | Pre-condition / Trigger | Acceptance Criteria (Dev & QC) | Sprint | Priority | Status | Person in Charge | Note
Phase 1 — Onboarding & Activation
PP001 | Activate partner account via email invite | Partner Onboarding | Account Activation | As a Partner Admin, I want to activate my partner account by setting a password through the email invite link, so that I can securely access the partner portal and begin registering deals. | Partner Admin | SA has approved the partner application. System has created the partner account with status PENDING_ACTIVATION. Activation email has been sent with a single-use token (72h TTL). | 1. Partner clicks the activation link in the email — link contains a single-use token. 2. System validates the token: if expired (> 72h) or already used, Partner is shown an error with a prompt to request a new invite. 3. Partner is presented with a password-set form (no pre-filled password — PENDING_ACTIVATION model, no temporary password issued by SA). 4. Password must meet complexity requirements (min 8 chars, 1 uppercase, 1 number, 1 special character); inline validation shown before submit. 5. For Registered and Select tier: TOTP (2FA) setup is optional — Partner may skip. 6. For Advanced and Premier tier: TOTP setup is mandatory — Skip button is not rendered; Partner cannot proceed without completing TOTP enrollment. 7. On successful activation: account status transitions from PENDING_ACTIVATION to Active; JWT issued (access token 8h, refresh token 30 days). 8. Partner is redirected to Home / Dashboard (/dashboard) after first login. 9. Activation token is invalidated immediately after use — cannot be reused. 10. Audit log: partner account ID, action = account_activated, timestamp. |  | High | To Do | Neven | PENDING_ACTIVATION model — no temporary password. TOTP mandatory for Advanced/Premier.
PP002 | View home dashboard | Partner Onboarding | Home Dashboard | As a Partner Admin, I want to view a home dashboard summarising my pipeline, commissions, and client health at a glance, so that I can immediately identify what needs my attention when I log in. | Partner Admin | Partner account is Active. Partner is authenticated. | 1. Dashboard route: /dashboard (or /). 2. KPI cards displayed: Active deals (count), Pending SA approval (count + oldest waiting), Total commissions earned YTD, Clients at renewal risk (count). 3. Pipeline snapshot: top 5 active deals by ACV with stage and days remaining on protection. 4. Recent activity feed: last 5 events (deal approved, commission paid, client health alert, tier change). 5. If partner has no deals yet: empty state shown with CTA "Register your first deal". 6. Tier badge and T12M ARR progress displayed in header. 7. Blazey AI assistant widget visible on dashboard; shows upsell suggestions based on client usage data. 8. Dashboard data reflects the authenticated partner's own deals and clients only — no cross-partner data visible. |  | High | To Do | Neven | —
Phase 2 — Deal Management
PP004 | Register a new deal | Deal Management | Deal Registration | As a Partner Admin, I want to register a new deal through a 4-step wizard completed in under 90 seconds on mobile, so that my prospect receives domain protection and I can track the expected commission before submitting. | Partner Admin | Partner account is Active. Partner has at least one member with BlazeUp Sales Certified (required to register deals). Partner is authenticated. | 1. Deal registration route: /deals/register. 2. Step 1 — Company: fields: Company name (required), Domain (required), Country (required). On domain entry: system auto-enriches logo, HQ country, and headcount via Apollo/Clearbit and displays enrichment results inline. System runs domain conflict check in real time — if domain already registered by another partner, inline warning shown before partner proceeds. 3. Step 2 — Contact: fields: Full name (required), Email (required), Job title (optional). 4. Step 3 — Deal details: fields: Estimated ACV (required), Expected close date (required), Modules of interest (multi-select, required), Deal type (Referral / Reseller / Co-sell — required). Live commission preview displayed immediately when ACV is entered, using partner's current tier rate and selected deal type. Preview updates in real time as ACV changes. 5. Step 4 — Confirm & Submit: read-only summary of all entered data; Partner may navigate back to edit. Submit button enabled only when all required fields are complete. 6. On submit: deal record created with status = Pending Review; registeredAt timestamp stamped to millisecond precision; Kafka: blazeup.partner.deal.registered fired. 7. System response on submit: < 2 seconds. 8. Partner receives in-portal and email confirmation: "Your deal has been submitted and is pending SA review." 9. Partner is redirected to /deals/:id (new deal detail page) after successful submission. 10. If domain conflict is detected after submission (race condition): deal is automatically routed to Conflict Detected status; partner is notified. |  | High | To Do | Bastian | Target 90 seconds on mobile. Live commission preview at Step 3. Domain conflict check at Step 1 (real-time) and on submit.
PP005 | View deal pipeline (My Pipeline) | Deal Management | Pipeline View | As a Partner Admin, I want to view all my registered deals in a pipeline list with stage, ACV, and protection status, so that I can monitor deal health and prioritise follow-up actions. | Partner Admin | Partner account is Active. Partner has at least one registered deal. | 1. Route: /deals. 2. Table columns: Deal (prospect company + domain), Deal ID, Type (Referral/Reseller/Co-sell/Expansion), ACV, Stage, Commission (estimated or locked), Protection (days remaining as progress bar), Last updated. 3. Filter tabs: All / Pending Approval / Approved / In Progress / Won / Lost / Expired — each shows count. 4. Search: filters by prospect company name or domain in real time. 5. Sort: by ACV, stage, or registration date. 6. Deals approaching protection expiry (≤ 14 days remaining) are flagged with amber indicator. 7. Deals with Conflict Detected status are flagged with red badge. 8. Each row clickable → navigates to Deal Detail (/deals/:id). 9. "Register new deal" CTA visible in toolbar. 10. Partner sees only their own deals — no other partner's deals visible. |  | High | To Do | Cofadict | —
PP006 | View deal detail | Deal Management | Deal Detail | As a Partner Admin, I want to view the full detail of a single deal including commission preview, protection window, and approval timeline, so that I understand exactly where my deal stands and what commission I will receive. | Partner Admin | Partner account is Active. Deal exists and belongs to the authenticated partner. | 1. Route: /deals/:id. 2. Header: prospect company name, domain, deal type badge, stage badge, ACV, expected close date. 3. Section — Commission details: estimated payout (or locked payout if approved), rate basis, deal type formula; rate shown as locked after SA approval with lock icon and approval date. 4. Section — Deal protection window: domain, protection start (on SA approval), expiry date, days remaining progress bar; auto-extend eligibility shown. 5. Section — Approval timeline (read-only): chronological list of status changes with actor, action, timestamp — no edit or delete controls rendered for any user. 6. For Co-sell deals: assigned BlazeUp Sales Rep (name + photo) displayed; commission split shown (partner % and cash amount); split read-only after SA approval. 7. For Reseller deals: billing flow summary displayed (BlazeUp invoices partner; partner invoices client); clawback not applicable note shown. 8. Action available if deal is Approved and partner type is Reseller/Co-sell: "Mark as Won" button → requires confirmed ACV and close date. 9. "Mark as Lost" available for Approved deals → requires close reason (dropdown + optional notes). 10. Approval Timeline is immutable — partner cannot edit any entry. |  | High | To Do | Cofadict | Approval Timeline must be immutable read-only. Commission locked indicator after SA approval.
PP007 | Mark reseller deal as Won | Deal Management | Deal Closure | As a Partner Admin, I want to mark my approved Reseller deal as Won when the client signs, so that tenant provisioning is triggered and my commission is calculated automatically. | Partner Admin | Deal is in Approved status. Deal type is Reseller or Co-sell (partner-close path). Partner is authenticated and is the deal owner. | 1. "Mark as Won" button visible on Deal Detail page for Approved Reseller and Co-sell deals. 2. Partner enters: confirmed ACV (required), close date (required), optional notes. 3. Confirmed ACV must be a positive number — inline validation before submit. 4. On confirm: deal status → Won; closedAt timestamp stamped. 5. Kafka: blazeup.partner.deal.won fired. 6. Commission engine calculates payout automatically: Reseller = list price − wholesale; Co-sell = ACV × tier rate × partner split %. 7. Commission record created with status = Pending Approval. 8. Tenant provisioning triggered based on billing model (reseller → BlazeUp invoices partner at wholesale). 9. go_live_at stamped on deal record when tenant is provisioned (used for clawback clock for Co-sell). 10. Partner receives notification: "Deal marked Won. Commission of $X is pending SA approval. Expected payout: net-30 from close date." 11. Partner is redirected to updated Deal Detail showing Won status and locked commission. |  | High | To Do | Cofadict | go_live_at anchors clawback clock. Reseller: no clawback. Co-sell: clawback applies.
PP008 | Register an expansion deal | Deal Management | Deal Registration | As a Partner Admin, I want to register an expansion deal against an existing attributed client, so that I earn expansion commission when the client adds modules or seats. | Partner Admin | Partner account is Active. An existing Won deal with active attribution exists (within 12-month attribution window). Partner is authenticated. | 1. Partner selects "Register expansion deal" from /clients/:id or /deals/register with Expansion type. 2. Deal type = Expansion; existing tenant_id pre-populated from attributed client. 3. Partner selects expansion type: additional seats, new modules, or tier upgrade. 4. System validates attribution is within 12-month window from last deal close; if window expired, expansion deal blocked with inline message. 5. Partner enters: expansion ACV delta (required), modules/seats being added (required), expected close date. 6. Commission preview: expansion rate × delta ARR (typically 50% of new-logo referral rate, SA-configured); displayed live. 7. On submit: Expansion Deal record created; Kafka: blazeup.partner.deal.registered with deal_type = expansion. 8. No new tenant is created — provisioning updates existing tenant on deal Won. 9. Partner notified on SA approval. |  | Medium | To Do |  | Attribution window 12 months. No new tenant created. Expansion commission = SA-configured rate × delta ARR. | resell
PA025 | Accept or review co-sell split override proposed by SA | Deal Management | Deal Review | As a Partner Admin, I want to review and accept or decline a co-sell commission split override proposed by SA for deals above $100K ACV, so that the split is locked only with my explicit written agreement and BlazeUp cannot impose a non-default split unilaterally. | Partner Admin | A co-sell deal with ACV > $100K exists. SA has proposed a non-default commission split override at deal approval. Partner Admin is authenticated. | 1. When SA proposes a non-default co-sell split for a deal with ACV > $100K, an Action Required notification appears on the partner's Home Dashboard with a day countdown. 2. Partner Admin navigates to the deal in /deals; a prominent banner shows: "BlazeUp has proposed a commission split of [X%] partner / [Y%] BlazeUp for this deal. The default is 70% / 30%. Your written acceptance is required to proceed." 3. The deal stage does not advance and the protection clock does not start until the Partner Admin explicitly accepts or declines the proposed split. 4. Partner Admin may click [Accept override] — a confirmation modal shows the proposed split and requires Partner Admin to type "I AGREE" or tick an explicit consent checkbox before [Confirm] is enabled. 5. On acceptance: the cosellSplit{} record is updated with overrideApproved = true; the split is locked and cannot be renegotiated; deal proceeds to Approved state; both parties are notified. 6. Partner Admin may click [Decline override] — a modal opens with an optional reason; on confirmation, SA is notified and the deal reverts to the default 70/30 split or enters SA review. 7. Audit log entry is created recording Partner Admin actor, proposed split, decision (accepted / declined), and timestamp. |  | High | To Do | Cofadict | v1.8: co-sell split override for >$100K ACV. Partner written acceptance required. Split locked at acceptance. Q5/OQ-23 resolved.
Phase 3 — Commission & Payouts
PP009 | View commission and payout history | Commission Management | Commission History | As a Partner Admin, I want to view all my commissions including pending, approved, and paid payouts with full calculation detail, so that I can verify each amount is correct and track expected payment dates. | Partner Admin | Partner account is Active. At least one deal has been Won. | 1. Route: /commissions. 2. Table columns: Commission ID, Deal (prospect + deal ID), Type (Referral/Reseller/Co-sell/Expansion), Base ACV, Rate (locked at approval + rate table version), Commission amount, Status (Pending/Approved/Paid/Clawback), Expected payout date. 3. Filter tabs: All / Pending / Approved / Paid / Clawback — each shows count and total amount. 4. Filter by time period: MTD / QTD / YTD. 5. Each row expandable → shows full breakdown: formula applied, rate table version, lock date, two-eye approval chain (if > $10K). 6. Clawback rows highlighted in amber with clawback reason and amount deducted. 7. "Total YTD earned" and "Pending payout" KPI figures shown at top. 8. Partner sees only their own commissions — no cross-partner visibility. |  | High | To Do | Bastian | Rate table version shown per commission. Two-eye chain visible for >$10K payouts.
PP010 | Request clawback waiver (product-failure) | Commission Management | Clawback | As a Partner Admin, I want to request a product-failure clawback waiver when a client churns due to a BlazeUp product issue, so that I am not penalised for churn outside my control. | Partner Admin | A commission clawback has been applied to the partner's account. Churn occurred within 12 months of tenant go_live_at. Deal type is Referral or Co-sell (waiver not available for Reseller). | 1. "Request Waiver" button visible on Clawback commission rows in /commissions. 2. Partner enters: waiver reason (required, free text), linked support ticket ID or incident report (required). 3. Submission creates a waiver request record; status = Pending SA Review. 4. Partner receives confirmation: "Waiver request submitted. SA will review within 30 days." 5. SA reviews within 30-day SLA; decision = approved (full or partial credit) or rejected. 6. Kafka: blazeup.partner.commission.waiver_decided fired on SA decision. 7. Partner receives notification of SA decision with reason. 8. Decision is final — no appeal path available; partner portal shows decision as read-only. 9. Waiver request only available for Referral and Co-sell deals — Reseller clawback waiver button is not rendered. |  | Medium | To Do | Bastian | 30-day SLA for SA review. Decision is final and immutable. Clawback applies only to Referral/Co-sell.
PP011 | Update payment details | Commission Management | Payment Settings | As a Partner Admin, I want to update my bank account details for commission payouts, so that payments are directed to the correct account. | Partner Admin | Partner account is Active. Partner is authenticated with MFA completed. | 1. Route: /settings → Payment details section. 2. Fields: Bank name, Account holder legal name, Account number (masked on display — last 4 digits only), BSB/Sort code / IBAN / SWIFT-BIC, Currency preference. 3. All banking fields are encrypted at rest (AES-256-GCM, client-side field-level encryption) — plaintext values are never stored in application databases. 4. Display masking: only last 4 digits of account number and IBAN shown in UI — all other characters replaced with asterisks. 5. Changes require re-authentication (MFA challenge) before saving. 6. On save: new banking details take effect for next scheduled payout; in-progress payouts use previous details. 7. Audit log: actor, action = banking_details_updated, timestamp, IP address — retained 7 years. 8. Partner receives email confirmation of banking detail change. |  | High | To Do | Bastian | AES-256-GCM field-level encryption. MFA re-challenge required. Display masked to last 4 digits.
Phase 4 — Client Management
PP012 | View client health dashboard | Client Management | Client Health | As a Partner Admin, I want to view DAU/MAU, module adoption, and renewal dates for each client I have sourced, so that I can identify upsell opportunities and act before clients churn. | Partner Admin | Partner account is Active. Partner has at least one Won deal with an active tenant. | 1. Route: /clients. 2. Client list columns: Client name, Modules active, DAU/MAU (%), Renewal date (days remaining), Open support tickets (count + severity), Health score. 3. Health score calculated from: DAU/MAU trend, module adoption, days to renewal, open critical tickets. 4. Clients at churn risk (health score below threshold) flagged with red indicator. 5. Clients with renewal within 30 days flagged with amber indicator. 6. Each row clickable → /clients/:id (client health detail). 7. Data sourced natively from BlazeUp platform — no external integration required. 8. Blazey AI assistant shows upsell suggestions per client based on usage patterns. 9. For non-MSP partners: support ticket visibility = count + severity only (no ticket content). 10. For MSP partners: full ticket content visible only if mspTicketContentConsent.granted = true on that tenant. |  | High | To Do | Neven | Native DAU/MAU from BlazeUp platform. MSP ticket content gated by mspTicketContentConsent.
PP013 | View client health detail | Client Management | Client Health | As a Partner Admin, I want to view the full health detail of a single client including module-level adoption and activity trends, so that I can have informed conversations with the client and identify expansion opportunities. | Partner Admin | Partner account is Active. Client tenant exists and is attributed to the authenticated partner. | 1. Route: /clients/:id. 2. Header: client name, industry, headcount, BlazeUp modules active, billing model, renewal date. 3. Section — Usage: DAU/MAU by module (chart), 30/60/90 day trend, inactive users count. 4. Section — Module adoption: % of licensed seats using each module; modules with < 30% adoption flagged. 5. Section — Support: open ticket count and severity breakdown. For non-MSP: count + severity only. For MSP: full content if consent granted. 6. Section — Upsell opportunities: Blazey AI suggestions (e.g. "Client uses Core HR but not Payroll — 420 seats eligible"). 7. Section — Expansion deals: any open or won expansion deals for this client. 8. "Register expansion deal" CTA available if attribution window (12 months) is still active. 9. Partner cannot access: payroll/salary data, individual PII above SA-configured ceiling, employee records, billing configuration. |  | High | To Do | Neven | Hard limits: no payroll/salary data, no PII above SA ceiling, no billing config.
Phase 5 — Training & Certification
PP015 | View and start certification courses | Training & Certification | Certification | As a Partner Admin, I want to view available certifications and track my team's completion status, so that we unlock the deal types and commission eligibility we need. | Partner Admin | Partner account is Active. Partner is authenticated. | 1. Route: /training. 2. Certification catalogue: BlazeUp Sales Certified (4h), BlazeUp HR Specialist (6h), BlazeUp CRM Specialist (4h), BlazeUp Implementation Certified (12h). 3. Each certification card shows: title, duration, what it unlocks, completion status per team member. 4. "What it unlocks" shown clearly per cert: - Sales Certified → deal registration + referral commission eligibility - HR Specialist → co-sell eligibility on HR/Payroll deals - CRM Specialist → co-sell eligibility on CRM deals - Implementation Certified → MSP billing model access 5. Partner Admin can see completion status for all team members. 6. On completion: Kafka: blazeup.partner.certification.earned fired; unlocked feature activated immediately. 7. Required certifications for pending deal types are highlighted — e.g. if partner has co-sell deal pending without HR cert, inline nudge shown. |  | Medium | To Do |  | Cert unlocks features, not tiers. blazeup.partner.certification.earned on completion.
Phase 6 — Team Management
PP018 | Invite and manage team members | Team Management | Member Management | As a Partner Admin, I want to invite new team members to the portal and manage their access, so that my sales team can register deals and view the shared pipeline. | Partner Admin | Partner account is Active. Partner Admin is authenticated. | 1. Route: /team. 2. Team member list: name, email, role (Admin/Member), status (Active/Invited/Deactivated), last login, certifications completed. 3. "Invite member" CTA: Partner Admin enters email; system sends invite email with single-use activation link (72h TTL, PENDING_ACTIVATION model — no temporary password). 4. Partner Admin may assign role: Admin (full access) or Member (deal registration + shared pipeline view only). 5. Partner Admin may deactivate a member → member loses portal access immediately; their deals remain visible. 6. Partner Admin may reactivate a deactivated member. 7. Only one Partner Admin role per account — Admin cannot downgrade themselves to Member. 8. Partner Member inherits the same deal pipeline visibility as Partner Admin for all shared deals. 9. Deactivated member's deals and commissions remain attributed to the partner account. |  | High | To Do |  | PENDING_ACTIVATION model for invites. Only one Admin per account.
PP019 | View partner team pipeline (Member view) | Team Management | Pipeline Sharing | As a **Partner Member**, I want to view and work on deals registered by any member of my partner organisation, so that the team shares a single pipeline without duplication. | Partner Member | Partner account is Active. Partner Member is authenticated. Partner Admin has shared pipeline access. | 1. Route: /deals — same as Partner Admin pipeline view. 2. Member sees all deals registered by any member of the same partner account (not just their own). 3. Member can: register new deals, view deal details, update stage on own deals, mark Reseller deals as Won. 4. Member cannot: manage team members, update payment details, view/edit partner account settings. 5. Deals are attributed to the registering member — commission is credited to the partner account (not the individual member). 6. Member sees commission ledger for deals they registered; Partner Admin sees all commissions for the whole account. |  | Medium | To Do |  | Pipeline shared across all members. Commission attributed to partner account, not individual.
PP003 | Change team member role between Admin and Member | Partner Onboarding | Account Activation | As a Partner Admin, I want to change a team member's role between Admin and Member, so that access responsibilities can be reassigned as the team evolves. | Partner Admin | Partner Admin is authenticated. At least one other team member exists in Active status. | 1. Partner Admin navigates to /team; each member row shows name, email, role badge, and an [Edit role] action. 2. Partner Admin clicks [Edit role] on a member; a dropdown shows Admin / Member options; the current role is pre-selected. 3. System prevents the Partner Admin from changing their own role if they are the sole Admin in the organisation; an inline message is shown: "You are the only Admin — assign another Admin first before changing your role." 4. On save: the member's role is updated immediately; the member's session is not invalidated; role badge updates on the /team list. 5. Audit log entry is created recording Partner Admin actor, affected member, previous role, new role, and timestamp. |  | Medium | To Do | — | At least one Admin must exist at all times; system must prevent the last Admin from being demoted.
PP023 | Revoke team member access | Partner Onboarding | Account Activation | As a Partner Admin, I want to revoke a team member's access to the partner portal, so that former employees or contractors lose access immediately and cannot act on behalf of the organisation. | Partner Admin | Partner Admin is authenticated. Target team member exists in Active status. | 1. Partner Admin navigates to /team; each member row shows a [Revoke access] action. 2. Clicking [Revoke access] opens a confirmation dialog: "This will immediately sign out [name] and remove their access. This cannot be undone without re-inviting." 3. System prevents revocation of the last Admin; if the target is the sole Admin, [Revoke access] is disabled with a tooltip explaining the constraint. 4. On confirmation: member status is set to Revoked; their JWT (access and refresh tokens) is invalidated server-side immediately; any active session is terminated. 5. Revoked member can no longer log in; their historical actions remain in the audit log attributed to their userId. 6. Revoked member is removed from the /team list or displayed with a "Revoked" badge (read-only). 7. Audit log entry is created recording Partner Admin actor, revoked member userId, and timestamp. |  | High | To Do | — | JWT must be invalidated server-side immediately on revocation.
Phase 7 — Settings & Profile
PP020 | Manage partner profile and account settings | Settings & Profile | Profile Management | As a Partner Admin, I want to update my company profile, contact information, and notification preferences, so that my account details are accurate and I receive the right alerts. | Partner Admin | Partner account is Active. Partner Admin is authenticated. | 1. Route: /settings. 2. Sections: Company info (name, domain, address, logo upload), Primary contact (name, email, phone), Notification preferences (email alerts for: deal approved, commission paid, tier change, client health alert, support ticket update), Security (change password, TOTP management). 3. Company name and domain changes require SA approval — fields are editable but show "Pending SA review" status after save. 4. Logo upload: max 2MB, PNG/JPG only; displayed in portal header after save. 5. Notification preferences saved per user (not per account) — Partner Admin and Members have independent preferences. 6. Password change requires current password verification. 7. TOTP: Partner Admin can enrol, regenerate backup codes, or remove TOTP (Advanced/Premier tier: TOTP removal blocked — backend enforces). 8. Audit log: actor, action = profile_updated, fields_changed, timestamp. |  | Medium | To Do |  | Company name/domain changes need SA approval. TOTP removal blocked for Advanced/Premier.
PP021 | View tier status and progress | Settings & Profile | Tier Progress | As a Partner Admin, I want to view my current tier, T12M ARR progress toward the next tier, and what benefits I unlock at each tier, so that I can plan my sales activity to maintain or advance my tier. | Partner Admin | Partner account is Active. Partner Admin is authenticated. | 1. Tier status visible in portal header (tier badge) and in Settings → Tier section. 2. Current tier displayed with: T12M ARR value, threshold for current tier, threshold for next tier, ARR gap to next tier. 3. Progress bar: current T12M ARR / next tier threshold (capped at 100% if Premier). 4. Tier benefits table: all 4 tiers with rates, protection windows, and features — current tier highlighted. 5. If partner is in grace period (downgrade announced): grace_tier_until date shown with notice "Your current tier rates are protected until [date]." 6. Next quarterly review date shown. 7. Tier changes communicated via in-portal notification and email — 30-day advance notice for downgrades. |  | Medium | To Do |  | Grace period display. grace_tier_until shown when partner is in downgrade grace quarter.
PP024 | Manage TOTP two-factor authentication settings | Navigation & Overview | Partner Detail | As a Partner Admin, I want to enroll in or update my TOTP two-factor authentication settings, so that my account is protected according to the security requirements of my tier. | Partner Admin | Partner Admin is authenticated. For Advanced/Premier tiers: TOTP is already enrolled. | 1. Partner Admin navigates to /settings → Security; TOTP enrollment section shows current status (Enabled / Not enrolled). 2. If TOTP is not enrolled: [Set up 2FA] button is shown; clicking it opens the TOTP setup wizard displaying a QR code compatible with Google Authenticator and Authy, plus a manual entry key for accessibility. 3. Partner Admin must enter a valid 6-digit TOTP code to complete enrollment; [Confirm] is disabled until a 6-digit code is entered; an invalid code shows an inline error. 4. On successful enrollment: TOTP status updates to Enabled; recovery codes are generated and displayed once — Partner Admin must acknowledge saving them before the modal closes. 5. If the partner's tier is Registered or Select: an [Disable 2FA] option is available; clicking it requires password re-confirmation before disabling. 6. If the partner's tier is Advanced or Premier: [Disable 2FA] is not rendered; TOTP cannot be disabled at these tiers. 7. Audit log entry is created for each TOTP enrollment and disable action, recording actor, action, and timestamp. |  | High | To Do | — | TOTP optional for Registered/Select; mandatory for Advanced/Premier. Disabling TOTP not permitted at Advanced/Premier.
Phase 8 — Support
PP022 | Submit and track support tickets | Support | Support Tickets | As a Partner Admin, I want to submit support requests and track their status in the portal, so that I can get help on deal issues, commission queries, and technical problems without leaving the partner platform. | Partner Admin | Partner account is Active. Partner Admin is authenticated. | 1. Route: /support. 2. "New ticket" form: subject (required), category (Deal / Commission / Technical / Account / Other), description (required), attachments (optional, max 10MB). 3. Ticket can be linked to a specific deal or commission record from a dropdown. 4. Ticket list: ID, subject, category, status (Open/In progress/Resolved/Closed), created date, last updated. 5. Partner can view full ticket thread including SA responses. 6. Partner can add replies to open tickets. 7. Partner can close a resolved ticket. 8. Email notification sent to partner on: ticket created, SA reply received, ticket closed. 9. SLA visibility: partner sees target response time based on ticket priority (Critical 4h, High 1 business day, Medium 3 business days). |  | Medium | To Do
Partner Portal — Partner Admin User Stories v1.8 ¦ Actor: Partner Admin ¦ Based on PRD v1.8+ Analysis doc