## Bug Tracker
Bug ID | Test Case ID | Test Case Name | Module | Feature | Severity | Priority | Status | Summary | Expected | Actual | Evidence / Assertion | Reported By | Date Opened | Date Closed | Notes
API
BUG-API-001 | 2060122 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_022 | Partner | Certifications | Major | P2 | CLOSE | Re-granting the same certification to the same user creates a duplicate | Re-grant is idempotent (or 409) — no second active cert | Returns 201 and creates a 2nd active cert | AssertionError: re-granting must not duplicate active cert | QA | 2026-07-16 | 2026-10-01 | CLOSED 2026-10-01 — NOT A BUG (works as designed, confirmed by BE / Khoa Nguyen on PPM-BUG-01): re-grant is a RENEWAL — the active cert is revoked (revokeReason=superseded_by_renewal) and one new active cert is created; a unique index allows one active cert per user+type. The TC counted records regardless of status (revoked + active = 2) → false positive. Test fixed to count ACTIVE only + assert the renewal trail; TC 2060122 PASSES, be_gap removed.
BUG-API-002 | 2060208 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 | Partner | Deal Approval | Major | P2 | CLOSE | Approving a deal does not stamp rate / rateTableVersion | Approved deal exposes rate + rateTableVersion | Fields not stamped/exposed | AssertionError: approved deal must stamp rate + rate table version | QA | 2026-07-16
BUG-API-003 | 2060221 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_021 | Partner | Deal Registration | Major | P2 | CLOSE | Deal registration accepts a non-existent (ghost) planId | Reject 4xx when planId absent (FK validation) | Returns 201 registered | CHECK ghost planId (verified absent) -> FAIL (status=201) | QA | 2026-07-16
BUG-API-004 | 2060713 | PARTNER_API_PARTNER_USERS_013 | Partner | Partner Users | Major | P2 | CLOSE | Inviting a duplicate email creates a second user | Reject (409) or idempotent — no duplicate user | Returns 201; two users share one login | AssertionError: re-inviting must not duplicate user | QA | 2026-07-20
BUG-API-005 | 2061003 | PARTNER_API_AUTH_ACCESS_CONTROL_003 | Partner | AUTH_ACCESS_CONTROL | Major | P2 | CLOSE | cross-partner access - a partner cannot read another's deal. | 404 (preferred, hides existence) or 403 for cross-partner access | Returns 400 (mislabels a valid request as malformed); isolation holds (no data leak) | FAIL ¦ [1/1] Partner B requests partner A's deal → refused, no leak (333ms) -- AssertionError: cross-partner access should be 404 (preferred) or 403, got 400 — BE returns 400 (a valid request, not a bad one); confirm with BE | AI Triage | 2026-07-20
BUG-API-006 | 2060231 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_031 | Partner | DEAL_REGISTRATION_PIPELINE | Minor | P2 | CLOSE | GET deal by a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_registration_pipeline_031 [1/2]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-007 | 2060232 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_032 | Partner | DEAL_REGISTRATION_PIPELINE | Minor | P2 | CLOSE | lose deal on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_registration_pipeline_032 [2/3]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-008 | 2060228 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_028 | Partner | DEAL_REGISTRATION_PIPELINE | Minor | P2 | CLOSE | approve deal on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_registration_pipeline_028 [1/3]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-009 | 2060229 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_029 | Partner | DEAL_REGISTRATION_PIPELINE | Minor | P2 | CLOSE | resolve-conflict on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_registration_pipeline_029 [6/6]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-010 | 2060230 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_030 | Partner | DEAL_REGISTRATION_PIPELINE | Minor | P2 | CLOSE | extend-protection on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_registration_pipeline_030 [8/8]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-011 | 2061111 | PARTNER_API_DEAL_APPROVAL_QUEUE_011 | Partner | DEAL_APPROVAL_QUEUE | Minor | P2 | CLOSE | reject deal on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent deal id | 400 Bad Request with message "Deal 000000000000000000000000 not found" (status contradicts message) | test_partner_api_deal_approval_queue_011 [1/3]: expected 404, got 400, msg="Deal 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-012 | 2060113 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_013 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Minor | P2 | CLOSE | approve partner: well-formed but non-existent partner id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent partner id | 400 Bad Request with message "Partner 000000000000000000000000 not found" (status contradicts message) | test_partner_api_partner_account_management_013 [1/3]: expected 404, got 400, msg="Partner 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-013 | 2060114 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_014 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Minor | P2 | CLOSE | deactivate partner: well-formed but non-existent partner id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent partner id | 400 Bad Request with message "Partner 000000000000000000000000 not found" (status contradicts message) | test_partner_api_partner_account_management_014 [1/3]: expected 404, got 400, msg="Partner 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-014 | 2060115 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_015 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Minor | P2 | CLOSE | change-tier partner: well-formed but non-existent partner id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent partner id | 400 Bad Request with message "Partner 000000000000000000000000 not found" (status contradicts message) | test_partner_api_partner_account_management_015 [6/6]: expected 404, got 400, msg="Partner 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-015 | 2060120 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_020 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Minor | P2 | CLOSE | grant-certification on a well-formed but non-existent userId returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent userId | 400 Bad Request with message "User 000000000000000000000000 not found" (status contradicts message) | test_partner_api_partner_account_management_020 [4/4]: expected 404, got 400, msg="User 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-016 | 2060714 | PARTNER_API_PARTNER_USERS_014 | Partner | PARTNER_USERS | Minor | P2 | CLOSE | reset-password on a well-formed but non-existent userId returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent userId | 400 Bad Request with message "User 000000000000000000000000 not found" (status contradicts message) | test_partner_api_partner_users_014 [1/2]: expected 404, got 400, msg="User 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-017 | 2060414 | PARTNER_API_TERRITORIES_014 | Partner | TERRITORIES | Minor | P2 | CLOSE | get-territory-by-id on a well-formed but non-existent id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent / already-removed territory id | 400 Bad Request with message "Territory ... not found" (status contradicts message) | test_partner_api_territories_014 [1/2]: expected 404, got 400, msg="Territory 000000000000000000000000 not found" | QA (review) | 2026-07-20
BUG-API-018 | 2060415 | PARTNER_API_TERRITORIES_015 | Partner | TERRITORIES | Minor | P2 | CLOSE | delete territory on a non-existent / already-removed id returns 400 instead of 404 | 404 Not Found for a well-formed but non-existent / already-removed territory id | 400 Bad Request with message "Territory ... not found" (status contradicts message) | test_partner_api_territories_015 [1/3] + [3/3]: expected 404, got 400 (ghost id AND already-removed), msg="Territory ... not found" | QA (review) | 2026-07-20
BUG-API-019 | 2060512 | PARTNER_API_CERTIFICATIONS_SA_012 | Partner | CERTIFICATIONS_SA | Minor | P2 | CLOSE | revoke-certification not-found targets (ghost user / cert-not-held / already-revoked) return 400 instead of 404 | 404 Not Found when the revoke target (user or active cert) does not exist | 400 Bad Request with a "not found" message (User ... not found / Active ... certification not found) | test_partner_api_certifications_sa_012: cases 2,3,5 expected 404, got 400 (msg contains not found) | QA (review) | 2026-07-20
BUG-API-020 | 2060234 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_034 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P2 | CLOSE | Win deal: WinDealDto required fields not enforced (companyWebsite/industry/adminFirstName/adminLastName) | 400 when a required win-intake field is missing (per WinDealDto required list) | 201 - deal is won even with all required fields missing (empty body also wins) | test_partner_api_deal_registration_pipeline_034 [1-4/8]: missing companyWebsite/industry/adminFirstName/adminLastName each returned 201 (expected 400) | QA (review) | 2026-07-22 | 2026-10-13 | CLOSED 2026-10-13 - FIXED by BE. run_20261009_144113: steps [1/8]-[4/8] (missing companyWebsite / industry / adminFirstName / adminLastName) each now return 400 'required win-intake fields - <field> is missing' (was 201). TC-2060234 still FAILS, but at step [8/8] and for a DIFFERENT cause - see BUG-API-043 (/win uncallable).
BUG-API-021 |  | (no TC yet — DELETE partner is never asserted) | Partner | PARTNER_ACCOUNT_MANAGEMENT | Major | P2 | Open | Soft delete is INTENTIONAL (confirmed by BE) — but a deleted partner and a suspended one both end up with status='suspended', so no client can tell them apart. The business status 'suspended' has effectively lost its meaning, and QA has no way to remove test data. | Keep the soft delete. Add a way to DISTINGUISH the two states — e.g. a read-only deletedAt / isDeleted field, or an optional filter on GET /v1/sa/partners. No behaviour change needed and SA can still see every partner. Separately: a supported way for QA to purge its own test data (maintenance endpoint, or an agreed manual DB cleanup). | DELETE returns 200 {"message":"Partner deleted successfully"}; the record stays, status flips pending/active -> 'suspended' and internalNotes -> 'Deleted by SA'. That free-text note is the ONLY signal separating a deleted partner from a genuinely suspended one. Measured on stgsa 2026-08-10: 2371 of 2416 partners are 'suspended', and 2369 of those carry 'Deleted by SA' — so only 2 are real suspensions. Volume is also growing: 1808 partners on 2026-08-06 -> 2416 on 2026-08-10 (+608 in 4 days), and nothing can remove them. | Probe on stgsa 2026-08-06: create partner -> DELETE (200) -> GET /v1/sa/partners?search=<name> still returns it at +0s/+3s/+10s with status='suspended', internalNotes='Deleted by SA'. Reproduced from a UI run: 'CLEANUP LEAK: DELETE partner ... returned HTTP 200 but the record is STILL listed'. | QA (review) | 2026-08-06 |  | BE DESIGN CONFIRMED (Khoa Nguyen, 2026-08-10): partners are never hard-deleted on purpose — SA must see every partner, and the status has to be revertible. So this is NOT a request to hard delete; the remaining ask is only a field that separates 'deleted' from 'suspended'. ¦ Impact on automation: created_resources cleanup receives 200 and reports success while removing nothing — that is how ~2.4k QA-AUTO partners accumulated unnoticed. utils/ui_cleanup.py and utils/cleanup_staging.py now re-read the record after DELETE and report CLEANUP LEAK instead of trusting the status code. ¦ Impact on testing: PARTNER_UI_SA_PARTNER_MODULE_016 (reactivate) needs a genuinely Suspended partner and only 2 candidates exist among 2371 rows. ¦ Also missing, tracked here for now: no DELETE for deals, and no delete/revoke for partner-users (only certifications), so data created by PARTNER_UI_MY_PIPELINE_005 and PARTNER_UI_PARTNER_TEAM_001 cannot be cleaned by any route. ¦ Open question back to Product: should 'application declined' and 'active partner suspended' really share one status too? deactivate serves both.
BUG-API-022 | 2061401 | PARTNER_API_PARTNER_TEAM_001 | Partner | PARTNER_TEAM | Major | P2 | Open | partner team directory - invited member appears in list and detail. | partner team directory - invited member appears in list and detail. | FAIL ¦ [6/6] Read the session user by id → must return THAT user (259ms) -- AssertionError: GET /directory/users/{userId} ignored the path parameter: asked for 6aaa783b5a1d688484cf3045, got 6aaa783f5a1d688484cf3059 (team.qa.auto+aaron35-aa19222eed3b@ | FAIL ¦ [6/6] Read the session user by id → must return THAT user (400ms) -- AssertionError: GET /directory/users/{userId} ignored the path parameter: asked for 6ac4b5cfd1eeecba2e946cf6, got None (qa.auto+michael61-021d89c8060e@mailinator.com). A ghost id and a malformed id return this same record with HTTP 200. Partner scoping still holds — another partner gets its own user, not this one — so it is wrong data, not a cross-partner leak. BUG-API-022, confirm with BE. | AI Triage | 2026-09-16 |  | Re-verified 2026-10-06: same defect, but the endpoint now answers 'got none' where it previously returned ANOTHER user ('got <id>') - same root cause (path parameter ignored). Evidence refreshed to the current run so reconcile matches it.
BUG-API-023 | 2061403 | PARTNER_API_PARTNER_TEAM_003 | Partner | PARTNER_TEAM | Major | P2 | Open | team member deals and commissions - own records, scoped. | team member deals and commissions - own records, scoped. | FAIL ¦ [6/7] The rollup must DISCRIMINATE between members (547ms) -- AssertionError: GET /directory/users/{userId}/deals ignores the path parameter: the member 6aab91e1b8ca8e4baea2a4ca registered NO deals, yet asking for it returns the same 1 row(s) | FAIL ¦ [6/7] The rollup must DISCRIMINATE between members (547ms) -- AssertionError: GET /directory/users/{userId}/deals ignores the path parameter: the member 6aab91e1b8ca8e4baea2a4ca registered NO deals, yet asking for it returns the same 1 row(s) as the session user who registered them. A ghost u | AI Triage | 2026-09-17
BUG-API-024 | 2060124 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_024 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Critical | P1 | CLOSE | PATCH /v1/sa/partners/:id accepts fields UpdatePartnerDto does not expose. _id -> HTTP 500 leaking the MongoDB error; code and status are silently written. Writing status moves a PENDING partner straight to active. | A field outside UpdatePartnerDto is ignored or refused with 400 — never a 5xx, never a write. status must change only through POST /partners/:id/approve¦deactivate, so the 3-stage approval FSM (PRD §12.1 B3: SA Review -> Legal Countersign -> SA Final Approval) cannot be skipped. Error bodies must not expose the storage engine. | PATCH {"_id": "<ghost>"} -> 500 "Plan executor error during findAndModify :: caused by :: Performing an update on the path '_id' would modify the immutable field '_id'". PATCH {"code": "QA-HACKED"} -> 200 and the partner code is overwritten. PATCH {"status": "active"} -> 200 and a pending partner becomes active without approve. | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_024 step [5/5], staging 2026-09-17, BE v26 @ 0b35609. Each field sent on its own so the failing one is named. The positive TC _023 passes: the 6 declared fields persist and a repeat PATCH is idempotent. | QA (automation) | 2026-09-17 |  | NEEDS BE CONFIRMATION on the status part: is writing status through PATCH intended for SA, or an FSM bypass? The _id 500 and the writable code are defects either way.
BUG-API-025 | 2060236 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_036 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P1 | CLOSE | GET /v1/sa/deals: limit=0 and page=abc are accepted and the endpoint returns the ENTIRE result set in one page (1406 deals). limit=-1 is correctly refused with 400. | Any nonsensical pagination value is refused with 400, the same way limit=-1 already is. A page size must never resolve to unbounded. | GET /v1/sa/deals?limit=0 -> 200, data[] holds 1406 rows. GET /v1/sa/deals?page=abc -> 200, data[] holds 1406 rows. GET /v1/sa/deals?limit=-1 -> 400 "Invalid pagination: limit must be a positive integer". | PARTNER_API_DEAL_REGISTRATION_PIPELINE_036 step [3/4], staging 2026-09-21, BE v26 @ 0b35609. The positive TC _035 passes: partnerId, status and dealType all narrow correctly and limit=1 caps the page. | QA (automation) | 2026-09-21 |  | Impact is a full-table dump per request, not just a validation gap — worth checking whether other list endpoints share the same pagination guard.
BUG-API-026 | 2060908 | PARTNER_API_PARTNER_PORTAL_008 | Partner | PARTNER_PORTAL | Major | P2 | CLOSE | GET /v1/partner/portal/modules: groupByCategory=true returns rows that are only {"_id": "undefined"}, and no pagination value is validated (limit=-1, limit=0 and page=abc all answer 200 with the whole catalogue). | groupByCategory=true returns usable groups (a category name and its modules). Nonsensical pagination is refused with 400 — GET /v1/sa/deals already refuses limit=-1, so the service knows how to do this. | GET /portal/modules?groupByCategory=true -> 200, total=23, data[] holds 10 objects each exactly {"_id": "undefined"} — the literal JS string "undefined", no name, no members. GET /portal/modules?limit=-1 -> 200 (1 row); ?limit=0 and ?page=abc -> 200 with all 23 rows. | PARTNER_API_PARTNER_PORTAL_008 steps [4/5] and [5/5], staging 2026-09-21, BE v26 @ 0b35609. The positive TC _007 passes: the plain catalogue, the name filter, and both team-certification filters all narrow correctly. | QA (automation) | 2026-09-21 |  | The pagination half is the same class as BUG-API-025 on /v1/sa/deals but a different endpoint and stricter: /sa/deals at least refuses limit=-1, this one refuses nothing.
BUG-API-027 | 2061510 | PARTNER_API_CLIENT_HEALTH_MSP_010 | Partner | CLIENT_HEALTH_MSP | Minor | P3 | Open | GET /v1/partner/portal/clients: limit=0 and page=abc are not validated and answer 200. limit=-1 IS refused with 400, so the guard exists on this very endpoint and simply misses the other two values. | A nonsensical page size or page number is refused with 400, consistently with limit=-1 on the same endpoint and with GET /v1/sa/deals. | GET /portal/clients?limit=-1 -> 400 (correct). ?limit=0 -> 200. ?page=abc -> 200. Both returned 0 rows, but only because the caller had no clients: the value was accepted rather than rejected, so the row count proves nothing about the guard. | PARTNER_API_CLIENT_HEALTH_MSP_010 step [4/4], staging 2026-09-21, BE v26 @ 0b35609. The rest of the TC passes: a ghost attribution id and a malformed id are both refused with 400 and neither refusal leaks client row fields. The positive TC _001 passes in full, including JWT scoping (a partnerId in the query does not widen the result). | QA (automation) | 2026-09-21 |  | Third endpoint with the same root cause, after BUG-API-025 (/v1/sa/deals) and BUG-API-026 (/v1/partner/portal/modules) — worth ONE shared fix rather than three. Severity is lower here only because this list is empty on staging (no attribution is reachable, G2); the same miss on /sa/deals dumps 1406 rows in a single page, so the impact returns as soon as a partner owns clients.
BUG-API-028 | 2061613 | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_013 | Partner | TENANT_PROVISIONING_ATTRIBUTION | Major | P2 | CLOSE | GET /v1/sa/partner-attributions: limit=0 and page=abc are not validated and answer 200 with the whole ledger. limit=-1 IS refused with 400, so the guard exists on this very endpoint and misses the other two values. | A nonsensical page size or page number is refused with 400, consistently with limit=-1 on the same endpoint. | GET /v1/sa/partner-attributions?limit=-1 -> 400 "Invalid pagination: limit must be a positive integer" (correct). ?limit=0 -> 200 with all 10 rows. ?page=abc -> 200 with all 10 rows. Unlike the portal twin this list is NOT empty, so the caller receives the entire SA-wide ledger in one page. | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_013 step [4/4], staging 2026-09-23, BE v26. The rest of the TC passes: status/clientLifecycleState outside the enum -> 400 listing the allowed values, malformed partnerId and malformed attribution id -> 400, ghost partnerId -> 200 empty, ghost attribution id -> 400. The positive TC _012 passes in full (10 rows across 6 distinct partners, partnerId filter narrows 10 -> 1, detail route returns the requested row). | QA (automation) | 2026-09-23 |  | FOURTH endpoint with the identical root cause: BUG-API-025 (/v1/sa/deals), BUG-API-026 (/v1/partner/portal/modules), BUG-API-027 (/v1/partner/portal/clients), now this one. Every instance refuses limit=-1 and accepts limit=0 and page=abc, which points at one shared pagination validator rather than four separate misses. Recommend BE fix it once at that layer and close all four together.
BUG-API-029 | 2060910 | PARTNER_API_PARTNER_PORTAL_010 | Partner | PARTNER_PORTAL | Major | P2 | CLOSE | GET /v1/partner/portal/plans/{planId}: the path parameter named planId is the only value it will NOT accept. The route matches on the mongo _id; a plan's own planId slug answers 400 'Invalid id'. | The parameter documented by the route's own @ApiParam as a 'Kebab-case plan key, e.g. pro-annual' resolves the plan. Either the implementation should query { planId: <slug> }, or the route, @ApiParam and the service docstring should all say _id. | GET /portal/plans returns rows carrying both _id and planId. GET /portal/plans/6aa76eab1e7d8bcb2279dd3f (the _id) -> 200 with the plan. GET /portal/plans/full-modules-ss (that same row's planId) -> 400 "Invalid id: 'full-modules-ss'". partner-lookup.service.ts getPlanByPlanId queries { _id: planId, status: PUBLISHED } while its docstring says 'Fetches a published billing plan by its planId slug'. | PARTNER_API_PARTNER_PORTAL_010 step [2/4], staging 2026-09-23, BE v26. The rest of the pair passes: _009 verifies the catalogue is published standard editions only with unique ids/slugs and an exact detail match by _id; _010 confirms a ghost key -> 404 naming it and 'not-a-plan'/'%20'/'null' -> 400. ¦ PROBE 2026-09-28 (live): GET /v1/partner/portal/plans/{_id=6aa76eab1e7d8bcb2279dd3f} -> 200 (returns the plan); GET /v1/partner/portal/plans/{planId='full-modules-ss'} -> 400 'Invalid id: full-modules-ss'. Same plan object carries BOTH _id (ObjectId) and planId (slug); the catalogue returns planId as a field and the route is declared plans/:planId with @ApiParam=slug, but the service queries {_id: param} so only the ObjectId is accepted. Confirmed BE contract bug (NOT test-data): the param named planId is the one value it rejects. | QA (automation) | 2026-09-23 |  | Contract-level, not a crash: the deal-registration form works because it passes _id. The cost is that any client written from the OpenAPI spec fails 100% of the time, and the naming actively misleads - a reader has no way to tell from the route that planId means _id. Low fix cost either way; BE only needs to decide which side is authoritative. NOT related to the pagination family (BUG-API-025/026/027/028). ¦ FIX (BE): either (a) accept the slug on plans/:planId (query {planId: param} or fall back), matching the param name + OpenAPI docs [expected per spec]; or (b) rename param to :id + document ObjectId and have callers use _id.
BUG-API-030 | 2060324 | PARTNER_API_COMMISSIONS_PAYOUTS_024 | Partner | COMMISSIONS_PAYOUTS | Minor | P3 | CLOSE | GET /v1/partner/portal/commissions: limit=0 and page=abc are not validated and answer 200. limit=-1 IS refused with 400 on the same endpoint. | A nonsensical page size or page number is refused with 400, consistently with limit=-1 on the same endpoint. | ?limit=-1 -> 400 'Invalid pagination: limit must be a positive integer' (correct). ?limit=0 -> 200. ?page=abc -> 200. Both returned 0 rows, but only because no commission exists anywhere on staging (G1): the value was accepted rather than rejected, so the row count proves nothing about the guard. | PARTNER_API_COMMISSIONS_PAYOUTS_024 step [3/3], staging 2026-09-24, BE v26. The rest of the pair passes: status='bogus' -> 400 listing all eight statuses; the positive TC _020 passes in full (envelope, all 8 status values accepted, ledger agrees with its summary, a partnerId in the query does not widen the JWT scope). | QA (automation) | 2026-09-24 |  | FIFTH endpoint with the identical root cause: BUG-API-025 (/v1/sa/deals), 026 (/v1/partner/portal/modules), 027 (/v1/partner/portal/clients), 028 (/v1/sa/partner-attributions), now this one. Every instance refuses limit=-1 and accepts limit=0 and page=abc. Five independent misses of the same two values is not plausible - this is one shared pagination validator, and one fix at that layer should close all five together. Filed separately only so each failing TC has its own traceable row; recommend BE treat 025/026/027/028/030 as a single defect.
BUG-API-031 | 2061402 | PARTNER_API_PARTNER_TEAM_002 | Partner | PARTNER_TEAM | Major | P2 | CLOSE | Partner team directory read-by-id ignores the path parameter: a ghost (well-formed, absent) userId is not rejected, and a malformed userId is not rejected. | GET /v1/partner/directory/users/{userId}: a ghost (well-formed but non-existent) userId -> 404 not found; a malformed userId -> 400 invalid id. | ghost userId 000000000000000000000000 -> HTTP 200 returning a DIFFERENT user (userId=6aba0a4b...); malformed userId 'not-an-id' -> HTTP 200. The path parameter is ignored, so a caller reading a member it never asked for gets no error at all. | FAIL test_partner_api_partner_team_002 (run 2026-09-28): 'Validation gaps on /v1/partner/directory/users: ghost userId 000...000 returned HTTP 200 with userId=6aba0a4b... instead of 404; malformed userId not-an-id returned HTTP 200 instead of 400.' | AI Triage | 2026-09-28 |  | Negative counterpart of BUG-API-022 (2061401) - SAME root cause: GET /directory/users/{userId} ignores the path param. Fix together with BUG-API-022/023.
BUG-API-032 | 2061404 | PARTNER_API_PARTNER_TEAM_004 | Partner | PARTNER_TEAM | Major | P2 | Open | Team member deals/commissions read ignores the path parameter: a ghost/malformed userId is not rejected (reads as a member with no records). | GET /v1/partner/directory/users/{userId}/{deals,commissions}: a ghost userId -> 404 not found; a malformed userId -> 400 invalid id. | ghost userId -> HTTP 200 with 0 rows (expected 404); malformed userId -> HTTP 200 with 0 rows (expected 400). Path param ignored -> a non-existent member reads as one that simply has no records; the same call returns ANOTHER member's deals when there ARE any (see BUG-API-023 / _003) = cross-member data disclosure risk. | SOFT FAIL ¦ [5/6] Ghost and malformed userId -> expect 404 / 400 -- [5/6] ghost userId answered 200 with 0 row(s), expected 404 - the path parameter is ignored (BUG-API-023) ¦ [5/6] malformed userId answered 200 with 0 row(s), expected 400 - the path parameter is ignored (BUG-API-023). Re-confirmed run_20261009_144113. | AI Triage | 2026-09-28 |  | Negative counterpart of BUG-API-023 (2061403) - SAME root cause: GET /directory/users/{userId}/{deals,commissions} ignores the path param. Fix together with BUG-API-022/023.
BUG-API-033 | 2061602 | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 | Partner | TENANT_PROVISIONING_ATTRIBUTION | Critical | P1 | Open | Winning a deal never provisions a tenant on staging. After a successful win (status=won, message 'tenant provisioning kicked off'), the async provision chain never completes: provisioningState stays 'awaited', wonTenantId and goLiveAt are never stamped. Across ALL staging deals byProvisioningState.resolved=0 (won=262, overdue=117, awaited=3) — i.e. 0/262 won deals have ever provisioned. | After win, the event-driven chain (blazeup.partner.deal.won -> ms-sa-partners -> SA /internal/tenants/provision -> blazeup.tenant.provisioned) completes within a bounded time: wonTenantId + goLiveAt stamped on the WON deal, provisioningState -> resolved, tenant appears in SA Tenant Management, admin creds email sent. (PRD v1.8 §7.1 Referral Close -> Provision Flow; partner_requirement §7.1 BE=Done.) | Deal _id 6a44cd20ce54e808583cf38c (UI 583CF38C, reseller) won 2026-10-01 09:21:04Z. GET /v1/sa/deals/{id}: provisioningState='awaited', wonTenantId=null, goLiveAt=null; updatedAt frozen = closedAt (09:21:04Z) even 15+ min later -> nothing written to the deal after win. GET /v1/sa/deals/stats byProvisioningState = {awaited:3, overdue:117, resolved:0, legacy_unknown:0}, won=262. | GET /v1/sa/deals/{id} + GET /v1/sa/deals/stats, staging 2026-10-01, BE v26.9. approve+win both succeed via API (approve needs plan catalog _id; win needs adminPhoneNumber{number,countryCode}). TCs PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 and _007 BLOCKED on this. Polled 95s + re-checked 15min: no change. | QA (automation) | 2026-10-02 |  | Raised at Khoa's (BE) request. BLOCKER for the entire commission test group (A/B/C): provisioning is upstream of billing/payment/accrual, so commission cannot be reached until this is fixed (goLiveAt is required for the accrual eligibility window). partner_requirement §7.1 marked BE=Done but no deal provisions on staging -> the provisioning worker (deal.won consumer -> /internal/tenants/provision -> the tenant.provisioned consumer that stamps wonTenantId/goLiveAt) appears not running/deployed on staging. No public endpoint exists to trigger provision manually; /v1/sa/deals/{id}/link-tenant only links an already-provisioned tenant.
BUG-API-034 | 2060413 | PARTNER_API_TERRITORIES_013 | Partner | TERRITORIES | Major | P2 | CLOSE | list territories invalid filter/pagination - rejected (4xx, never 5xx). | list territories invalid filter/pagination - rejected (4xx, never 5xx). | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | AI Triage | 2026-10-05 | 2026-10-08 | CLOSED 2026-10-08 - NOT A DEFECT (invalid). BE behavior is correct: page=0/page=-1 -> 400 "page must not be less than 1". The TC failed only because the test asserted a stale expected-message hint ("non-negative"); status 400 already matched. Auto-logged by AI Triage on 2026-10-05 when the BE FIXED pagination validation and the old hint stopped matching. Test hint corrected to "must not be less than 1" (2026-10-08); TC now PASSES.
BUG-API-035 | 2060514 | PARTNER_API_CERTIFICATIONS_SA_014 | Partner | CERTIFICATIONS_SA | Major | P2 | CLOSE | list SA certifications invalid filter/pagination - rejected (4xx, never 5xx). | list SA certifications invalid filter/pagination - rejected (4xx, never 5xx). | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | AI Triage | 2026-10-05 | 2026-10-08 | CLOSED 2026-10-08 - NOT A DEFECT (invalid). BE behavior is correct: page=0/page=-1 -> 400 "page must not be less than 1". The TC failed only because the test asserted a stale expected-message hint ("non-negative"); status 400 already matched. Auto-logged by AI Triage on 2026-10-05 when the BE FIXED pagination validation and the old hint stopped matching. Test hint corrected to "must not be less than 1" (2026-10-08); TC now PASSES.
BUG-API-036 | 2060711 | PARTNER_API_PARTNER_USERS_011 | Partner | PARTNER_USERS | Major | P2 | CLOSE | list partner-users invalid pagination/filter - graceful, never 5xx. | list partner-users invalid pagination/filter - graceful, never 5xx. | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | CHECK page=0 → FAIL (status=400, msg="['page must not be less than 1']") | AI Triage | 2026-10-05 | 2026-10-08 | CLOSED 2026-10-08 - NOT A DEFECT (invalid). BE behavior is correct: page=0/page=-1 -> 400 "page must not be less than 1". The TC failed only because the test asserted a stale expected-message hint ("non-negative"); status 400 already matched. Auto-logged by AI Triage on 2026-10-05 when the BE FIXED pagination validation and the old hint stopped matching. Test hint corrected to "must not be less than 1" (2026-10-08); TC now PASSES.
BUG-API-037 | 2060102 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_002 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Major | P2 | CLOSE | POST create internal partner - a pending account is created. | status (201,) | 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | FAIL ¦ [1/5] Call API: POST /v1/sa/partners (create 'QA-AUTO Obrien, Burton and Grant') (393ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | AI Triage | 2026-10-05
BUG-API-038 | 2060103 | PARTNER_API_PARTNER_ACCOUNT_MANAGEMENT_003 | Partner | PARTNER_ACCOUNT_MANAGEMENT | Major | P2 | CLOSE | POST partner approve - activation + approval event are created. | status (201,) | 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | FAIL ¦ [1/5] Call API: POST /v1/sa/partners (create 'QA-AUTO Obrien, Burton and Grant') (393ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | AI Triage | 2026-10-05
BUG-API-039 | 2060201 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_001 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P2 | CLOSE | register a partner deal - deal is created (registered). | status (201,) | 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | FAIL ¦ [1/5] Call API: POST /v1/sa/partners (create 'QA-AUTO Obrien, Burton and Grant') (393ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | AI Triage | 2026-10-05
BUG-API-040 | 2060208 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_008 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P2 | CLOSE | internal deal approve - approved + rate/rate-table version stamped. | status (201,) | 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | FAIL ¦ [1/5] Call API: POST /v1/sa/partners (create 'QA-AUTO Obrien, Burton and Grant') (393ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | AI Triage | 2026-10-05
BUG-API-041 | 2060218 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_018 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P2 | CLOSE | SA marks an approved deal as won - status 'won' + provisioning/commission events emitted. | status (201,) | 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | FAIL ¦ [1/5] Call API: POST /v1/sa/partners (create 'QA-AUTO Obrien, Burton and Grant') (393ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"The requester cannot be an approver on their own request","error":"Bad Request","timestamp":"2026-10-05T09:26:43.400Z","pat | AI Triage | 2026-10-05 | 2026-10-13 | CLOSED 2026-10-13 - NOT A BUG (test-side, no BE change). The 400 'The requester cannot be an approver on their own request' was the BE correctly enforcing the new approval chain: the test created a partner and approved it with the SAME SA account. Fixed in automation by assigning a separate QA approver (pytest_support/approval.py + ADMIN2). TC-2060218 still fails, now at [1/4] for a DIFFERENT cause - see BUG-API-043.
BUG-API-042 | 2061510 | PARTNER_API_CLIENT_HEALTH_MSP_010 | Partner | CLIENT_HEALTH_MSP | Minor | P3 | Open | GET /v1/partner/portal/clients/:id returns 404 for a MALFORMED (non-ObjectId) id instead of 400. The route skips id-format validation and treats a malformed id as 'not found', inconsistent with the SA :id routes. | A malformed (non-ObjectId) path id is rejected with 400 'Invalid id' (format validated before the existence/ownership check), consistent with /sa/partners/:id and the deal :id routes. A 400 for a malformed id does NOT weaken the no-existence-oracle property, which only requires ghost == foreign == 404. | GET /v1/partner/portal/clients/not-an-id -> 404 'Client not-an-id not found' (staging 2026-10-06). A well-formed ghost id and a real foreign id both correctly return 404; only the malformed-id case is wrong (should be 400). | PARTNER_API_CLIENT_HEALTH_MSP_010 step [3/5], staging 2026-10-06 (run_20261006_134511). Rest of the TC passes (ghost->404, foreign->404 identical no-oracle, pagination limit=-1/0 & page=abc->400). -- [3/5] a malformed attribution id answered 404, expected 400 | QA | 2026-10-06 |  | Split from BUG-API-027 (pagination limit=0/page=abc -> 200), which is now FIXED (limit=0 -> 400) -> close BUG-API-027. This is the DISTINCT remaining cause on the same TC (2061510), surfaced by the triage 'signature changed' detection. Low severity: no data leak, no crash -- a status-code/contract inconsistency only (should mirror the SA endpoints' 400 'Invalid id'). Confirm with BE whether portal /clients/:id should validate id format (400) or intentionally returns 404 uniformly.
BUG-API-043 | 2061602 | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 | Partner | TENANT_PROVISIONING_ATTRIBUTION | Critical | P1 | Open | POST /v1/sa/deals/{id}/win is UNCALLABLE: billingCycle case mismatch between WinDealDto (lowercase monthly¦annual) and the downstream provisioning intake (UPPERCASE MONTHLY¦ANNUAL). No value satisfies both validators, so an approved deal can no longer be won at all. | Winning an approved deal with the DTO-documented billingCycle ('annual') returns 201 and status 'won' — the BE normalizes/maps the value when building the provisioning intake (e.g. toUpperCase), or the two enums use the same casing. | billingCycle='annual' -> 400 'Tenant provisioning failed: [INVALID_PAYLOAD] intake.billingCycle: billingCycle must be one of the following values: MONTHLY, ANNUAL'. billingCycle='ANNUAL' -> 400 'billingCycle must be one of the following values: monthly, annual' (WinDealDto refuses it before provisioning). Both verified on staging 2026-10-06. | PARTNER_API_TENANT_PROVISIONING_ATTRIBUTION_002 step [1/4], staging 2026-10-06 (run_20261006_154346). Sending 'ANNUAL' instead is refused by WinDealDto itself: 400 ['billingCycle must be one of the following values: monthly, annual'] (run_20261006_155040), so no value satisfies both validators. FAIL ¦ [1/4] Mark the approved deal as won (win intake incl. required adminPhoneNumber) -> status 'won' (321ms) -- AssertionError: Expected status (201,), got 400: {"statusCode":400,"message":"Tenant provisioning failed: [INVALID_PAYLOAD] intake.billingCycle: billingCycle must be one of the following values: MONTHLY, ANNUAL","error":"Tenant provisioning failed: [INVALID_PAYLOAD] intake.billingCycle: billingCycle must be one of the following values: MONTHLY, ANNUAL","timestamp":"2026-10-06T08:43:53.300Z","path":"/sa-partners-api/v1/sa/deals/6ac4b4c8d1eeecba2e946c97/win"} | QA | 2026-10-06 |  | REGRESSION: win returned 201 and reached status 'won' on 2026-10-02 (same TC). The BE has since wired the provisioning call into /win and now surfaces its INVALID_PAYLOAD, but the two enums disagree on case. BLOCKS the whole won -> provision -> bill -> commission chain, and blocks re-verifying BUG-API-033 (provisioning never completes) because win can no longer succeed. Also note register stores billingCycle lowercase ('annual'), so the lowercase form is the one the deal itself carries. Fix: normalize the value when mapping WinDealDto -> provisioning intake, or align the enums. Surfaced by the triage 'signature changed' detection (the old BUG-API-033 cause no longer reproduces).
BUG-API-044 | 2060221 | PARTNER_API_DEAL_REGISTRATION_PIPELINE_021 | Partner | DEAL_REGISTRATION_PIPELINE | Major | P2 | CLOSE | register deal invalid/missing fields - rejected with 400. | register deal invalid/missing fields - rejected with 400. | CHECK ghost planId (verified absent above) → FAIL (status=403, msg='Partner account is not active') | CHECK ghost planId (verified absent above) → FAIL (status=403, msg='Partner account is not active') | AI Triage | 2026-10-08
BUG-API-045 | 2061009 | PARTNER_API_AUTH_ACCESS_CONTROL_009 | Partner | AUTH_ACCESS_CONTROL | Minor | P2 | Open | Partner login answers 400 instead of 401 for invalid credentials (wrong or no-longer-valid password). | POST /v1/partner/auth/login with a wrong or no-longer-valid password -> 401 Unauthorized (failed authentication). This is what it returned until 2026-10-09, and what the rest of the partner auth module still returns: change-password with a wrong current password -> 401, invalid refresh token -> 401, missing token -> 401. | 400 Bad Request {"message":"Invalid credentials"}. The credential IS rejected - only the status code is wrong. Seen on every failed partner login in run_20261014_133423 (5 TCs). Account lockout also answers 400 ("Too many failed login attempts"). | FAIL ¦ [4/4] The OLD password is rejected (401) (746ms) -- AssertionError: old password must be rejected (401), got 400 (run 2026-10-14) | QA | 2026-10-14 |  | ALSO FAILS: TC-2061405 (PARTNER_API_PARTNER_TEAM_005) step [4/8] 'The OLD password must stop working' - rejected with 400 instead of 401 after an admin password reset. Same root cause, so one bug. Changed between 2026-10-09 (401; both TCs PASSED) and 2026-10-13. Swagger documents only 200 for login, so no contract states 400. Minor: behaviour is correct (the old password is refused), the status code is not.
UI
BUG-UI-001 | 12060101 | PARTNER_UI_PARTNER_PORTAL_SHELL_001 | Partner | PARTNER_PORTAL_SHELL | Major | P2 | CLOSE | every primary nav page loads via URL (no MFE error). | every primary nav page loads via URL (no MFE error). |  | Page [apps] FAILED - Partner Portal section 'apps' rendered its shell but the CONTENT failed to load: banner 'Failed to load' is visible in <main>. Data-fetch/backend issue for this page — confirm with BE. | AI Triage | 2026-07-23 | 2026-09-30 | CLOSED 2026-09-30 — no longer applicable: the 'My Apps' page was REMOVED from the partner portal (no nav item; /apps renders a 404 page). 'apps' dropped from the test; PARTNER_UI_PARTNER_PORTAL_SHELL_001 now PASSES 5/5, be_gap removed.
BUG-UI-002 | 12060102 | PARTNER_UI_PARTNER_PORTAL_SHELL_002 | Partner | PARTNER_PORTAL_SHELL | Major | P2 | CLOSE | portal stays usable at mobile width (no h-overflow, nav reachable). | portal stays usable at mobile width (no h-overflow, nav reachable). | Page [deals] FAILED - 'deals' overflows the mobile viewport by 162px (content does not fit 375px → responsive-layout defect; confirm with FE) | Page [deals] FAILED - 'deals' overflows the mobile viewport by 162px (content does not fit 375px → responsive-layout defect; confirm with FE) | AI Triage | 2026-07-24 | 2026-09-30 | FIXED — re-verified 2026-09-30: /deals no longer overflows at 375px (was +162px). My Apps page removed from the portal. TC 12060102 still fails, but ONLY on /directory — a distinct defect logged as BUG-UI-010.
BUG-UI-003 | 12060203 | PARTNER_UI_MY_PIPELINE_003 | Partner | MY_PIPELINE | Major | P2 | CLOSE | an invalid domain must be rejected with a format error. | an invalid domain must be rejected with a format error. | FAIL ¦ [1/1] Each malformed domain must be rejected (block Next / flag field) (246ms) -- AssertionError: wizard accepts invalid domain(s) ["'@@@' (field kept '@@@', Next enabled, not flagged)", "'ab cd' (field kept 'ab cd', Next enabled, not flagged) | FAIL ¦ [1/1] Each malformed domain must be rejected (block Next / flag field) (246ms) -- AssertionError: wizard accepts invalid domain(s) ["'@@@' (field kept '@@@', Next enabled, not flagged)", "'ab cd' (field kept 'ab cd', Next enabled, not flagged)", "'notadomain' (field kept 'notadomain', Next en | AI Triage | 2026-07-27 | 2026-09-30 | FIXED — re-verified 2026-09-30: the Domain field now validates ('Use letters, numbers, and hyphens only — no dots or symbols, e.g. my-company'). Test inputs corrected: 'notadomain' removed (VALID under the rule) and replaced with 'acme.com'. PARTNER_UI_MY_PIPELINE_003 PASSES, be_gap removed.
BUG-UI-004 | 12060207 | PARTNER_UI_MY_PIPELINE_007 | Partner | MY_PIPELINE | Major | P2 | CLOSE | a malformed contact email must be rejected with a format error. | a malformed contact email must be rejected with a format error. | FAIL ¦ [1/1] Each malformed email must be rejected (block Next / flag field) (246ms) -- AssertionError: wizard accepts malformed email(s) ["'notanemail' (field kept 'notanemail', Next enabled, not flagged)", "'abc@' (field kept 'abc@', Next enabled, | FAIL ¦ [1/1] Each malformed email must be rejected (block Next / flag field) (246ms) -- AssertionError: wizard accepts malformed email(s) ["'notanemail' (field kept 'notanemail', Next enabled, not flagged)", "'abc@' (field kept 'abc@', Next enabled, not flagged)", "'abc@x' (field kept 'abc@x', Next | AI Triage | 2026-07-27
BUG-UI-005 | 12060507 | PARTNER_UI_SA_PARTNER_MODULE_007 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | SA Deal Approval Queue (/partners/deals): deal-list API consistently returns "Server Error - Invalid id: pro-v1" instead of the deals. | GET deal-list for /partners/deals returns the deals (200); the queue table shows deal rows. No "Invalid id" error. | The deal-list fetch consistently returns "Server Error - Invalid id: pro-v1"; the UI shows "No Data Found" and no deal rows load (partners DO have open deals). | FAIL ¦ [3/3] The Pending Approval + Conflicts queues load without a server error (3161ms) -- AssertionError: the deal approval queues must load their deals, but the deal-list fetch fails with a backend error on: ['Pending Approval: "Server Error Invalid id: \'pro-v1\' Server Error Invalid id: \'"', | AI Triage | 2026-07-29 | 2026-08-10 | FIXED — re-verified 2026-08-10: PARTNER_UI_SA_PARTNER_MODULE_007 now PASSES (15.3s, log: 'CHECK deals load -> OK (no server error)'). The deal-list fetch no longer returns "Invalid id: 'pro-v1'". be_gap marker removed from the test and the registry re-synced, so this TC is back inside the merge gate. ¦ Root cause = contract drift: a plan-slug "pro-v1" (string) is used where the API expects a Mongo _id (24-hex), so deal-list id validation fails. CONSISTENT, not intermittent (updated 2026-08-05): earlier "lucky PASS" runs were a TEST race - the assertion ran before the async deal-list error painted; the test now waits for the fetch to settle and fails deterministically. UI test 12060507 renders fine (shell/filters/headers OK); this step reflects the BE defect. Fix BE so deal-list never returns Invalid id: pro-v1.
BUG-UI-006 | 12060511 | PARTNER_UI_SA_PARTNER_MODULE_011 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | the SA partner-programme analytics dashboard. | the SA partner-programme analytics dashboard. | FAIL ¦ [3/3] The analytics data loads without a server error (44ms) -- AssertionError: the analytics dashboard must load its data, but a query fails with a backend error: 'Server Error limit must not be greater than 100 Server Error Invalid p'. The d | FAIL ¦ [3/3] The analytics data loads without a server error (44ms) -- AssertionError: the analytics dashboard must load its data, but a query fails with a backend error: 'Server Error limit must not be greater than 100 Server Error Invalid p'. The dashboard shell renders but a paginated analytics q | AI Triage | 2026-07-29
BUG-UI-007 | 12060405 | PARTNER_UI_DASHBOARD_005 | Partner | DASHBOARD | Major | P2 | Open | tier-qualification math (T12M ARR threshold + next-tier delta). | tier-qualification math (T12M ARR threshold + next-tier delta). | FAIL ¦ [2/3] Next-tier T12M ARR threshold target + remaining delta are shown (0ms) -- AssertionError: the next-tier T12M ARR threshold target and remaining delta must be shown in Tier Progress, but only current tier/ARR/deal-count are rendered (panel | FAIL ¦ [2/3] Next-tier T12M ARR threshold target + remaining delta are shown (0ms) -- AssertionError: the next-tier T12M ARR threshold target and remaining delta must be shown in Tier Progress, but only current tier/ARR/deal-count are rendered (panel='Tier & Performance SELECT T12M ARR USD 0 Tier Pr | AI Triage | 2026-07-30
BUG-UI-008 | 12060515 | PARTNER_UI_SA_PARTNER_MODULE_015 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | suspend (deactivate) an active partner. | SA can suspend an Active partner from Partner Detail -> Partner actions -> Deactivate: partner transitions to Suspended/Inactive and loses portal access. | Deactivate fails. The "Deactivate Partner" confirm dialog collects NO reason, so the FE calls the deactivate API without one; BE returns 400 Server Error ("reason should not be empty / reason must be a string / reason must be <= 2000 characters"). Partner stays Active. No SA can suspend a partner via the UI. | FAIL ¦ [2/2] The partner is suspended and no error is shown (0ms) -- AssertionError: Deactivate failed — the BE rejected the request: 'Failed to deactivate partner Server Error reason must be shorter than or equal to 2000 charactersreason should not be emptyreason must be a string Partner approved Q | AI Triage | 2026-07-31 | 2026-09-30 | FIXED — re-verified 2026-09-30: the Deactivate Partner dialog now has a required Reason textarea (Deactivate disabled until filled); the request succeeds and the partner becomes Suspended. PARTNER_UI_SA_PARTNER_MODULE_015 PASSES, be_gap removed. Unblocks _016 (reactivate). ¦ FE<->BE contract mismatch. Fix options: (a) add a required Reason textarea to the Deactivate dialog and send it, or (b) make reason optional on the deactivate API. Repro: onboard partner -> Approve -> Partner actions -> Deactivate -> Confirm. Blocks SA_PARTNER_MODULE_016 (reactivate) too. TC marked be_gap.
BUG-UI-009 | 12060201 | PARTNER_UI_MY_PIPELINE_001 | Partner | MY_PIPELINE | Critical | P1 | CLOSE | Register-a-Deal wizard: Country dropdown is empty ('No options') on Chrome/Chromium (works on Edge). The wizard's countries lookup is sent WITHOUT an Authorization header -> 401, so no country can be selected and a deal cannot be registered. | On every browser (incl. Chrome) the Country dropdown lists countries; partner completes Step 1 and registers a deal. | On Chrome/Chromium (manual AND automation), GET /sa-partners-api/v1/partner/portal/countries is sent with NO Authorization header -> 401 -> dropdown shows 'No options' -> Step 1 cannot be completed. On Edge (manual) the same request carries the bearer token -> 200 -> options load. | countries request hasAuth=false -> 401 on Chromium (Playwright) and manual Chrome; 200 on manual Edge. Shell /partner/auth/refresh + /auth/me return 200, so the shell is authenticated but the token is not attached to the MFE's countries call. Manual repro: Chrome FAIL / Edge PASS. | tam.do@terralogic.com | 2026-09-28 | 2026-09-30 | FIXED — verified manually by QA on 2026-09-30 (ticket BLAZ7-5-27 PV VALIDATION → CLOSED): Country dropdown loads on Chrome. ¦ Browser-specific (Chrome/Chromium FAIL, Edge PASS) at BOTH manual and automation level. Affects all 11 register-wizard TCs: 12060201-12060208, 12060211-12060213 (automation runs on Chromium -> all fail). Leading hypothesis for FE: Chrome's stricter storage-partitioning / third-party-context defaults block the deals micro-frontend (partnerDealsApp, which has its own token-store bundle) from reading the auth token (pp_refresh_token in sessionStorage) -> token not attached to the countries request. FE to verify how partnerDealsApp obtains/attaches the access token on Chrome. NOTE: AI triage mislabels these as [FLAKY] (Locator.click-timeout heuristic) - they are deterministic, not flaky.
BUG-UI-010 | 12060102 | PARTNER_UI_PARTNER_PORTAL_SHELL_002 | Partner | PARTNER_PORTAL_SHELL | Major | P2 | CLOSE | Partner Portal /directory overflows horizontally at mobile width (375px): the 'Invite User' button and the member table do not fit, so the whole page scrolls sideways. | At 375×812 the Directory page fits the viewport (horizontal overflow ≤ 5px); the member table scrolls inside its own container if it is wider than the screen. | The page overflows by +93px (scrollWidth 468 vs 375): the 'Invite User' button sticks out 93px and the member table (MEMBER / ROLE / STATUS / LAST LOGIN) is ~607px wider than the viewport with no overflow-x wrapper. | Page [directory] FAILED - 'directory' overflows the mobile viewport by 93px (content does not fit 375px → responsive-layout defect; confirm with FE) ¦ probe: documentElement.scrollWidth=468 vs clientWidth=375; 'Invite User' button right edge +93px; member <table> right edge +607px (no overflow-x container) | QA | 2026-09-30 |  | Distinct from BUG-UI-002 (Deals overflow, now fixed) — same TC, different page/cause, kept as its own bug. Other pages (dashboard/deals/commissions/resources) fit. Fix: wrap the member table in an overflow-x:auto container and let the header action bar wrap/stack on small screens.
BUG-UI-011 | 12060514 | PARTNER_UI_SA_PARTNER_MODULE_014 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | add a portal user (member) to a partner. | add a portal user (member) to a partner. | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (41791ms) -- AssertionError: Onboard Partner did not settle within 30000 ms (no success toast and the form is still open). | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (41791ms) -- AssertionError: Onboard Partner did not settle within 30000 ms (no success toast and the form is still open). | AI Triage | 2026-10-05
BUG-UI-012 | 12060515 | PARTNER_UI_SA_PARTNER_MODULE_015 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | suspend (deactivate) an active partner. | suspend (deactivate) an active partner. | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (41791ms) -- AssertionError: Onboard Partner did not settle within 30000 ms (no success toast and the form is still open). | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (41791ms) -- AssertionError: Onboard Partner did not settle within 30000 ms (no success toast and the form is still open). | AI Triage | 2026-10-05
BUG-UI-013 | 12060514 | PARTNER_UI_SA_PARTNER_MODULE_014 | Partner | SA_PARTNER_MODULE | Major | P2 | CLOSE | add a portal user (member) to a partner. | add a portal user (member) to a partner. | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (40048ms) -- TimeoutError: Locator.click: Timeout 30000ms exceeded. | FAIL ¦ Setup: onboard a throwaway partner and approve it to Active (40048ms) -- TimeoutError: Locator.click: Timeout 30000ms exceeded. | AI Triage | 2026-10-09 | 2026-10-15 | CLOSED 2026-10-15 - NOT A BUG (test-side; design change). Raised by AI Triage from a setup timeout. Since the approval-chain redesign the 'Partner actions' menu is STATE-GATED: it shows on an Active partner (verified 2026-10-15 on PAR-878984) but not on a Pending one, whose detail page now has an 'Approval chain' panel (0/N approved, approver, Configure) instead. The setup still tried 'Partner actions -> Approve' on a freshly onboarded Pending partner, so it timed out. The creator may not approve its own partner anyway; the setup must approve through the QA approver (API approval library). Same cause failed TC 12060513 [3/3] and TC 12060515 setup.
BUG-UI-014 | 12060403 | PARTNER_UI_DASHBOARD_003 | Partner | DASHBOARD | Major | P2 | Open | Partner dashboard is missing the Tier Progress card - PRD 4.3 design rule 'Tier progress bar is always visible' is not met. | /dashboard shows a Tier Progress card: progress bar, current tier -> next tier, and '$<T12M ARR> of $<next-tier threshold> <next tier>' (PRD 4.3; requirement sheet 4.3 'Tier progress bar'; backlog PP002 'Header: tier badge + T12M ARR progress'). | Since the 2026-10 dashboard redesign no Tier Progress element is rendered anywhere on /dashboard. Only the header tier badge ('Registered') remains; the new 'Performance' panel shows deal counts + win rate only. Last seen rendered 2026-10-09 (old 'Tier & Performance' panel). | FAIL ¦ [1/2] Tier Progress shows current tier + 'working towards' next tier (15ms) -- AssertionError: the Tier Progress component must be present (run_20261013_114021) | QA | 2026-10-13 |  | Same root cause also fails TC-12060407 step [3/3] ('Tier Progress' must still be highlighted). Kept SEPARATE from BUG-UI-007 (TC-12060405: tier card present but threshold/delta not shown) - 1 bug per distinct failure. Likely FE-only: GET /v1/partner/portal/dashboard already returns partner.tier='registered' + totalArrCents (run_20261013_103101); tier thresholds are fixed by requirement 2.1 (Select $50K / Advanced $200K / Premier $750K).